## TO 190 Summary
STPSat 6 Antenna Ground Equipment and Satellite Operations Center – Materials | WBS | Awarded Amount to Date | Estimate to Complete for Materials & Milestone Payments (MODS 7, 8) | Materials planned for procurement for Mod 0 & Milestone Payments | Materials planned for procurement for Mod 1 & Milestone Payments | Materials planned for procurement for Mod 2 & Milestone Payments | Materials planned for procurement for Mod 3 & Milestone Payments | Materials planned for procurement for Mod 4 & Milestone Payments | Materials planned for procurement for Mod 5 & Milestone Payments | Materials planned for procurement for Mod 6 & Milestone Payments | Materials planned for procurement Mod 7 & Milestone Payments | Materials planned for procurement PENDING Mod 8 & Milestone Payments | Materials planned for procurement PENDING Mod 9 & Milestone Payments | PO Issued Cost for Materials Mod 0 & Milestone Payments | PO Issued Cost for Materials Mod 1 & Milestone Payments | PO Issued Cost for Materials Mod 2 & Milestone Payments | PO Issued Cost for Materials Mod 3 & Milestone Payments | PO Issued Cost for Materials Mod 4 & Milestone Payments | PO Issued Cost for Materials Mod 5 & Milestone Payments | PO Issued Cost for Materials Mod 6 & Milestone Payments | PO Issued Cost for Materials Mod 7 & Milestone Payments | PO Issued Cost for Materials Mod 8 & Milestone Payments | Comments
PMO | 1 | 80984.96 | [20 empty] | -
Reserved | 2 | 0 | [20 empty] | -
SABEL (materials) | 3 | 6362207 | 476180.93 | 1354399.252 | 2232 | 814122.876 | 105623.27 | 2950 | 7642.46 | 0 | -307772 | 265250.48 | 210930.45 | 812170.26 | 2212 | 620566.94 | 104303.27 | 2950 | 7342.72 | 0 | 0 | 0
SABEL (milestone payments) | 3 |  | 0 | 0 | 0 | 3329082 | 0 | 129601.88 | 369898 | 507075 | 0 | 0 | 0 | 0 | 0 | 924745 | 0 | 0 | 39427.3 | 0 | 0 | 0
SSOC (materials) | 4 | 886427 | 75520.45 | 415868.73 | 225103.43 | 92785.94 | 96343.18 | 0 | 56325.38 | 0 | 0 | 0 | 75520.45 | 332435.37 | 144692.71 | 65030.13 | 148116.22 | 0 | 39427.3 | 0 | 0 | 0
SSOC (milestone payments) | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SI (materials) | 5 | 2039561 | 48069.64 | 13170.05 | 0 | 1077415.961 | -24032.51 | 0 | 96062.3 | 0 | 0 | 0 | 48069.64 | 0 | 0 | 693379.04 | 155462.64 | 0 | #REF! | 0 | 0 | 0
SI (milestone payments) | 5 |  | 0 | 0 | 0 | 199122 | 484895.88 | 0 | 192928.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 9369179.96 | 599771.02 | 1783438.032 | 227335.43 | 5512528.777 | 662829.82 | 132551.88 | 722856.26 | 507075 | -307772 | 265250.48 | 334520.54 | 1144605.63 | 146904.71 | 2303721.11 | 407882.13 | 2950 | #REF! | 0 | 0 | 0
[14 empty] | 638832.402 | 80430.72 | 3208807.667 | 254947.69
| Total Materials & Milestones Awarded Mod 0-7 | 9369179.96
| Less PMO | -80984.96
| Awarded Materials & Milestones (0-7) | 9288195 | [5 empty] | As of 04/22/19 | 722856.26 | 507075 | -307772 | 265250.48 | 334520.54 | 1144605.63 | 146904.71 | 2303721.11 | 407882.13 | 2950 | #REF! | 0 | 0 | 0 | 0
| Future Mod 8 (as of 04/22/19) | 265250.48
| Future Mod 9 (as of 04/22/19) | 334520.54
| Total Material & Milestone Database Mods 0-8 | 9887966.02 | [5 empty] | As of 12/03/18 | 737756.71 | 670153 |  | 265250.48 | 334520.54
[8 empty] | As of 11/15/18 | 737756.71 | 865000 |  | 265250.48 | 334520.54
Sanity Check
9968950.98
80984.96
9887966.02
9840614.219
47351.801
Note on K4: Awarded after ME September 2018 Close
Note on L4: Mason, Monika (Peraton) (US Person): Awarded December 2018 (12/11/18)
Note on K7: Mason, Monika (Peraton) (US Person): Forecast for February 2019 - $7,642.46
Note on N7: Mason, Monika (Peraton) (US Person): Forecast for October 2019- $148,004.44 Forecast for December 2019 - $117,246.04
Note on O7: Mason, Monika (Peraton) (US Person): Forecast for June 2020 - $210,930.45
Note on R7: Mason, Monika (Peraton) (US Person): HDR & LDR Milestone Payments 1-3
Note on K8: Mason, Monika (Peraton) (US Person): Forecast for December 2018 - $369,989 Vendor is ViaSat
Note on L8: 12/07/18: Final Proposal updated to $554,427 Forecast February 2019: $221,770.8 Forecast March 2019: $110,885.4 Forecast April 2019: $221,770.8 11/27/18: This amount was updated to $670,153 after receiving RFP's from vendors. Vendor will be selected on 11/30/18. 10/08/18: Forecast for April 2019 $865,000 Vendor is TBD
Note on R8: Mason, Monika (Peraton) (US Person): Viasat Payments 1&2
Note on K9: Mason, Monika (Peraton) (US Person): Forecast for December 2018 - $41,917.41 Forecast for February 2019 - $14,407.97
Note on O9: Mason, Monika (Peraton) (US Person): Forecast for June 2020 - $75,520.45
Note on K11: Mason, Monika (Peraton) (US Person): Forecast for December 2018 - $2,158.25 Forecast for January 2019 - $25,254.01 Forecast for February 2019 - $35,943.86 Forecast for June 2019 - $32,389.0
Note on O11: Mason, Monika (Peraton) (US Person): Forecast for June 2020 - $48,069.64
Note on K12: Mason, Monika (Peraton) (US Person): Forecast for December 2018 - $87694.60 Vendor is C&E Forecast for February 2019 - $96,464.06 Vendor is C&E Forecast for March 2019 - $8,769.46 Vendor is C&E
Note on P15: Mason, Monika (U.S. Person): The difference is between Materials Planned for Procurement for Mod 0 and the Actual Cost for Materials Mod 0.
Note on Q15: Mason, Monika (U.S. Person): The difference is between Materials Planned for Procurement for Mod 1 and the Actual Cost for Materials Mod 1.
Note on R15: Mason, Monika (U.S. Person): The difference is between Materials Planned for Procurement for Mod 2 and the Actual Cost for Materials Mod 2.
Note on S15: Mason, Monika (U.S. Person): The difference is between Materials Planned for Procurement for Mod 3 and the Actual Cost for Materials Mod 3.

## MDB
When do you need procurement to submit? | NASA Increment | WBS | CI List Aware | CI Number | CI Name | Description | Manufacturer/Vendor | ACL LIST | Model Number | Part Number | Vendor | Vendor Part Number | Total Quantity | Ship to | Per Unit Cost | Budgeted Estimate Cost | Actual Unit Cost | PO Issued Cost |  | Variance between the BOE and PO Issued Cost | Purchase Requisition Number | Purchase Order Number | Approved by Dave Zwick | Planned PO Date | Actual PO Date | Need By Date | Estimated Vendor Delivery Date | Received / Acceptance Date | Long Lead Items Over 90 Days | Requiring Maintenance / Licensing Agreements | Remarks | Paid | Paid Amount | ACL List | Forecast January 2019 | Forecast February 2019 | Forecast March 2019 | Forecast April 2019 | Forecast May 2019 | Forecast June 2019 | Forecast July 2019 | Forecast August 2019 | Forecast September 2019
| 0 | 5 | Y |  |  | Dell PowerEdgeR630 1U 500 GB | Dell | [5 empty] | 1 |  | 13170.05 | 13170.05 |  |  | ICT equipment
| 0 | 4 | Y |  |  | Various | [6 empty] | 1 |  | 29380.28 | 29380.28 |  | 0 | ICT equipment
| 0 | 3 | Y | 3.1.2.5 | EM-0058 | HPA -S Band | Communications and power industries Inc. (CPII) |  |  | CKPA, K3S64D |  |  | 1 |  | 478000 | 478000 |  | 473000 | ICT equipment | 5000 | PR-031194-2712 | 442091 |  |  | 2017-10-03 |  | 2018-05-11 | 2019-02-07 | Y - 2/1/17 |  | 10/23/17: Fyi on the S1 HPA. It’s end of May in our IMS now, if/when George provides a different date I’ll pass it on to you. Or if Chris gets it he’ll pass it on to all of us. This has to do with the klystron tubes. 09/6/2017: What is total price? Has one HPA been ordered? Differs from MDB 08/16/17: (Choate) Supposed to be one on order vendor and part info as indicated. Install will be 2 HPA and will purchase 1 as spare (3 total) Item 1, Quantity 2-3, CKPA K3S64D, QTY 3, 2 for the 1:1 system, plus 1 spare, Includes DFTS. Unit Price $118,500 Item 2, Quantity 1, 1:1 Switch System, as per discussion with Dennis Choate. Includes SST Cabinet. Unit Price $95,000 Item 3, Quantity 1, 1RU Remote Control Panel. Unit Price $2,500 Item 4, Quantity 1, Installation Service for on-site installation at NASA White Sands Location. Unit Price $20,000 | Yes | 473000
| 0 | 4 | Y | 4.01 |  | PowerEdge R630 Server | Dell |  |  |  | Dell |  | 2 |  | 9441 | 18882 |  | 20454.62 | ICT equipment | -1572.62 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 20454.62
| 0 | 4 | Y |  |  | EqualLogic PS6210 24 X 2.5" | Dell | [5 empty] | 1 |  | 21516 | 21516 |  | 23335.06 | ICT equipment | -1819.06 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 23335.06
| 0 | 4 | Y |  |  | Wyse 3030 thin client | Dell | [5 empty] | 1 |  | 329 | 329 |  | 335.82 | ICT equipment | -6.82 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 335.82
| 0 | 4 | Y |  |  | Dell UltraSharp 34 Curved Monitor - U3415W | Dell | [5 empty] | 1 |  | 779.99 | 779.99 |  | 699.99 | ICT equipment | 80 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 699.99
| 0 | 4 | Y |  |  | Precision 15 7000 Series (7510) | Dell | [5 empty] | 1 |  | 4172.56 | 4172.56 |  | 1881.75 | ICT equipment | 2290.81 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 1881.75
| 0 | 4 | Y |  |  | PowerEdge R530 Rack Server | Dell | [5 empty] | 2 |  | 3808.94 | 7617.88 |  | 6460.14 | ICT equipment | 1157.74 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 6460.14
| 0 | 4 | Y | 4.02 |  | OptiPlex 7440 All-in-One | Dell |  |  |  | Dell |  | 2 |  | 1427.14 | 2854.28 |  | 1784.32 | ICT equipment | 1069.96 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 1784.32
| 0 | 4 | Y | 4.03 |  | PowerEdge R730 Rack Server | Dell |  |  |  | Dell |  | 1 |  | 10824 | 10824 |  | 6061.46 | ICT equipment | -5732.46 | PR-026876-2712 | 436378 |  |  | 2017-02-21 |  | 2017-03-15 | 2017-04-13 |  |  |  | Status Unknown | 6061.46
| 0 | 4 | Y |  |  | Clients (OptiPlex 5050 SFF) | Dell |  |  | OptiPlex 5050 SFF | Dell |  | 6 |  | 1249 | 7494 |  | 7494 | ICT equipment | 0 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-04-12 |  |  | 01/30/18: Awaiting new expected delivery date from Purchasing Manager | Yes | 95965.47
| 0 | 4 | Y |  |  | Monitors (34") | Dell |  |  | U3415W | Dell |  | 6 |  | 749.99 | 4499.94 |  | 4499.94 | ICT equipment | 0 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-04-12 |  |  | 01/30/18: Awaiting new expected delivery date from Purchasing Manager | Yes | 0
| 0 | 4 | Y |  |  | CISCO WS-C3850-12X48U-L Catalyst 3850-48UL-L Managed L3 Switch - 48 Ethernet Ports UPOE. New Factory Sealed | Cisco |  |  | WS-C3850-12X48U-L | ServerSupply |  | 2 |  | 4950 | 9900 |  | 14790 | ICT equipment | -4890 | PR-034206-2712 | PO18-00085 |  |  | 2018-01-10 |  | 2018-02-11 | 2018-04-13 |  |  |  | Yes | 14790
| 0 | 4 | Y |  |  | Fileservers SnapServer XSR 120 16TB Enterprise SATA Bundle (4 x 4TB) 12-Bay Rackmount NAS by Overland Storage | Overland Storage |  |  | OT-NAS200219 | Provantage |  | 2 |  | 1719 | 3438 |  | 7350 | ICT equipment | -3912 | PR-034208-2712 | 444543 |  |  | 2017-11-28 |  | 2017-12-22 | 2018-05-07 |  |  |  | Yes | 7350
| 0 | 4 | Y | 4.49 |  | Portable encrypted drives DataLocker H100 500 GB 2.5" External Hard Drive - USB 2.0 | IronKey |  |  | H100500 | Jet.com |  | 1 |  | 432.66 | 432.66 |  | 399.09 | ICT equipment | 33.57 | PR-033894-2712 | 443207N |  |  | 2017-10-11 |  | 2017-10-18 | 2017-10-31 |  |  |  | Status Unknown | 399.09
| 0 | 4 | Y | 4.09 |  | Environmental monitor Room Alert 3E - Monitor w/PoE (100% Warranty) | Avtech |  |  | RA3E-ES0-BAS | Avtech |  | 1 |  | 175 | 175 |  | 175 | ICT equipment | 0 | PR-029411-2712 | 438780N |  |  | 2017-04-21 |  | 2017-05-02 | 2017-05-01 |  |  | 10/25/17: Check - this one is dev lab and Adam's BOM says delivered, so Mod 1 is likely for WSC. clear to order | Status Unknown | 175
| 0 | 4 | Y | 4.1 |  | Light tower Light Tower w/Audio & Adapter (RYG, Adapter, Bracket, 15' | Avtech |  |  | ST-RYG-LT/A | Avtech |  | 1 |  | 325 | 325 |  | 325 | ICT equipment | 0 | PR-029411-2712 | 438780N |  |  | 2017-04-21 |  | 2017-05-02 | 2017-05-01 |  |  | 10/25/17: Check - this one is dev lab and Adam's BOM says delivered, so Mod 1 is likely for WSC. clear to order | Status Unknown | 325
| 0 | 4 | Y | 4.11 |  | GoToMyDevices software GoToMyDevices Annual Personal Service | Avtech |  |  | GTMD-PER-AAS | Avtech |  | 1 |  | 99.95 | 99.95 |  | 13.05 | ICT equipment | 86.9 | PR-029411-2712 | 438780N |  |  | 2017-04-21 |  | 2017-05-02 | 2017-05-01 |  |  |  | Status Unknown | 13.05
| 0 | 4 | Y | 4.5 |  | Environmental monitor Room Alert 3E - Monitor w/PoE (100% Warranty) | Avtech |  |  | RA3E-ES0-BAS | Avtech |  | 1 |  | 175 | 175 |  | 175 | ICT equipment | 0 | PR-033902-2712 | 443356N |  |  | 2017-10-12 |  | 2017-10-18 | 2017-10-31 |  |  |  | Status Unknown | 175
| 0 | 4 | Y | 4.51 |  | Light tower Light Tower w/Audio & Adapter (RYG, Adapter, Bracket, 15' | Avtech |  |  | ST-RYG-LT/A | Avtech |  | 1 |  | 325 | 325 |  | 325 | ICT equipment | 0 | PR-033902-2712 | 443356N |  |  | 2017-10-12 |  | 2017-10-18 | 2017-10-31 |  |  |  | Status Unknown | 325
| 0 | 4 | Y | 4.52 |  | GoToMyDevices software GoToMyDevices Annual Personal Service | Avtech |  |  | GTMD-PER-AAS | Avtech |  | 1 |  | 99.95 | 99.95 |  | 13.05 | ICT equipment | 86.9 | PR-033902-2712 | 443356N |  |  | 2017-10-12 |  | 2017-10-18 | 2017-10-31 |  |  |  | Status Unknown | 13.05
| 0 | 4 | Y | 4.12 |  | VMware software license vSphere with Operations Management Enterprise Plus - Basic Support Subscription for 1 year | VMware |  |  | N/A | VMware |  | 4 |  | 5318 | 21272 |  | 17584.24 | ICT equipment | 3687.76 | PR-026928-2712 | 436958 |  |  | 2017-03-03 |  | 2017-03-10 | 2017-03-08 |  |  |  | Status Unknown | 17584.24
| 0 | 4 | Y | 4.12 |  | vCenter Server | VMware |  |  | N/A | VMware |  | 1 |  | 7254 | 7254 |  | 0 | ICT equipment | 7254 | PR-026928-2712 | 436958 |  |  | 2017-03-03 |  | 2017-03-10 | 2017-03-08 |  |  |  | Status Unknown | 0
| 0 | 4 | Y | 4.13 |  | RHEL licenses (W/S) | Red Hat |  |  | N/A |  |  | 8 |  | 399 | 3192 |  | 2040 | ICT equipment | 1152 | PR-030823-2712 | 440210J |  |  | 2017-06-14 |  | 2017-06-21 | 2017-07-14 |  |  |  | Status Unknown | 2040
| 0 | 4 | Y | 4.14 |  | Windows license, 16-core Microsoft Windows Server 2016 Standard 64 Bit License 16 cores | Microsoft |  |  | N/A |  |  | 6 |  | 737.99 | 4427.94 |  | 4128 | ICT equipment | 299.94 | PR-026930-2712 | 437011 |  |  | 2017-03-06 |  | 2017-03-10 | 2017-03-13 |  |  |  | Status Unknown | 4128
| 0 | 4 | Y | 4.15 |  | PV-WAVE Foundation PC Deployment License | RogueWave |  |  | PVWA-PWFN-DEP-PCXX-LIC |  |  | 1 |  | 995 | 995 |  | 960 | ICT equipment | 35 | PR-026932-2712 | 435903 |  |  | 2017-02-07 |  | 2017-02-17 | 2017-03-03 |  |  |  | Status Unknown | 960
| 0 | 4 | Y | 4.15 |  | PV-WAVE Foundation PC Deployment Standard Maintenance and Support | RogueWave |  |  | PVWA-PWFN-DEP-PCXX-SMS |  |  | 1 |  | 995 | 995 |  | 240 | ICT equipment | 755 | PR-026932-2712 | 435903 |  |  | 2017-02-07 |  | 2017-02-17 | 2017-03-03 |  |  |  | Status Unknown | 240
| 0 | 4 | Y | 4.16 |  | NX workstation licences NoMachine Workstation Subscription Pack | NoMachine |  |  | N/A |  |  | 1 |  | 994.5 | 994.5 |  | 994.5 | ICT equipment | 0 | PR-029413-2712 | 438813J |  |  | 2017-04-24 |  | 2017-04-24 | 2017-04-24 |  |  |  | Status Unknown | 994.5
| 0 | 4 | Y |  |  | PowerEdge R630 Server (210-ACXS) | Dell | [5 empty] | 6 |  | 10227.31 | 61363.86 |  | 61363.86 | ICT equipment | 0 | PR-026881-2712 | 435926 |  |  | 2017-02-07 |  | 2017-02-24 |  |  |  | WBS 4.0 SSOC CDS (Bill Reid) 10/25/17: Ask Bill if he has all 6. Adam's BOM says 6. Ship to Rome, NY, cost shown in other qt7 3 above | Status Unknown | 61363.86
| 0 | 4 | Y |  |  | Red Hat Enterprise Linux Server - Standard subscription (1 year) - 2 sockets, 1 physical/2 virtual nodes | Red Hat |  |  |  | Insight |  | 4 |  | 590.1 | 2360.4 |  | 2360.4 | ICT equipment | 0 | PR-027783-2712 | 436987 |  |  | 2017-03-06 |  | 2017-03-06 |  |  |  | Requested by Bill Reid, Ship to Rome, NY | Status Unknown | 2360.4
| 0 | 4 | Y |  |  | ORACLE SOLARIS PREMIER SUB SPRT, RUNNING ON NON-ORACLE HW (1-4 SOCKET SERVER) | Red Hat |  |  |  | Insight |  | 4 |  | 1071.98 | 4287.92 |  | 4287.92 | ICT equipment | 0 | PR-027783-2712 | 436987 |  |  | 2017-03-06 |  | 2017-03-06 |  |  |  | Requested by Bill Reid, Ship to Rome, NY | Status Unknown | 4287.92
| 0 | 4 | Y |  |  | Office Home & Business 2016 | Microsoft |  |  |  | Provantage |  | 1 |  | 229.99 | 229.99 |  | 219.62 | ICT equipment | 10.37 | PR-028999-2712 | 438258J |  |  | 2017-04-05 |  | 2017-04-07 | 2017-04-07 |  |  | For Pete Gaffney | Status Unknown | 219.62
| 0 | 4 | Y |  |  | VMware Workstation 12.5 pro | VMware |  |  |  | CDW |  | 1 |  | 249.99 | 249.99 |  | 241.99 | ICT equipment | 8 | PR-029001-2712 | 438261J |  |  | 2017-04-05 |  | 2017-04-07 | 2017-04-07 |  |  | For Pete Gaffney | Status Unknown | 241.99
| 0 | 4 | Y |  |  | Red Hat Enterprise Linux Server, Standard | Red Hat |  |  |  | DLT Solutions |  | 18 |  | 799 | 14382 |  | 11400.48 | ICT equipment | 2981.52 | PR-029006-2712 | 438467 |  |  | 2017-04-13 |  | 2017-04-14 | 2017-04-21 |  |  | For Pete Gaffney | Status Unknown | 11400.48
| 0 | 4 | Y |  |  | QLogic 57810 Dual Port 10Gb Base-T Low Profile Network Adapter,CusKit (540-BBIU) non-TAA | Dell | [5 empty] | 4 |  | 296.54 | 1186.16 |  | 1186.16 | ICT equipment | 0 | PR-029742-2712 | 439011 |  |  | 2017-05-04 |  | 2017-05-04 | 2017-05-08 |  |  | Omitron | Status Unknown | 1186.16
| 0 | 4 | Y |  |  | Internal Dual SD Module,CusKit (330-BBCN) Replacement Part | Dell | [5 empty] | 2 |  | 26.35 | 52.7 |  | 52.7 | ICT equipment | 0 | PR-029742-2712 | 439011 |  |  | 2017-05-04 |  | 2017-05-04 | 2017-05-08 |  |  | Omitron | Status Unknown | 52.7
| 0 | 4 | Y |  |  | VFlash, 8GB SD Card for iDRAC Enterprise, V2, Customer Install (385-BBIC) Replacement Part | Dell | [5 empty] | 4 |  | 39.53 | 158.12 |  | 158.12 | ICT equipment | 0 | PR-029742-2712 | 439011 |  |  | 2017-05-04 |  | 2017-05-04 | 2017-05-08 |  |  | Omitron | Status Unknown | 158.12
| 0 | 4 | Y |  |  | Open Market - X520-DA2 10GBE SVR 2PT-SFP+ VM FCOE ISCSI IPSEC (A3612382) non-TAA | Dell |  |  |  | Provantage |  | 8 |  | 3719.92 | 29759.36 |  | 2352 | ICT equipment | 27407.36 | PR-029789-2712 | 439116 |  |  | 2017-05-03 |  | 2017-05-16 |  |  |  | Requested by Bill Reid, Ship to Rome, NY | Status Unknown | 2352
| 0 | 4 | Y |  |  | 8 GB SDHC Flash Memory Card | Dell | [5 empty] | 4 |  | 9.45 | 37.8 |  | 43.96 | ICT equipment | -6.16 | PR-029906-2712 | 439185N |  |  | 2017-05-04 |  | 2017-05-12 |  |  |  | Omitron | Status Unknown | 43.96
| 0 | 4 | Y |  |  | Internal Dual SD Module,Customer Kit | Dell | [5 empty] | 2 |  | 29.99 | 59.98 |  | 77.54 | ICT equipment | -17.56 | PR-029906-2712 | 439185N |  |  | 2017-05-04 |  | 2017-05-12 |  |  |  | Omitron | Status Unknown | 77.54
| 0 | 4 | Y |  |  | QLogic 57810 Dual Port 10Gb Base-T Low Profile Network Adapter,Customer Kit | Dell | [5 empty] | 4 |  | 337.49 | 1349.96 |  | 1232.76 | ICT equipment | 117.2 | PR-029906-2712 | 439185N |  |  | 2017-05-04 |  | 2017-05-12 |  |  |  | Omitron | Status Unknown | 1232.76
| 0 | 4 | Y |  |  | Internal Dual SD Module,Customer Kit | Dell | [5 empty] | 2 |  | 59.98 | 119.96 |  | 52.7 | ICT equipment | 67.26 | PR-030087-2712 | 439474N |  |  | 2017-05-15 |  | 2017-05-26 | 2017-05-26 |  |  | Omitron | Status Unknown | 52.7
| 0 | 4 | Y |  |  | QLogic 57810 Dual Port 10Gb Base-T Low Profile Network Adapter,Customer Kit | Dell | [5 empty] | 3 |  | 1012.47 | 3037.41 |  | 889.62 | ICT equipment | 2147.79 | PR-030087-2712 | 439474N |  |  | 2017-05-15 |  | 2017-05-26 | 2017-05-26 |  |  | Omitron | Status Unknown | 889.62
| 0 | 4 | Y |  |  | IntelliJ Idea Ultimate | IntelliJ Idea | [5 empty] | 1 |  | 499 | 499 |  | 499 | ICT equipment | 0 | PR-033815-2712 | 443535J |  |  | 2017-10-18 |  | 2017-10-19 | 2017-12-08 |  |  |  | Status Unknown | 499
| 0 | 4 | Y |  |  | IntelliJ Idea Ultimate | IntelliJ Idea | [5 empty] | 1 |  | 499 | 499 | 499 | 499 | ICT equipment | 0 | PR-028995-2712 | 438417J |  |  | 2017-04-11 |  | 2017-04-11 | 2017-04-11 |  |  |  | Status Unknown | 499
| 0 | 4 | Y |  |  | CISCO WS-C3850-24XU-L CATALYST WS-C3850-24XU LAYER 3 SWITCH - 24 PORTS - MANAGEABLE - STACK PORT - 10GBASE-T - 24 X NETWORK - TWISTED PAIR - 10 GIGABIT ETHERNET - 3 LAYER SUPPORTED | Cisco |  |  |  | Sterling Computers |  | 2 |  | 7495 | 14990 |  | 14990 | ICT equipment | 0 | PR-026924-2712 | 436651 |  |  | 2017-02-24 |  | 2017-03-22 | 2017-03-15 |  |  | Omitron | Status Unknown | 14990
| 0 | 4 | Y |  |  | SnapServer XSR 40 16TB (4 X 4TB) Enterprise SATA bundle 1U Rackmount NAS by Overland Storage |  |  |  |  | Provantage |  | 2 |  | 1719 | 3438 |  | 3342 | ICT equipment | 96 | PR-026926-2712 | 436215 |  |  | 2017-02-14 |  | 2017-03-01 | 2017-03-02 |  |  | Omitron | Status Unknown | 3342
| 0 | 4 | Y |  |  | Data Locker H100 500 GB 2.5" External Hard Drive - USB 2.0 |  |  |  |  | Provantage |  | 1 |  | 348 | 348 |  | 366 | ICT equipment | -18 | PR-026927-2712 | 435988 |  |  | 2017-02-08 |  | 2017-02-15 | 2017-03-02 |  |  |  | Status Unknown | 366
| 0 | 4 | Y |  |  | Dell UltraSharp 34" Curved Ultrawide Monitor | Dell | [5 empty] | 3 |  | 779.99 | 2339.97 |  | 2099.97 | ICT equipment | 240 | PR-029446-2712 | 439138 |  |  | 2017-05-04 |  | 2017-05-19 | 2017-05-16 |  |  | Omitron | Status Unknown | 2099.97
| 0 | 4 | Y |  |  | OptiPlex 5040 SFF | Dell | [5 empty] | 4 |  | 692.25 | 2769 |  | 2474.64 | ICT equipment | 294.36 | PR-029446-2712 | 439138 |  |  | 2017-05-04 |  | 2017-05-19 | 2017-05-16 |  |  |  | Status Unknown | 2474.64
| 0 | 4 | Y |  |  | VMware vCenter Server Standard for vSphere (Per Instance) - Basic Support for 1 year | VMware | [5 empty] | 1 |  | 7254 | 7254 |  | 4152 | ICT equipment | 3102 | PR-034313-2712 | 444258 |  |  | 2017-11-13 |  | 2017-11-30 | 2017-12-08 |  |  |  | Status Unknown | 4152
| 0 | 4 | Y |  |  | Compass Redundant Backup System | Kratos | [5 empty] | 2 |  | 15000 | 30000 |  | 30000 | ICT equipment | 0 | PR-026934-2712 | 437164 |  |  | 2017-03-10 |  | 2017-03-31 | 2017-04-18 |  |  | AI Solutions | Status Unknown | 30000
| 0 | 4 | Y |  |  | A browser-based interface 5-pack for operator access, configuration and system modifications. | Kratos | [5 empty] | 2 |  | 2250 | 4500 |  | 4500 | ICT equipment | 0 | PR-026934-2712 | 437164 |  |  | 2017-03-10 |  | 2017-03-31 | 2017-04-18 |  |  | AI Solutions | Status Unknown | 4500
| 0 | 4 | Y |  |  | Compass module that provides support for SNMP Manager V1, V2 and V3 capabilities. It provides an Alarm Trap GUI and allows for auto discovery and import of SNMP MIBs into Compass. | Kratos | [5 empty] | 2 |  | 2250 | 4500 |  | 4500 | ICT equipment | 0 | PR-026934-2712 | 437164 |  |  | 2017-03-10 |  | 2017-03-31 | 2017-04-18 |  |  | AI Solutions | Status Unknown | 4500
| 0 | 4 | Y |  |  | 12 Months Compass PLATINUM Maintenance for all software licenses from NDS-112846a and NDS-112846b. | Kratos | [5 empty] | 1 |  | 15417 | 15417 |  | 15417 | ICT equipment | 0 | PR-026934-2712 | 437164 |  |  | 2017-03-10 |  | 2017-03-31 | 2017-04-18 |  |  | AI Solutions | Status Unknown | 15417
| 0 | 4 | Y |  |  | Compass server license of for monitor and control of 100 devices remotely and automatically. Includes: - 1 Server license for up to 100 devices - 1 Compass GUI license - web-based interface for operator access, configuration and system modifications - Monitor and control of 100 devices via Ethernet, SNMP, Serial, TL-1, proprietary protocols, TBOS and Discrete IO - USB Key | Kratos | [5 empty] | 2 |  | 11335.01 | 22670.02 |  | 15517 | ICT equipment | 7153.02 | PR-026934-2712 | 437164 |  |  | 2017-03-10 |  | 2017-03-31 | 2017-04-18 |  |  | AI Solutions | Status Unknown | 15517
| 0 | 4 | Y |  |  | GSA Freeflyer Mission Node-Locked Maintenance | A.I. Solutions | [5 empty] | 2 |  | 7370 | 14740 |  | 14740 | ICT equipment | 0 | PR-034319-2712 | 444111 |  |  | 2017-11-15 |  | 2017-11-30 | 2017-11-30 |  |  | AI Solutions | Status Unknown | 14740
| 0 | 4 | Y |  |  | Meridian Software Maintenance | A.I. Solutions | [5 empty] | 2 |  | 5400 | 10800 |  | 10800 | ICT equipment | 0 | PR-034319-2712 | 444111 |  |  | 2017-11-15 |  | 2017-11-30 | 2017-11-30 |  |  | AI Solutions | Status Unknown | 10800
| 0 | 4 | Y |  |  | 1GB network cables - 5' 7 ft Cat6a UTP RJ45 Ethernet Network Cable (white) Monoprice 9805 FLEXboot Series Cat6 24AWG UTP Ethernet Network Patch Cable, 5ft Black C2G 14 ft Cat6 Ethernet Cable (Yellow) |  |  |  |  | Outlet PC |  | 5 |  | 3.64 | 18.2 |  | 99.9 | ICT equipment | -81.7 | PR-29407-2712 | 438770N |  |  | 2017-04-21 |  | 2017-05-02 | 2017-05-02 |  |  |  | Status Unknown | 99.9
| 0 | 3 | Y |  |  | Emcore (Various) | [6 empty] | 1 |  | 15765.964 | 15765.964 |  |  | ICT equipment
| 0 | 3 | Y |  |  | Miteq (Various) | [6 empty] | 1 |  | 212250 | 212250 |  |  | ICT equipment
| 0 | 3 | Y |  |  | MCS | [6 empty] | 1 |  | 27710 | 27710 |  |  | ICT equipment
| 0 | 3 | Y |  |  | High Rate Transceiver (Dual Pol) | RTL | [5 empty] | 1 |  | 487500 | 487500 |  | 247014.2 | ICT equipment | -240485.8 | PR183412 | PO444492 | [9 empty] | Yes | 400267
| 0 | 3 | Y |  |  | Miteq (Various) | [6 empty] | 1 |  | 24562.5 | 24562.5 |  |  | ICT equipment
| 0 | 3 | Y |  |  | HHASM | [6 empty] | 1 |  | 33043.754 | 33043.754 |  |  | ICT equipment
| 0 | 3 | Y |  |  | N/S CORNING 072EWP-T4101D20 72-FIBER OUTDOOR CABLE | Corning |  |  | 072EWP-T4101D20 | ANIXTER |  | 3000 |  | 3.6 | 10800 |  | 9205 | ICT equipment | 1595 | PR-033803-2712 | 443278 |  |  | 2017-10-11 |  | 2017-10-20 |  |  |  |  | Status Unknown | 9205
| 0 | 3 | Y | 3.1.2.18.3 | EM-0058 | FOTS PS-200F-NA, Power supply PS-200F-NA POWER SUPPLY | Emcore |  | PS-200F-NA | Y1564-001-001 |  |  | 4 |  | 1060 | 4240 |  | 5533.32 | ICT equipment | -1293.32 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 19273.32
| 0 | 3 | Y | 3.1.2.18.1 | EM-0058 | FOTS Rack Mount Enclosure, 16 slot NEXT GEN OPTIVA CHASSIS | Emcore |  | OT-CC-16F-003 | Y1565-001-002 |  |  | 2 |  | 1826 | 3652 |  | 3780 | ICT equipment | -128 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 12417.82
| 0 | 3 | Y | 3.1.2.18.2 | EM-0058 | FOTS Controller with CWDM Channel #61 SNMP V3 OPV-CTLR-1-IC WITH CWDM CHANNEL #61 SNMP V3 | Emcore |  | OPV-CTLR-1-L461/L461-IC | N/A |  |  | 2 |  | 1684 | 3368 |  | 7376.67 | ICT equipment | -4008.67 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 9960
| 0 | 3 | Y | 3.1.2.9.4 | EM-0058 | FOTS DEMUX, DWDM, 8-channel 30-37, SC-PC, + 9 jumpers DEMUX, DWDM, 8 CHANNEL 30-37, SC-PC, +9 JUMPERS | Emcore |  | MDM-7001C-8-D-SA | MDM-7001C-8-D-SA |  |  | 3 |  | 3341 | 10023 |  | 9960 | ICT equipment | 63 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 5463.33
| 0 | 3 | Y | 3.1.2.8.4 | EM-0058 | FOTS MUX, CWDM, 8-channel 30-37, SC-PC, + 9 jumpers DEMUX, DWDM, 8 CHANNEL 30-37, SC-PC, +9 JUMPERS | Emcore |  | MDM-7001C-8-M-SA | MDM-7001C-8-M-SA |  |  | 3 |  | 3341 | 10023 |  | 9960 | ICT equipment | 63 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 10926.66
| 0 | 3 | Y | 3.1.2.8.1 | EM-0058 | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 47, 6DBM, SC-APC | Emcore |  | OTS-1LCT/S5-4706-SA-IC | OTS-1LCT/S5-4706-SA-IC |  |  | 3 |  | 1826 | 5478 |  | 5463.33 | ICT equipment | 14.67 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 10926.66
| 0 | 3 | Y | 3.1.2.8.2 | EM-0058 | TX,CWDM, 50-2500 MHZ, 50 OHM SMA, CHANNEL 49,6DBM SC-APC | Emcore |  | OTS-1LCT/S5-4906SAIC | OTS-1LCT/S5-4906SAIC |  |  | 3 |  | 1684 | 5052 |  | 5463.33 | ICT equipment | -411.33 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y | 3.1.2.8.1 | EM-0058 | TX, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 51, 6DBM, SC-APC | Emcore |  | OTS-1LCT/S5-5106-SA-IC | OTS-1LCT/S5-5106-SA-IC |  |  | 3 |  | 3341 | 10023 |  | 5463.33 | ICT equipment | 4559.67 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y | 3.1.2.8.2 | EM-0058 | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 53, 6DBM, SC-APC | Emcore |  | OTS-1LCT/S5-5306-SA-IC | OTS-1LCT/S5-5306-SA-IC |  |  | 3 |  |  | 0 |  | 5463.33 | ICT equipment | -5463.33 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y | 3.1.2.8.2 | EM-0058 | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 59, 6DBM, SC-APC | Emcore |  | OTS-1LCT/S5-5906-SA-IC | OTS-1LCT/S5-5906-SA-IC |  |  | 3 |  |  | 0 |  | 5463.33 | ICT equipment | -5463.33 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y | 3.1.2.9.1 | EM-0058 | RX, CWDM, 50-2500 MHZ, 50 OHM SMA, 6DBM SC-APC | Emcore |  | OTS-1LSR/S5-4706-SA-IC | OTS-1LSR/S5-4706-SA-IC |  |  | 10 |  |  | 0 |  | 12366.7 | ICT equipment | -12366.7 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y |  | EM-0058 | BLANK PANEL, 1 SLOT, OPTIVA | Emcore |  | OT-OPF-1 | OT-OPF-1 |  |  | 2 |  |  | 0 |  | 51.12 | ICT equipment | -51.12 | PR-033691-2712 | 444174 |  |  | 2017-11-08 |  | 2018-01-12 |  | N, 8 Weeks ARO |  |  | Yes | 0
| 0 | 3 | Y |  |  | FIS LC Quad 3 Pack APC Singlemode, Loaded, 12 Fiber Green | FIS |  | F1LC3QBLKAPCUL | F1LC3QBLKAPCUL |  |  | 24 |  | 16.3 | 391.2 |  | 278.4 | ICT equipment | 112.8 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 278.4
| 0 | 3 | Y |  |  | FIS Blank plate with No Holes Unloaded Black | FIS |  | F1BLANKUBK | F1BLANKUBK |  |  | 12 |  | 30 | 360 |  | 32.4 | ICT equipment | 327.6 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 32.4
| 0 | 3 | Y |  |  | FIS 12 Fiber 900um LC/APC SM 3 mtr Pigtails with Green Boots | FIS |  | SP12LCAPCGR | SP12LCAPCGR |  |  | 14 |  | 185 | 2590 |  | 420 | ICT equipment | 2170 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 420
| 0 | 3 | Y |  |  | FIS Fusion Protection Sleeve 60mm, Clear Shrink to 3mm, 50 pack | FIS |  | F11002C50 | F11002C-50 |  |  | 6 |  | 14.25 | 85.5 |  | 60 | ICT equipment | 25.5 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 60
| 0 | 3 | Y |  |  | 3M Large Fiber Optic Splice Case, holds up to 192 splices (trays NOT included) | FIS |  | 2178LS | 2178LS |  |  | 1 |  | 2.85 | 2.85 |  | 258.3 | ICT equipment | -255.45 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 258.3
| 0 | 3 | Y |  |  | 80610933154 NEW 80611486525 3M 24Fusion Splice Tray (stackable hinged tray), includes fusion splice holders | FIS |  | 2524FT | 2524FT |  |  | 7 |  | 795 | 5565 |  | 265.65 | ICT equipment | 5299.35 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 265.65
| 0 | 3 | Y |  |  | Corning Buffer Tube Fan Out Kit 12 fiber 25" | FIS |  | FANBT2512 | FANBT2512 |  |  | 13 |  | 14.25 | 185.25 |  | 195.65 | ICT equipment | -10.4 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 195.65
| 0 | 3 | Y |  |  | FIS Cheetah LC/APC SM Splice On Connector 900um Green Boot Blister Pk 101 | FIS |  | F1LCAPCSOC100B | F1LCAPCSOC100B |  |  | 2 |  |  | 0.234 |  | 1431 | ICT equipment | -1430.766 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 1431
| 0 | 3 | Y |  |  | 4RU Rack Mount Fiber Optic Patch Panel Enclosure; up to 12 LGX Plates or Cassettes; w/Lexan Front Door; Color Black; 19"Brackets included, 23" Brackets sold separately. | FIS |  | F1RM4RU12XL | F1RM4RU12XL |  |  | 1 |  |  | 0 |  | 170.2 | ICT equipment | -170.2 | PR-033697-2712 | 443347N |  |  | 2017-10-12 |  | 2017-10-18 |  |  |  |  | Status Unknown | 170.2
| 1 | 3 | Y |  |  | W/GCOAX ADPTR 15.022.0 GHz SMAF WR51 | AZTEC ENTERPRISES, INC |  | 4628 | 4628 |  |  | 1 |  | 420 | 420 |  | 400 | ICT equipment | 20 | PR-033196-2712 | 442740N |  |  | 2017-09-21 |  | 2017-11-16 |  |  |  |  | Status Unknown | 400
| 1 | 3 | Y |  |  | W/GCOAX ADPTR 22.033.0 GHz KF WR34 (RT Angle) | AZTEC ENTERPRISES, INC |  | 4630 | 4630 |  |  | 1 |  | 640 | 640 |  | 640 | ICT equipment | 0 | PR-033196-2712 | 442740N |  |  | 2017-09-21 |  | 2017-11-16 |  |  |  |  | Status Unknown | 640
| 1 | 3 | Y |  |  | GAIN HORN, STD W/G 15.022.0GHZ WR51 | AZTEC ENTERPRISES, INC |  | 662-20 | 662-20 |  |  | 1 |  | 586 | 586 |  | 586 | ICT equipment | 0 | PR-033196-2712 | 442740N |  |  | 2017-09-21 |  | 2017-11-16 |  |  |  |  | Status Unknown | 586
| 1 | 3 | Y |  |  | GAIN HORN, STD W/G 22.033.0GHZ WR34 | AZTEC ENTERPRISES, INC |  | 664-20 | 664-20 |  |  | 1 |  | 586 | 586 |  | 586 | ICT equipment | 0 | PR-033196-2712 | 442740N |  |  | 2017-09-21 |  | 2017-11-16 |  |  |  |  | Status Unknown | 586
| 0 | 3 | Y |  |  | Terminal Server | MOXA |  |  | CN2650I-2AC |  |  | 2 |  | 1864 | 3728 |  | 3495 | ICT equipment | 233 | PR-033681-2712 | PO18-00438 |  |  | 2018-01-29 |  | 2018-03-02 |  |  |  |  | Yes | 3507.95
| 1 | 4 | Y | 4.5 |  | Environmental monitor Room Alert 3E - Monitor w/PoE (100% Warranty) | Avtech |  |  | RA3E-ES0-BAS | Avtech |  | 1 |  | 175 | 175 |  | 175 | ICT equipment | 0 | PR-034211-2712 | 443725N |  |  | 2017-10-24 |  | 2017-10-30 | 2017-10-31 |  |  | 01/30/18: It looks like quantity 2 was ordered by mistake. I will reduce line 279 below to quantity 0 po: 443356N; WSC received qty: 1 >>Did we order qty 2 by mistake | Status Unknown | 175
| 1 | 4 | Y | 4.51 |  | Light tower Light Tower w/Audio & Adapter (RYG, Adapter, Bracket, 15' | Avtech |  |  | ST-RYG-LT/A | Avtech |  | 1 |  | 325 | 325 |  | 325 | ICT equipment | 0 | PR-034211-2712 | 443725N |  |  | 2017-10-24 |  | 2017-10-30 | 2017-10-31 |  |  | 01/30/18: It looks like quantity 2 was ordered by mistake. I will reduce line 280 below to quantity 0 po: 443356N; WSC received qty: 1 >>Did we order qty 2 by mistake | Status Unknown | 325
| 1 | 4 | Y | 4.52 |  | GoToMyDevices software GoToMyDevices Annual Personal Service | Avtech |  |  | GTMD-PER-AAS | Avtech |  | 1 |  | 99.95 | 99.95 |  | 13.05 | ICT equipment | 86.9 | PR-034211-2712 | 443725N |  |  | 2017-10-24 |  | 2017-10-30 | 2017-10-31 |  |  | 01/30/18: It looks like quantity 2 was ordered by mistake. I will reduce line 279 below to quantity 0 po: 443356N; GoToMyDevices monthly service: qty indicated on received packing slip: 3 (RRusty) Did we order qty 2 by mistake | Status Unknown | 13.05
| 1 | 4 | Y |  |  | Kingston Digitial 64GB USB 256bit HW Encrypt FIPS 140-2 Level 3 (DT4000G2/64GB) |  |  |  |  | AWDATA |  | 4 |  | 209.99 | 839.96 |  | 860 | ICT equipment | -20.04 | PR-027766-2712 | 436849N |  |  | 2017-03-01 |  | 2017-03-07 | 2017-03-03 |  |  | For Pete Gaffney | Status Unknown | 860
| 1 | 4 | Y |  |  | Red Hat Enterprise Linux Server Operating Systems - Standard Subscription (1 year) - 2 Sockets, 1 Physical/2 virtual nodes | RedHat |  |  |  | Carasoft |  | 6 |  | 590.1 | 3540.6 |  | 3431.52 | ICT equipment | 109.08 | PR-034389-2712 | 444125 |  |  | 2017-11-07 |  | 2017-11-10 | 2017-12-13 |  |  | For Pete Gaffney | Status Unknown | 3431.52
| 1 | 4 | Y |  |  | Dell Precision 7520 per spec | Dell | [5 empty] | 1 |  | 10018.7 | 10018.7 |  | 3034.44 | ICT equipment | 6984.26 | PR-033593-2712 | 443721 |  |  | 2017-10-24 |  | 2017-11-10 | 2017-11-10 |  |  | 11/06/17: RG Systems Laptop ordered on TO-190/1 has arrived and it’s at the RG Systems Ivy Lane office. | Status Unknown | 3034.44
| 1 | 4 | Y |  |  | Dell Energy Backpack 15 | Dell | [5 empty] | 1 |  | 79.99 | 79.99 |  | 52.71 | ICT equipment | 27.28 | PR-033593-2712 | 443721 |  |  | 2017-10-24 |  | 2017-11-10 | 2017-11-10 |  |  | 11/06/17: RG Systems Laptop ordered on TO-190/1 has arrived and it’s at the RG Systems Ivy Lane office. | Status Unknown | 52.71
| 1 | 4 | Y |  |  | Dell Wireless Mouse-WM326 | Dell | [5 empty] | 1 |  | 29.99 | 29.99 |  | 19.76 | ICT equipment | 10.23 | PR-033593-2712 | 443721 |  |  | 2017-10-24 |  | 2017-11-10 | 2017-11-10 |  |  | 11/06/17: RG Systems Laptop ordered on TO-190/1 has arrived and it’s at the RG Systems Ivy Lane office. | Status Unknown | 19.76
| 1 | 4 | Y | 4.29 |  | VM servers (SSOC config) PowerEdge R630 Server | Dell |  |  | pe_630_1337 |  |  | 3 |  | 20698 | 62094 |  | 36165.33 | ICT equipment | 25928.67 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-02-28 |  |  | 02/01/18: Awaiting new expected delivery date from Purchasing Manager. | Yes | 4499.94
| 1 | 4 | Y | 4.35 |  | SANs EqualLogic PS6210 24 x 2.5: | Dell |  |  | EqualLogic PS6210X el_ps6210x_1279 |  |  | 2 |  | 22098 | 44196 |  | 41746.62 | ICT equipment | 2449.38 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-02-28 |  |  | 02/01/18: Awaiting new expected delivery date from Purchasing Manager. | Yes | 36165.33
| 1 | 4 | Y | 4.37 |  | Clients OptiPlex 5050 SFF | Dell |  |  | Optiplex 5050 SFF xctoo5050sffusr |  |  | 6 |  | 999.99 | 5999.94 |  | 0 | ICT equipment | 5999.94 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-02-28 |  |  | 02/01/18: Awaiting new expected delivery date from Purchasing Manager. | Yes | 41746.62
| 1 | 4 | Y | 4.38 |  | Monitors (34") Dell UltraSharp 34 Curved Ultrawide Monitor - U3415W | Dell |  |  | U3415W u3415wsap |  |  | 6 |  | 999.99 | 5999.94 |  | 0 | ICT equipment | 5999.94 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-02-28 |  |  | 02/01/18: Awaiting new expected delivery date from Purchasing Manager. | Yes | 4098.54
| 1 | 4 | Y | 4.48 |  | Tape library PV TL2000 | Dell |  |  | PowerVault TL2000 m1885 |  |  | 1 |  | 10395.28 | 10395.28 |  | 9455.04 | ICT equipment | 940.24 | PR-034202-2712 | 444308 |  |  | 2017-11-15 |  | 2017-12-08 | 2018-02-28 |  |  | 02/01/18: Awaiting new expected delivery date from Purchasing Manager. | Yes | 9455.04
| 1 | 4 | Y |  |  | Network expansion modules Cisco Expansion Module for Catalyst 3850-24 | CDW |  |  | C850-NM-4-10G | PROACTIVE COMPONENTS INC |  | 2 |  | 2417 | 4834 |  | 3050 | ICT equipment | 1784 | PR-034315-2712 | 443990 |  |  | 2017-11-01 |  | 2017-11-17 |  |  |  | Requested by Bill Reid, Ship to Rome, NY | Status Unknown | 3050
| 1 | 4 | Y | 4.44 |  | Switches (SSOC) CISCO WS-C3850-12X48U-L Catalyst 3850-48UL-L Managed L3 Switch - 48 Ethernet Ports UPOE. New Factory Sealed | ServerSupply |  |  | WS-C3850-12X48U-L | ITSavvy |  | 2 |  | 10200 | 20400 |  | 14790 | ICT equipment | 5610 | PR-034206-2712 | PO18-00085 |  |  | 2018-01-10 |  | 2018-02-11 | 2018-02-11 |  |  |  | Yes | 14790
| 1 | 4 | Y | 4.46 |  | Fileservers SnapServer XSR 120 16TB Enterprise SATA Bundle (4 x 4TB) 12-Bay Rackmount NAS by Overland Storage | BackupWorks |  |  | OT-NAS200219 | Provantage |  | 2 |  | 4326 | 8652 |  | 7350 | ICT equipment | 1302 | PR-034208-2712 | 444543 |  |  | 2017-11-28 |  | 2017-12-22 | 2018-02-11 |  |  |  | Yes | 7350
| 1 | 4 | Y |  |  | VMware software license | VMware |  |  | vSphere Enterprise Plus |  |  | 6 |  | 4229 | 25374 |  | 19660.5 | ICT equipment | 5713.5 | PR-035983-2712 | PO18-00781 | Needs Zwicks Approval |  | 2018-02-09 |  | 2018-02-09 | 2018-02-09 |  |  |  | Yes | 19660.5
| 1 | 4 | Y |  |  | vCenter Server | VMware |  |  | vCenter Server Standard Basic |  |  | 1 |  | 7254 | 7254 |  | 0 | ICT equipment | 7254 | PR-035983-2712 | PO18-00781 | Needs Zwicks Approval |  | 2018-02-09 |  | 2018-02-09 | 2018-02-09 |  |  |  | Yes | 0
| 1 | 4 | Y |  |  | RHEL licenses | Red Hat |  |  | RHEL 7 for Workstations, self-support |  |  | 14 |  | 179 | 2506 |  | 3412.92 | ICT equipment | -906.92 | PR-26929-2712 | 436958 |  |  | 2017-03-03 |  | 2017-03-10 | 2017-03-10 |  |  |  | Status Unknown | 3412.92
| 1 | 4 | Y |  |  | Windows license, 16-core Microsoft Windows Server 2016 Standard - License UNPSC: 43233004 Electronic Distribution | CDW |  |  | Windows Svr. 2016 Std. |  |  | 9 |  | 737.99 | 6641.91 |  | 877.5 | ICT equipment | 5764.41 | PR-034385-2712 | 444000 |  |  | 2017-11-02 |  | 2017-11-08 | 2017-12-08 |  |  | 02/05/18: Sent Buyer Tim Scherer an email 02/05/18: Check with the buyer about receiving digital download. End User should be Adam. | Status Unknown | 877.5
| 1 | 4 | Y | 4.57 |  | NX workstation licences | NoMachine |  |  | Enterprise Desktop, 10 svrs. |  |  | 0 |  | 994.5 | 0 |  | 0 | ICT equipment | 0 | [10 empty] | 02/06/18: This PR-033896-2712 was cancelled due to vendor never receiving the order. This order was never fulfilled. Quantities will be added with line item #147 below. 02/05/18: Sent Buyer Christie Days an email 02/05/18: Have the buyer resend this information to Adam
| 1 | 4 | Y | 4.27 |  | 1GB network cables - 10' Cat6 Gray Ethernet Patch Cable, Snagless/Molded Boot, 10 foot | CableWholesale |  |  | 10X8-02110 |  |  | 25 |  | 2.8 | 70 |  | 64.25 | ICT equipment | 5.75 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-01 |  |  |  | Status Unknown | 64.25
| 1 | 4 | Y | 4.27a |  | CAT 6 cable bulk (500 ft.) Bulk Cat6 Gray Ethernet Cable, Solid, UTP (Unshielded Twisted Pair), Pullbox, 500 foot | CableWholesale |  |  | 10X8-021TF |  |  | 1 |  | 5403.97 | 5403.97 |  | 51.92 | ICT equipment | 5352.05 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-09 |  |  |  | Status Unknown | 51.92
| 1 | 4 | Y | 4.27b |  | RJ45 connectors, 100 ct. Cat6 RJ45 Crimp Connectors for Solid and Stranded Cable, 8P8C, 100 Pieces | CableWholesale |  |  | 31D0-580HD |  |  | 1 |  | 24.52 | 24.52 |  | 22.03 | ICT equipment | 2.49 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-01 |  |  |  | Status Unknown | 22.03
| 1 | 4 | Y | 4.27c |  | RJ45 strain relief boots, 50 ct. RJ45 Strain Relief Boots, Gray, 50 Pieces Per Bag | CableWholesale |  |  | SR-8P8C-GY |  |  | 1 |  | 2.77 | 2.77 |  | 2.49 | ICT equipment | 0.28 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-01 |  |  |  | Status Unknown | 2.49
| 1 | 4 | Y | 4.27d |  | RJ45 crimper Platinum Tools EZ-RJ45 Ethernet Crimp Tool | CableWholesale |  |  | 100004C |  |  | 1 |  | 54.41 | 54.41 |  | 48.93 | ICT equipment | 5.48 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-01 |  |  |  | Status Unknown | 48.93
| 1 | 4 | Y | 4.61 |  | 10GB network cables - 7' Cat6a Gray Ethernet Patch Cable, Snagless/Molded Boot, 500 MHz, 7 foot | CableWholesale |  |  | 13X6-02107 |  |  | 30 |  | 3.05 | 91.5 |  | 83.7 | ICT equipment | 7.8 | PR-034309-2712 | 443854N |  |  | 2017-10-27 |  | 2017-11-02 | 2017-11-01 |  |  |  | Status Unknown | 83.7
| 2 | 3.0 | Y |  |  | Ship the 9.1M GFE antenna to WSC-48’ FB with tarps | [6 empty] | 1 |  | 3800 | 3800 |  | 4425 |  | -625 | PR-036828-2712 | PO18-01014 |  |  | 2018-02-21 |  | 2018-04-19 | 2018-04-19 |  |  |  | Yes | 4491.38
| 2 | 3 | Y |  |  | Ship the 9.1M GFE antenna to WSC-53’ SD with tarps | [6 empty] | 3 |  | 3800 | 11400 |  | 15900 |  | -4500 | PR-036828-2712 | PO18-01014 |  |  | 2018-02-21 |  | 2018-04-19 | 2018-04-19 |  |  |  | Yes | 5300
| 2 | 3 | Y |  |  | Shipping of Telecommunication Equipment Balance due to Invoice #12851741-01 on PO18-01014 | [9 empty] | 0 |  | 157.88 |  |  | PR-040108-J2712 | PO18-01014 |  |  | 2018-06-15 |  | 2018-06-15 | 2018-06-15 |  |  |  | Yes | 5379.5
| 2 | 3 | Y |  |  | Equipment lift service for 9M Antenna | [6 empty] | 1 |  | 7084 | 7084 |  | 7484 |  | -400 | PR-037703- | PO18-01997 |  |  | 2018-03-29 |  | 2018-04-09 | 2018-04-19 |  |  |  | Yes | 7867.56
| 2 | 3 | Y |  |  | LDR Modem and FEP | RTL | [5 empty] | 1 |  | 460222 | 460222 |  | 446795 |  | -13427 | PR183989 | PO444697 | [9 empty] | Yes | 446795
| 2 | 3 | Y |  |  | Keysight N9000B/503 CXA Signal Analyzer, Multi-touch, 9 kHz to 26.5 GHz TE P/N 24983.1 |  |  |  | 24983.1 |  |  | 4 |  | 12558.6 | 50234.4 |  | 49508 |  | 726.4 | PR-036511-2712 | PO18-01799 |  |  | 2018-03-22 |  | 2018-04-27 | 2018-05-16 |  |  |  | Yes | 56349.36
| 2 | 3 | Y |  |  | Keysight N9000BU/P03 Upgrades for CXA Signal Analyzer, Multi-touch TE P/N 25749.2 |  |  |  | 25749.2 |  |  | 4 |  | 1474.2 | 5896.8 |  | 5811.64 |  | 85.16 | PR-036511-2712 | PO18-01799 |  |  | 2018-03-22 |  | 2018-04-27 | 2018-05-16 |  |  |  | Yes | 0
| 2 | 3 | Y |  |  | Keysight 1CP105A Rack mount flange and handle kit 177.0mm H (4U) - two brackets and front handles TE P/N 26143.1 |  |  |  | 26143.1 |  |  | 4 |  | 276.27 | 1105.08 |  | 1028.92 |  | 76.16 | PR-036511-2712 | PO18-01799 |  |  | 2018-03-22 |  | 2018-04-27 | 2018-05-16 |  |  |  | Yes | 0
| 2 | 3 | Y |  |  | Power Divider/Combiner, 30 watts Weatherproof, 2-way, SMA-Female 0.500 - 6.000 GHz | MECA Electronics, Inc. |  |  | 802-2-3.250WWP |  |  | 5 |  | 217.75 | 1088.75 |  | 1088.75 |  | 0 | PR-036524-2712 | PO18-00828 |  |  | 2018-02-13 |  | 2018-02-16 | 2018-03-21 |  |  | 06/19/18: Contact Buyer, this is not in CostPoint 02/27/18: We will receive item on 03/12/18 02/27/18: Emailed Tommy Telles and Linda Hernandez regarding this partial delivery. | Yes | 1557.5
| 2 | 3 | Y |  |  | Power Divider/Combiner, 20 watts 2-way, SMA-Female, 2.0 - 4.0 GHz | MECA Electronics, Inc. |  |  | 802-2-3.000 |  |  | 3 |  | 98.75 | 296.25 |  | 296.25 |  | 0 | PR-036524-2712 | PO18-00828 |  |  | 2018-02-13 |  | 2018-02-16 | 2018-02-20 |  |  | 06/19/18: Contact Buyer, this is not in CostPoint | Yes | 0
| 2 | 3 | Y |  |  | Power Divider/Combinr, 2 watts 2-way, SMA-Female, 5 - 500 MHz | MECA Electronics, Inc. |  |  | 802-2-0.252 |  |  | 1 |  | 147.5 | 147.5 |  | 147.5 |  | 0 | PR-036524-2712 | PO18-00828 |  |  | 2018-02-13 |  | 2018-02-16 | 2018-02-20 |  |  | 06/19/18: Contact Buyer, this is not in CostPoint | Yes | 0
| 2 | 3 | Y |  |  | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 47, 6DBM, SC-APC | Emcore | [5 empty] | 1 |  | 203.756 | 203.756 |  | 0 |  | 203.756 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | TX,CWDM, 50-2500 MHZ, 50 OHM SMA, CHANNEL 49,6DBM SC-APC | Emcore | [5 empty] | 3 |  | 1833 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | TX, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 51, 6DBM, SC-APC | Emcore | [5 empty] | 3 |  | 1833 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 53, 6DBM, SC-APC | Emcore | [5 empty] | 3 |  | 1833 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | X, CWDM 50-2500 MHZ 50OHM SMA CHANNEL 59, 6DBM, SC-APC | Emcore | [5 empty] | 3 |  | 1833 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | MUX, DWDM, 8 CHANNEL 30-37, SC-PC. +9 JUMPERS | Emcore | [5 empty] | 3 |  | 3341 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | RX, CWDM, 50-2500 MHZ, 50 OHM SMA, 6DBM SC-APC | Emcore | [5 empty] | 10 |  | 1245 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | DEMUX, DWDM, 8 CHANNEL 30-37, SC-PC, +9 JUMPERS | Emcore | [5 empty] | 1 |  | 3341 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | BLANK PANEL, 1 SLOT, OPTIVA | Emcore | [5 empty] | 2 |  | 27 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | OPV-CTLR-1-IC WITH CWDM CHANNEL #61 SNMP V3 | Emcore | [5 empty] | 3 |  | 1684 | 0 |  | 0 |  | 0 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | Emcore Transmitter, 10 MHz, SMA 50 ohm, 1310 nm, 7 dBm, E2000 | Emcore | [5 empty] | 3 |  | -1545 | -4635 |  | 0 |  | -4635 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | Emcore Receiver, 10 MHz, SMA 50 ohm, E2000 | Emcore | [5 empty] | 3 |  | -993 | -2979 |  | 0 |  | -2979 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | Emcore MUX, CWDM, 4 Channel, 1470-1530 nm, SM, SC/APC | Emcore | [5 empty] | 5 |  | -1687 | -8435 |  | 0 |  | -8435 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | Emcore DEMUX, CWDM, 4 Channel, 1470-1530 nm, SM, SC/APC | Emcore | [5 empty] | 5 |  | -1687 | -8435 |  | 0 |  | -8435 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3 | Y |  |  | Miteq Shipping for items 14-17 and 20 from Mod 0 list | Emcore | [5 empty] | 1 |  | -582.5 | -582.5 |  | 0 |  | -582.5 | [10 empty] | 06/20/18: Duplicate items | N/A
| 2 | 3.0 | Y |  |  | 19X4 Crossbar Terminated RF Switch I/O ports are terminated to 2W 50-ohm load DC to 18 GHz operating frequency 4RU Enclosure SMA connectors on the rear panel LCD Touch Screen for manual control Ethernet with HTTP-Server (built-in website), RS -232 and USB remote controls | DowKey |  |  | 5425 |  |  | 1 |  | 49304 | 197716 |  | 50829 |  | 146887 | PR-037128-2712 | PO18-02373 |  |  | 2018-04-17 |  | 2018-08-08 | 2018-07-19 | 14-16 weeks |  | 02/07/18: Awaiting refresh quote | Yes | 50873.09
| 2 | 3 | Y |  |  | Shipping | DowKey |  |  | Shipping |  |  | 1 |  | 43.71 | 43.71 |  | 500 |  | -456.29 | PR-037128-2712 | PO18-02373 |  |  |  |  | 2018-08-08 | 2018-07-19 |  |  |  | Yes | 0
| 7 | 3 | Newly added 04/22/19 |  |  | Desccope: L-3 Narda-MITEQ | [9 empty] | -90000
| 7 | 3 | Newly added 04/22/19 |  |  | Descope: Microwave Components & Systems, Inc. | [9 empty] | -27560
| 7 | 3 | Newly added 04/22/19 |  |  | Descope: Microwave Components & Systems, Inc. | [9 empty] | -150
| 7 | 3 | Newly added 04/22/19 |  |  | Descope: Dow-Key Microwave | [9 empty] | -147912
| 7 | 3 | Newly added 04/22/19 |  |  | Descope: L-3 Narda-MITEQ | [9 empty] | -42150
| 2 | 3 | Y |  |  | DNS-2.07/2.25-1K, ONE THIRD RACK TEST TRANSLATOR, NO OPTIONS Inventory ID: 209530-6 (L-3 Use Only) The export jurisdiction of the proposed item falls under the EAR. The ECCN determination will be made at time of order placement. Specification per L-3 Data Sheet D-388 | L3 Narda-MITEQ |  |  | DNS-2.07/2.25-1K |  |  | 1 |  | 21075 | 21075 |  | 21075 |  | 0 | PR-036516-2712 | PO18-02314 |  |  | 2018-04-11 |  | 2018-10-12 |  |  |  |  | Yes | 36620.75
| 2 | 3.0 | Y |  |  | S-Band Range Zero Set (RZS) + NRE for product NRE for item 1 | L3 Narda-MITEQ |  |  | NRE-DNS-2.07/2.25-1K |  |  | 1 |  | 78876.13 | 78876.13 |  | 15520 |  | 63356.13 | PR-036516-2712 | PO18-02314 |  |  | 2018-04-11 |  | 2018-10-12 |  | 26 weeks ARO |  |  | Yes | 0
| 2 | 4 | Y |  |  | PV-WAVE Foundation PC Deployment Standard Maintenance and Support Start Date:02/08/2018 End Date:02/08/2019 License Number: LIC-201404016857 (PVWA-PWFN-DEP-PCXX-SMS) | RogueWave |  |  | OPP-20140437187 |  |  | 1 |  | 252 | 252 |  | 252 |  | 0 | PR-036570-2712 | PO18-00740 |  |  | 2018-02-08 |  | 2018-02-08 | 2018-02-08 |  | 1 year | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/0518: Opportunity Number 20140437187 | Yes | 252
| 2 | 4 | Y |  |  | PV-WAVE Foundation PC Deployment License (PVWA-PWFN-DEP-PCXX-LIC) | RogueWave |  |  | OPP-20140498217 |  |  | 2 |  | 995 | 1990 |  | 1920 |  | 70 | PR-036570-2712 | PO18-00740 |  |  | 2018-02-08 |  | 2018-02-08 | 2018-02-08 |  | 1 year | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/05/18: Account Number 500942. Opportunity Number 20140436819 02/05/18: Omitron. Adam will send the account number. | Yes | 2400
| 2 | 4 | Y |  |  | PV-WAVE Foundation PC Deployment Standard Maintenance and Support (PVWA-PWFN-DEP-PCXX-SMS) | RogueWave |  |  | OPP-20140498217 |  |  | 2 |  | 995 | 1990 |  | 480 |  | 1510 | PR-036570-2712 | PO18-00740 |  |  | 2018-02-08 |  | 2018-02-08 | 2018-02-08 |  | 1 year | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/05/18: Account Number 500942. Opportunity Number 20140436819 02/05/18: Omitron. Adam will send the account number. | Yes | 0
| 2 | 4 | Y |  |  | NOMachine Workstation Subscription Pack | NoMachine |  |  | Enterprise Desktop, 10 svrs. |  |  | 4 |  | 994.5 | 3978 |  | 498 |  | 3480 | PR-036695-2712 | PO18-01114 |  |  | 2018-03-02 |  | 2018-03-07 | 2018-03-30 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/05/18: Omitron. 03/19/2018-Emailed Adam for status on delivery confirmation. | Yes | 498
| 2 | 4 | Y |  |  | Optiplex 5050 SFF | Dell |  |  | Optiplex 5050 SFF |  |  | 2 |  | 493.08 | 986.16 |  | 13433.34 |  | -12447.18 | PR-036700-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/05/18: Omitron | Yes | 29795.57
| 2 | 4 | Y |  |  | Dell UltraSharp 34 Curved Ultrawide Monitor - U3415W | Dell |  |  | U3415W |  |  | 2 |  | 749.99 | 1499.98 |  | 1502.68 |  | -2.7 | PR-036700-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/05/18: Omitron | Yes | 0
| 2 | 4 | Y |  |  | Physical servers - domain controllers PowerEdge R430 | Dell |  |  | PowerEdge R430 |  |  | 2 |  | 5567.37 | 11134.74 |  | 4018.56 |  | 7116.18 | PR-036700-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/05/18: Omitron | Yes | 0
| 2 | 4 | Y |  |  | Physical servers - operations servers w/Windows PowerEdge R430 | Dell |  |  | PowerEdge R430 |  |  | 2 |  | 2187.87 | 4375.74 |  | 3424.46 |  | 951.28 | PR-036700-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/05/18: Omitron | Yes | 0
| 2 | 4 | Y |  |  | Windows 10 Pro | Microsoft | [5 empty] | 1 |  | 199 | 199 |  | 210.24 |  | -11.24 | PR-036520-2712 | PO18-01004 |  |  | 2018-02-20 |  | 2018-02-21 | 2018-02-20 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/05/18: Omitron will send a windows 10 license quote to submit. Quantity of 1. | Yes | 210.24
| 2 | 4 | Y |  |  | Microsoft Windows Server 2016 Standard - license | CDW |  |  | 9EM-00118 |  |  | 9 |  | 885.99 | 7973.91 |  | 7038 |  | 935.91 | PR-036554-2712 | PO18-00817 |  |  | 2018-02-12 |  | 2018-02-16 | 2018-02-12 |  |  |  | Yes | 7038
| 2 | 4 | Y |  |  | SnapServer XSR 120 16TB Enterprise SATA Bundle (4x4TB) 12-Bay Rackmount NAS by Overland Storage Part # OT-NAS200219 | BackupWorks |  |  | OT-NAS200219 | Provantage |  | 2 |  | 4326 | 8652 |  | 7578 |  | 1074 | PR-036593-2712 | PO18-01333 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-03 |  |  |  | Yes | 3789
| 2 | 4 | Y |  |  | Red Hat Enterprise Linux Workstation -Standard subscription (renewal) (1 year) -1-2 sockets Coverage Dates: 07-MAR-2018 - 06-MAR-2019 OPEN MARKET Contract #: 11330596 RHN: Rtison. ACCT #: 5765149 | Red Hat |  |  | RH0958488RN |  |  | 14 |  | 560.98 | 7853.72 |  | 3027.08 |  | 4826.64 | PR-036323-2712 | PO18-01462 |  |  | 2018-03-27 |  | 2018-03-30 | 2018-04-09 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 3027.08
| 2 | 4 | Y |  |  | Red Hat Enterprise Linux Developer Workstation - Professional Subscription (renewal) (1 year) - Linux Coverage Dates: 06-JUL-2018 - 05-JUL-2019 OPEN MARKET Contract #: 11438921 ACCT #: 5765149 | Red Hat |  |  | RH3482727RN |  |  | 8 |  | 244.54 | 1956.32 |  | 1956.32 |  | 0 | PR-036323-2712 | PO18-01462 |  |  | 2018-03-27 |  | 2018-03-30 | 2018-04-09 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 1956.32
| 2 | 4 | Y |  |  | PowerEdge R440 Rack Server | Dell |  |  | Dell R440 Quote |  |  | 4 |  | 3400 | 13600 |  | 12522.6 |  | 1077.4 | PR-036630-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-04-09 |  |  | 02/06/18: For Pete Gaffney | Yes | 29795.57
| 2 | 4 | Y |  |  | OptiPlex 7050 Micro (Clients) | Dell |  |  | Dell 7050 Quote |  |  | 1 |  | 5000 | 5000 |  | 823.79 |  | 4176.21 | PR-036630-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/06/18: For Pete Gaffney | Yes | 0
| 2 | 4 | Y |  |  | PowerEdge R730 Rack Server | Dell |  |  | SAGE - Archive Server |  |  | 1 |  | 15609.09 | 15609.09 |  | 5921.98 |  | 9687.11 | PR-036630-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/06/18: For Pete Gaffney | Yes | 0
| 2 | 4 | Y |  |  | Dell Monitor - E2417H | Dell | [5 empty] | 1 |  | 2543.76 | 2543.76 |  | 158.17 |  | 2385.59 | PR-036630-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/06/18: For Pete Gaffney | Yes | 0
| 2 | 4 | Y |  |  | Micro AIO Stand MFS18 CUS KIT | Dell | [5 empty] | 1 |  | 3003.06 | 3003.06 |  | 79.99 |  | 2923.07 | PR-036630-2712 | PO18-01412 |  |  | 2018-03-07 |  | 2018-03-30 | 2018-03-22 |  |  | 02/06/18: For Pete Gaffney | Yes | 0
| 2 | 4 | Y |  |  | Null Modem Cable DB9F to DB9F, 10 ft., Beige |  |  |  | SW-8104 |  |  | 3 |  | 7 | 21 |  | 19.35 |  | 1.65 | PR-036594-2712 | PO18-00879 |  |  | 2018-02-14 |  | 2018-02-19 | 2018-02-20 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/26/18: Pete Gaffney picked up items from Walker Drive on 02/26/18 02/06/18: For Pete Gaffney | Yes | 144.17
| 2 | 4 | Y |  |  | USB to DB9 Serial Plug-in Adapter |  |  |  | SW-1314 |  |  | 6 |  | 17.95 | 107.7 |  | 124.81 |  | -17.11 | PR-036594-2712 | PO18-00879 |  |  | 2018-02-14 |  | 2018-02-19 | 2018-02-20 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/26/18: Pete Gaffney picked up items from Walker Drive on 02/26/18 02/06/18: For Pete Gaffney | Yes | 0
| 2 | 4 | Y |  |  | 3ft USB 3.0 A Male To A Female Extension Cable |  |  |  | SKU #10U3-32103-E-BK |  |  | 6 |  | 9.96 | 59.76 |  | 40.76 |  | 19 | PR-036597-2712 | PO18-00880 |  |  | 2018-02-14 |  | 2018-02-16 | 2018-02-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/26/18: Pete Gaffney picked up items from Walker Drive on 02/26/18 02/06/18: For Pete Gaffney | Yes | 42.02
| 2 | 5 | Y |  |  | BOSCH DS9370 CEILING MOUNT TRITECH | Bosh |  |  | S03-BOS-DS9370 |  |  | 2 |  | 83.135 | 166.27 |  | 196.31 |  | -30.04 | PR-035991-2712 | PO18-00278 |  |  | 2018-01-23 |  | 2018-01-26 | 2018-01-25 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 205.45
| 2 | 5 | Y |  |  | 1 lot of WSC Electronics | CDW | [5 empty] | 1 |  | 61056.95 | 61056.95
| 2 | 5 | Y |  |  | Ship the 9.1M GFE antenna to WSC | Fedex | [5 empty] | 1 |  | 15200 | 15200
| 2 | 5 | Y |  |  | IEM Softbench Simulator | Orbital ATK | [5 empty] | 1 |  | 204408.05 | 204408.05
| 2 | 5 | Y |  |  | UTC Interlogix (Formerly GE Security/Sentrol) 2707A-L High Security Contact,Armored Cable,Triple Biased SPDT,3/16" to 5/8",36" cable | UTC Interlogox |  |  | 2707A-L |  |  | 1 |  | 91.75 | 91.75 |  | 80.45 |  | 11.3 | PR-037270-2712 | PO18-01569 |  |  | 2018-03-13 |  | 2018-04-06 | 2018-03-21 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 3893.8
| 2 | 5 | Y |  |  | UTC Interlogix (Formerly GE Security/Sentrol) 2507A-L Aluminium Housing Armored Cable Contact, SPDT,3" wide Gap | UTC Interlogox |  |  | 2507A-L |  |  | 8 |  | 27.78 | 222.24 |  | 223.12 |  | -0.88 | PR-037270-2712 | PO18-01569 |  |  | 2018-03-13 |  | 2018-04-06 | 2018-03-21 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 331.12
| 2 | 5 | Y |  |  | End of Line resistors | GRI Telemark Corp |  |  | GRI 6644-1 |  |  | 24 |  | 6.25 | 150 |  | 54.72 |  | 95.28 | PR-037270-2712 | PO18-01569 |  |  | 2018-03-13 |  | 2018-04-06 | 2018-03-20 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 76.62
| 2 | 5 | Y |  |  | Stanley- Electric Door Handle | Stanley |  |  | 9KW37DEU14DS3626RQE24V |  |  | 8 |  | 604 | 4832 |  | 3859.04 |  | 972.96 | PR-037270-2712 | PO18-01569 |  |  | 2018-03-13 |  | 2018-04-06 | 2018-04-05 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 4301.54
| 2 | 5 | Y |  |  | Shipping | Shipping |  |  | Shipping |  |  | 1 |  | 60 | 60 |  | 60 |  | 0 | PR-035996- | PO18-00285 |  |  | 2018-01-22 |  | 2018-01-29 | 2018-01-29 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/01/18: Submit PR week of 02/26/18 | Yes | 549.95
| 2 | 5 | Y |  |  | Axis Fixed Dome Network Camera with 3.0-10.5mm Lens | Axis |  |  | 0955-001 P3225-LVE |  |  | 1 |  | 615.02 | 615.02 |  | 560.89 |  | 0 | PR-035996- | PO18-00285 |  |  | 2018-01-22 |  | 2018-01-29 | 2018-01-25 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/01/18: Submit PR week of 02/26/18 | Yes | 10.94
| 2 | 5 | Y |  |  | Electric Strike for use with Hollow Metal or Aluminum Frame; Voltage-24VDC | Von Duprin |  |  | 6212 |  |  | 8 |  | 530 | 4240 |  | 3490.32 |  | 749.68 | PR-037278-2712 | PO18-01615 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-03 |  |  |  | Yes | 3490.32
| 2 | 5 | Y |  |  | Strut Channel. Low-Profile, Solid, Zinc-Plated Steel | MCMaster-Carr |  |  | 3310T523 |  |  | 30 |  | 8.75 | 262.5 |  | 296.22 |  | -33.72 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-03 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 296.22
| 2 | 5 | Y |  |  | Strut Channel Connector. Straight, Zinc Plated Steel. 9-1/8" length | MCMaster-Carr |  |  | 33125T891 |  |  | 72 |  | 1 | 72 |  | 440.76 |  | -368.76 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-05 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 626.4
| 2 | 5 | Y |  |  | High Strength Serrated Flange Hex Head Screw | MCMaster-Carr |  |  | 94239A113 |  |  | 216 |  | 4.78 | 1032.48 |  | 626.4 |  | 406.08 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-06-11 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 440.76
| 2 | 5 | Y |  |  | Steel Mil. Spec. Washer. Zinc Plated, 3/8" Screw Size, MS-51412-39 | MCMaster-Carr |  |  | 91922A226 |  |  | 216 |  | 12.6 | 2721.6 |  | 437.94 |  | 2283.66 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-05 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 437.94
| 2 | 5 | Y |  |  | Strut Channel Cap.Closed, for 13/16" Channel Height, White, Color: white | MCMaster-Carr |  |  | 3312T62 |  |  | 240 |  | 0.97 | 232.8 |  | 2146.75 |  | -1913.95 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-03 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 2146.75
| 2 | 5 | Y |  |  | Portable Band Saw Blade. 35-3/8" Long, 18 Teeth Per inch | MCMaster-Carr |  |  | 4051A35 |  |  | 3 |  | 7.18 | 21.54 |  | 42.02 |  | -20.48 | PR-036337-2712 | PO18-01558 |  |  | 2018-03-14 |  | 2018-03-30 | 2018-04-03 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 42.02
| 2 | 5 | Y |  |  | Thomas-Betts | Graybar |  |  | 61601326281 |  |  | 32 |  | 15.209 | 486.688 |  | 583.04 |  | -96.352 | PR-036345-2712 | PO18-00612 |  |  | 2018-02-02 |  | 2018-02-14 | 2018-02-14 |  |  |  | Yes | 1003.04
| 2 | 5 | Y |  |  | Thomas-Betts 700 1 1/4 EG | Graybar |  |  | 61601326281 |  |  | 240 |  | 1.1631 | 279.144 |  | 570 |  | -290.856 | PR-036345-2712 | PO18-00612 | 2018-02-02 | 2018-02-14 | 2018-02-02 |  | 2018-02-14 | 2018-02-14 |  |  |  | Yes | 150
| 2 | 5 | Y |  |  | H&H Industrial Corporation Equipment Racks (24" Wide, 87" H, and 42" Deep) | H&H Industrial |  |  | HHASM1176/8865 |  |  | 10 |  | 6697 | 66970 |  | 67810 |  | -840 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 67810
| 2 | 5 | Y |  |  | H&H Rack Accessories - 10-32 Cage Nuts for square holes (pkg) | H&H Industrial |  |  | N/A |  |  | 10 |  | 57.25 | 572.5 |  | 572.5 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-06-13 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 572.5
| 2 | 5 | Y |  |  | H&H Rack Accessories - 24" Deep Adjustable Flat Shelf | H&H Industrial |  |  | N/A |  |  | 20 |  | 94 | 1880 |  | 1905 |  | -25 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 1905
| 2 | 5 | Y |  |  | H&H Rack Accessories - 22" long Shelf angles (pair) | H&H Industrial |  |  | N/A |  |  | 100 |  | 60.25 | 6025 |  | 6100 |  | -75 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 6100
| 2 | 5 | Y |  |  | H&H Rack Accessories - 1/4-20 Steel Spring nuts & CRES Bolts (pkg) | H&H Industrial |  |  | N/A |  |  | 10 |  | 46.45 | 464.5 |  | 464.5 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 464.5
| 2 | 5 | Y |  |  | H&H Rack Accessories - Filler Panel (1U) | H&H Industrial |  |  | HHFP 1901XX |  |  | 44 |  | 14.25 | 627 |  | 627 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 627
| 2 | 5 | Y |  |  | H&H Rack Accessories - Filler Panel (2U) | H&H Industrial |  |  | HHFP 1902XX |  |  | 44 |  | 17.55 | 772.2 |  | 772.2 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 772.2
| 2 | 5 | Y |  |  | H&H Rack Accessories - Filler Panel (3U) | H&H Industrial |  |  | HHFP 1903XX |  |  | 44 |  | 21.7 | 954.8 |  | 954.8 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 954.8
| 2 | 5 | Y |  |  | H&H Rack Accessories - Filler Panel (6U) | H&H Industrial |  |  | HHFP 1906XX |  |  | 20 |  | 34.6 | 692 |  | 692 |  | 0 | PR-036260-2712 | PO18-01418 |  |  | 2018-03-08 |  | 2018-04-20 | 2018-05-16 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 692
| 2 | 5 | Y |  |  | H&H Industrial | H&H Industrial |  |  | Shipping |  |  | 1 |  |  | 4145 |  | 4145 |  |  | PR-036260-2712 | PO18-01418 | [8 empty] | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 4145
| 2 | 5 | Y |  |  | Cisco 1100W Hot Plug/Redundant Power Supply for Catalyst 3850-48F-E | Cisco |  |  | PWR-C1-1100WAC= | CDW |  | 4 |  | 1398.49 | 5593.96 |  | 4444 |  | 1149.96 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 4444
| 2 | 5 | Y |  |  | Cisco Catalyst 2960X-24TS-L - switch - 24 ports - managed - rack-mountable | Cisco |  |  | WS-C2960X-24TS-L | CDW |  | 2 |  | 1358.59 | 2717.18 |  | 2212 |  | 505.18 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 2212
| 2 | 5 | Y |  |  | Cisco ASA 5525-X Firewall Edition Security Appliance | Cisco |  |  | ASA5525-K9 | CDW |  | 4 |  | 5989.98 | 23959.92 |  | 19560 |  | 4399.92 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 19560
| 2 | 5 | Y |  |  | Cisco ASA Interface Card - expansion module - 6 ports | Cisco |  |  | ASA-IC-6GE-SFP-B= | CDW |  | 4 |  | 5006.44 | 20025.76 |  | 16372 |  | 3653.76 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 16372
| 2 | 5 | Y |  |  | Black Box 48 Port Serial over IP Gigabit Console Server, Cisco Compatible | BlackBox |  |  | LES1548A | CDW |  | 4 |  | 2293.24 | 9172.96 |  | 8504 |  | 668.96 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 8504
| 2 | 5 | Y |  |  | Microsoft Windows Server 2016- license | Windows |  |  | R18-05187 | CDW |  | 10 |  | 680.29 | 6802.9 |  | 290 |  | 6512.9 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-04-05 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 290
| 2 | 5 | Y |  |  | Seagate Expansion 2 TB External HDD | Seagate |  |  | STEA2000400 | CDW |  | 12 |  | 79.79 | 957.48 |  | 804 |  | 153.48 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 804
| 2 | 5 | Y |  |  | Red Hat Enterprise Linux Server - standard subscription | Linux |  |  | RH00004S-CS | CDW |  | 2 |  | 1000.48 | 2000.96 |  | 1314 |  | 686.96 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-04-05 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 1314
| 2 | 5 | Y |  |  | Tripp Lite Computer Power Extension Cord Adapter 10A 18AWG C14 to C13 4' | TrippLite |  |  | P004-004 | CDW |  | 48 |  | 5.98 | 287.04 |  | 192 |  | 95.04 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 192
| 2 | 5 | Y |  |  | APC Metered Rack PDU - power distribution strip -8.6 kW | APC |  |  | AP8865 | CDW |  | 20 |  | 883.78 | 17675.6 |  | 14120 |  | 3555.6 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 14120
| 2 | 5.0 | Y |  |  | Microsoft Windows Server 2012 R2 Standard License 1 Server | Microsoft |  |  | P73-06165 | CDW |  | 2 |  | 697.29 | 1394.58 |  | 1342 |  | 52.58 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-04-05 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 1342
| 2 | 5 | Y |  |  | Tripp Lite Computer Power Extension Cord Adapter 10A 18AWG C14 to C13 6' | TrippLite |  |  | P004-006 | CDW |  | 192 |  | 5.98 | 1148.16 |  | 768 |  | 380.16 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 768
| 2 | 5 | Y |  |  | Tripp Lite Computer Power Extension Cord Adapter 10A 18 AWG C14 to C13 10' | TrippLite |  |  | P004-010 | CDW |  | 48 |  | 7.97 | 382.56 |  | 240 |  | 142.56 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 240
| 2 | 5 | Y |  |  | Dell UltraSharp U2417H - LED monitor - 24" - with 3-Years Advanced Exchange | Dell |  |  | U2417H | CDW |  | 10 |  | 299.24 | 2992.4 |  | 2700 |  | 292.4 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-01 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 2700
| 2 | 5 | Y |  |  | Cisco Catalyst 3850-48T-L 48-Port Gigabit Ethernet Switch | Cisco |  |  | WS-C3850-48T-L | CDW |  | 12 |  | 5047.34 | 60568.08 |  | 50292 |  | 10276.08 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 50292
| 2 | 5 | Y |  |  | Cisco 350W Hot Plug/Redundant Power Supply for Catalyst 3850-24T-E | Cisco |  |  | PWR-C1-350WAC= | CDW |  | 8 |  | 478.79 | 3830.32 |  | 3048 |  | 782.32 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 3048
| 2 | 5 | Y |  |  | Cisco Catalyst 3850-12X48U-E - switch - 48 ports - managed - rack-mountable | Cisco |  |  | WS-C3850-12X48U-E | CDW |  | 13 |  | 14363.99 | 186731.87 |  | 180661 |  | 6070.87 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 180661
| 2 | 5 | Y |  |  | Juniper EX 4200 48T - switch - 48 ports - managed | Juniper |  |  | EX4200-48T | CDW |  | 1 |  | 5697.14 | 5697.14 |  | 4848 |  | 849.14 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 4848
| 2 | 5 | Y |  |  | Juniper Networks - expansion module | Juniper |  |  | EX-UM-4SFP | CDW |  | 1 |  | 322.99 | 322.99 |  | 283 |  | 39.99 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 283
| 2 | 5 | Y |  |  | Cisco Expansion Module for Catalyst 3850-24 |  |  |  | C3850-NM-4-10G= | CDW |  | 13 |  | 2348.39 | 30529.07 |  | 26117 |  | 4412.07 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-03-08 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 26117
| 2 | 5 | Y |  |  | Cisco 4-Port Expansion Module for Catalyst 3850-24Cisco 4-Port Expansion Module for Catalyst 3850-24 | Cisco |  |  | C3850-NM-4-1G= | CDW |  | 3 |  | 2416.93 | 7250.79 |  | 756 |  | 6494.79 | PR-036037-2712 | PO18-00996 |  |  | 2018-02-22 |  | 2018-03-30 | 2018-02-28 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 756
| 2 | 5 | Y |  |  | EMIT02-10, Eaton PDU, G3 Metered Input | Eaton |  |  | DP-17-10009 | Designed Power |  | 6 |  | 590 | 3540 |  | 2549.16 |  | 990.84 | PR-036676-2712 | PO18-01181 |  |  | 2018-02-27 |  | 2018-03-05 | 2018-03-08 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 2549.16
| 2 | 5 | Y |  |  | CoolBalance cable seal grommet, 6X16 - In-Floor Seal with edge protection. For new or existing installations with cables in place. (Consists of 2 brush seals, 4 side rails with edge protection, and 4 corner connectors with screws) | Cool Balance |  |  | CB11-0616 |  |  | 11 |  | 60.52 | 665.72 |  | 717.84 |  | -52.12 | PR-036946-2712 | PO18-01343 |  |  | 2018-03-05 |  | 2018-03-09 | 2018-04-09 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03.29.2018-Supplier will ship it on 04.02.2018.03/19/2018- Sent status confirmation email Eric and Rusty. 02/15/18: Requested refresh quotre from Eric Blum 02/09/18: Submit the week of 02/12/18 | Yes | 715.72
| 2 | 5 | Y |  |  | 10GBASE-ZR CWDM 1490NM SFP+ TRANSCEIVER 100% CISCO COMPATIBLE | Cisco |  |  | CWDM-SFP10G-1470 |  |  | 6 |  | 1295 | 7770 |  | 7770 |  | 0 | PR-036797-2712 | PO18-01182 |  |  | 2018-02-27 |  | 2018-03-16 | 2018-03-02 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 7770
| 2 | 5 | Y |  |  | 10GBASE-ZR CWDM 1470NM SFP+ TRANSCEIVER 100% CISCO COMPATIBLE | Cisco |  |  | CWDM-SFP10G-1490 |  |  | 6 |  | 1295 | 7770 |  | 7770 |  | 0 | PR-036797-2712 | PO18-01182 |  |  | 2018-02-27 |  | 2018-03-16 | 2018-03-02 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 7770
| 2 | 5 | Y |  |  | Cisco Compatible SFP Module - Long Haul (SM) - 1Gbps | Cisco |  |  | GLC-LH-SM |  |  | 8 |  | 69 | 552 |  | 490.48 |  | 61.52 | PR-036814-2712 | PO18-01134 |  |  | 2018-02-23 |  | 2018-03-02 | 2018-03-01 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 490.48
| 2 | 5 | Y |  |  | Cisco Compatible SFP Module - Short Haul (MM) - 1Gbps | Cisco |  |  | GLC-SX-MM |  |  | 20 |  | 39 | 780 |  | 394.42 |  | 385.58 | PR-036814-2712 | PO18-01134 |  |  | 2018-02-23 |  | 2018-03-02 | 2018-03-01 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 394.42
| 2 | 5 | Y |  |  | Cisco Compatible SFP Module - Long Haul (SM) - 1Gbps | Cisco |  |  | Shipping |  |  | 1 |  | 56.48 | 56.48 |  | 0 |  | 56.48 | PR-036814-2712 | PO18-01134 |  |  | 2018-02-23 |  | 2018-03-02 |  |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 0
| 2 | 5 | Y |  |  | 15 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 13.19 | 52.76 |  | 52.76 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 52.76
| 2 | 5 | Y |  |  | 140 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 50.02 | 200.08 |  | 200.08 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 200.08
| 2 | 5 | Y |  |  | 130 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 47.08 | 188.32 |  | 188.32 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 188.32
| 2 | 5 | Y |  |  | 135 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 48.55 | 194.2 |  | 194.2 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 194.2
| 2 | 5 | Y |  |  | 25 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 16.15 | 64.6 |  | 64.6 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 64.6
| 2 | 5 | Y |  |  | 30 feet, Single Mode Fiber Optic Cable LC/UPC-LC/APC -Plenum | CablesforLess |  |  | 400-522 |  |  | 4 |  | 17.62 | 70.48 |  | 70.48 |  | 0 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 70.48
| 2 | 5 | Y |  |  | Single Mode Fiber Optic Cable LC/UPC-LC/APC - Plenum (15ft Length Each) -STGT | CablesforLess |  |  | Shipping |  |  | 1 |  | 43.25 | 43.25 |  | 33.38 |  | 9.87 | PR-036905-2712 | PO18-01306 |  |  | 2018-03-02 |  | 2018-03-23 | 2018-03-26 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 02/09/18: Submit the week of 02/12/18 | Yes | 33.38
| 2 | 5 | Y |  |  | 2 Strand Custom Line Indoor 10-GIG 50/125 Om3 Multimode "Fiber Whips" Assembly, 60 Foot | LANShack |  |  | PRO-769-M10G-DP-2-L-2P-60 |  |  | 4 |  | 108.73 | 434.92 |  | 373 |  | 61.92 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 373
| 2 | 5 | Y |  |  | 2 Strand Custom Line Indoor 10-GIG 50/125 Om3 Multimode "Fiber Whips" Assembly, 50 Foot | LANShack |  |  | PRO-769-M10G-DP-2-L-2P-50 |  |  | 4 |  | 101.73 | 406.92 |  | 349 |  | 57.92 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 349
| 2 | 5 | Y |  |  | 2 Strand Custom Line Indoor 10-GIG 50/125 Om3 Multimode "Fiber Whips" Assembly, 45 Foot | LANShack |  |  | PRO-769-M10G-DP-2-L-2P-45 |  |  | 4 |  | 98.23 | 392.92 |  | 332 |  | 60.92 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 332
| 2 | 5 | Y |  |  | 2 Strand Custom Line Indoor 10-GIG 50/125 Om3 Multimode "Fiber Whips" Assembly, 55 Foot | LANShack |  |  | PRO-769-M10G-DP-2-L-2P-55 |  |  | 4 |  | 105.23 | 420.92 |  | 360 |  | 60.92 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 360
| 2 | 5 | Y |  |  | 1 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable-Plenum Rated | LANShack |  |  | FA-DLC-DLC-M-01-10GIG-AQ |  |  | 4 |  | 24.81 | 99.24 |  | 77 |  | 22.24 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 77
| 2 | 5 | Y |  |  | 3 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable-Plenum Rated | LANShack |  |  | FA-DLC-DLC-M-03-10GIG-AQ |  |  | 4 |  | 27.09 | 108.36 |  | 97 |  | 11.36 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-28 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 97
| 2 | 5 | Y |  |  | Cat 6E 1000x,UTP, Plenum Rated-Solid Cond. Cable-1000Ft (White) | LANShack |  |  | EL-TUP2404N70-SWH-S |  |  | 5 |  | 388.12 | 1940.6 |  | 1550 |  | 390.6 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-19 |  |  | 02/09/18: Submit the week of 02/16/18 | Yes | 1550
| 2 | 5 | Y |  |  | Cat 6E 1000x,UTP, Plenum Rated-Solid Cond. Cable-1000Ft (Blue) | LANShack |  |  | EL-TUP2404N70-SBU-S |  |  | 5 |  | 388.12 | 1940.6 |  | 1550 |  | 390.6 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-04-06 | 2018-03-19 |  |  |  | Yes | 1550
| 2 | 5 | Y |  |  | Cat 6E 1000x,UTP, Plenum Rated-Solid Cond. Cable-1000Ft (Gray) | LANShack |  |  | EL-TUP2404N70-SGY-S |  |  | 2 |  | 258.27 | 516.54 |  | 620 |  | -103.46 | PR-036888-2712 | PO18-01603 |  |  | 2018-03-14 |  | 2018-03-19 | 2018-03-19 |  |  |  | Yes | 620
| 2 | 5 | Y |  |  | Multi Mode Fiber Optic Cable LC-LC - Plenum (60ft Length Each) - STGT | LANShack |  |  | shipping |  |  | 1 |  | 106.49 | 106.49 |  | 100 |  | 6.49 | PR-036888-2712 | PO18-01603 | [8 empty] | 02/09/18: Submit the week of 02/16/18 | Yes | 100
| 2 | 5 | Y |  |  | CS-BNS 2843023-3 MP-6AU BOOT 51-1:BOOT 5.4-4.8MM 100/BAG --Non-Stock | Anixter |  |  | CS-BNS 2843023-3 |  |  | 10 |  | 219 | 2190 |  | 2160 |  | 30 | PR-036881-2712 | PO18-00943 |  |  | 2018-02-16 |  | 2018-03-05 | 2018-03-19 |  |  | 03/19/2018-Emailed Tim Scherer and Eric Blum about the status confirmation. 02/16/18: Submitted PR 02/15/18: Requested refresh quotre from Eric Blum 02/09/18: Submit the week of 02/12/18 | Yes | 477.14
| 2 | 5 | Y |  |  | Non-Stock CS-BNS 6-2843007-1 MODULAR PLUG CAT 6A/6 UNSHIELDED, COND INSULATION OD-0.99MM, 100PCS | Anixter |  |  | CS-BNS 6-2843007-1 |  |  | 10 |  | 42 | 420 |  | 420 |  | 0 | PR-036881-2712 | PO18-00943 |  |  | 2018-02-16 |  | 2018-03-05 | 2018-03-07 |  |  | 03/19/2018-Emailed Tim Scherer about the status confirmation. 02/16/18: Submitted PR. 02/15/18: Requested refresh quotre from Eric Blum 02/09/18: Submit the week of 02/12/18 | Yes | 2332.6
| 2 | 5 | Y |  |  | TCTHG-K;10/100/1000 COPPER nTAP Bluetooth - C1010 | ViaviSolutions |  |  | TCTHG-K | ViaviSolutions |  | 6 |  | 157.49 | 944.94 |  | 4290 |  | -3345.06 | PR-037081-2712 | PO18-01555 |  |  | 2018-03-13 |  | 2018-04-20 | 2018-05-04 |  |  |  | Yes | 4560.3
| 2 | 5 | Y |  |  | TCRM-K;19 in. 1U Rack Mount Panel for up to 3 Copper or Optical nTAPs | ViaviSolutions |  |  | TCRM-K | ViaviSolutions |  | 2 |  | 22.03 | 44.06 |  | 270.3 |  | -226.24 | PR-037081-2712 | PO18-01555 |  |  | 2018-03-13 |  | 2018-04-20 | 2018-05-04 |  |  |  | Yes | 0
| 2 | 5 | Y |  |  | Dell Optiplex 7050 MFF Computer v/VESA Mount | Dell |  |  | 7050 Optiplex | Dell |  | 2 |  | 859.81 | 1719.62 |  | 1719.62 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-17 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 1719.62
| 2 | 5 | Y |  |  | Dell 24 Monitor E2417H | Dell |  |  | 210-AIWH | Dell |  | 2 |  | 157.49 | 314.98 |  | 314.98 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 314.98
| 2 | 5 | Y |  |  | Dell Optiplex Micro Dual VESA mount | Dell |  |  | 482-BBBQ | Dell |  | 1 |  | 24237.88 | 24237.88 |  | 44.06 |  | 24193.82 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-05-04 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 220.3
| 2 | 5 | Y |  |  | PowerEdge R630 Server | Dell |  |  | R630 | Dell |  | 4 |  | 7375.45 | 29501.8 |  | 29783.48 |  | -281.68 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-24 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 29783.48
| 2 | 5 | Y |  |  | Dell 18.5 in 1U Rackmount LED KMM Console | Dell |  |  | A7546778 | Dell |  | 4 |  | 817.49 | 3269.96 |  | 3269.96 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 3269.96
| 2 | 5 | Y |  |  | Dell 1U KVM mounting bracket | Dell |  |  | A7485911 | Dell |  | 4 |  | 67.99 | 271.96 |  | 271.96 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 271.96
| 2 | 5 | Y |  |  | Dell Digital KVM Switch | Dell |  |  | A7546774 | Dell |  | 4 |  | 2243.99 | 8975.96 |  | 8975.96 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 8975.96
| 2 | 5 | Y |  |  | Dell Sever Interface Module | Dell |  |  | A7547276 | Dell |  | 30 |  | 97.49 | 2924.7 |  | 2924.7 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 2924.7
| 2 | 5 | Y |  |  | Dell Optiplex 3050 MFF Computer w/VESA Mount | Dell |  |  | 3050MX | Dell |  | 8 |  | 904.23 | 7233.84 |  | 7233.84 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-04-18 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 7233.84
| 2 | 5 | Y |  |  | Dell OptiPlex Micro Dual VESA Mount | Dell |  |  | 482-BBBQ | Dell |  | 8 |  | 22.03 | 176.24 |  | 176.24 |  | 0 | PR-037093-2712 | PO18-01739 |  |  | 2018-03-20 |  | 2018-04-20 | 2018-05-04 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 0
| 2 | 5 | Y |  |  | Kiwi Syslog Server - Single install - License with 24 Month Maintenance | Solarwinds |  |  | 9016-0514/ 300052053 |  |  | 2 |  | 395 | 790 |  | 671.48 |  | 118.52 | PR-037083-2712 | PO18-01314 |  |  | 2018-03-02 |  | 2018-03-09 | 2018-03-21 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/19/2018-Emailed Rosemarie and Eric Blum for the status check. | Yes | 671.48
| 2 | 5 | Y |  |  | Kiwi Log Viewer (Win) - single install license with 24 month software maintenance plan | Solarwinds |  |  | 9016-0581/ 300052097 |  |  | 2 |  | 114 | 228 |  | 193.8 |  | 34.2 | PR-037083-2712 | PO18-01314 |  |  | 2018-03-02 |  | 2018-03-09 | 2018-03-21 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/19/2018-Emailed Rosemarie and Eric Blum for the status check. | Yes | 193.8
| 2 | 5 | Y |  |  | L-Comm Ethernet media Converter 10/100/1000TX RJ45 to Single Gigabit SFP Socket | L-Comm |  |  | LC-MCGSFP | L-Comm |  | 2 |  | 77.69 | 155.38 |  | 176.91 |  | -21.53 | PR-037077-2712 | PO18-01310 |  |  | 2018-03-02 |  | 2018-03-07 | 2018-03-07 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint | Yes | 176.91
| 2 | 5 | Y |  |  | Keystone Wire & Cable KNP4461030S Access | Windy City Wire MFG |  |  | 4461030S |  |  | 5 |  | 946.21 | 4731.05 |  | 5121.78 |  | -390.73 | PR-037281-2712 | PO18-01730 |  |  | 2018-03-19 |  | 2018-03-30 | 2018-08-21 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/01/18: Receievd quote from Eric Blum and will submit PR 03/01/18: Submit PR week of 02/26/18 | Yes | 5032.65
| 2 | 5 | Y |  |  | Plenum Security Alarm Cable-18/2 (7 Strand),CMP,Shielded 1000ft | Primus Cable |  |  | ACS3-474/182 |  |  | 3 |  | 152.653 | 457.959 |  | 461.58 |  | -3.621 | PR-037283-2712 | PO18-01458 |  |  | 2018-03-08 |  | 2018-03-15 | 2018-03-29 |  |  | 06/19/18: Contacted buyer in reference to this not showing in CostPoint 03/01/18: Submit PR week of 02/26/18 | Yes | 461.58
| 2 | 5 | Y |  |  | Intelligent System Controller- 12 VDC or 24 VDC@300mA, size (5 in. (127mm) Wx 6 in. (152.4mm)Lx 1in. (25mm)H) | Lenel |  |  | LNL-3300 | Ariel Technologies |  | 1 |  | 3568.09 | 3568.09 |  | 1864.34 |  | 1703.75 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 1864.34
| 2 | 5 | Y |  |  | Command Display Lenel Command Keypad-32 character back-lit LCD display with 16 position keypad, supports both direct RS-485 communication with ISC and Wiegand TTL | Lenel |  |  | LNL-CK | Ariel Technologies |  | 1 |  | 1000 | 1000 |  | 373.45 |  | 626.55 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 373.45
| 2 | 5 | Y |  |  | EFLOW104N8D is a power supply/charger that converts a 120VAC 60Hz input into eight protected power-limited 24VDC outputs with a total of 10 amps max. | eFlow |  |  | EFLOW104N8D | Ariel Technologies |  | 1 |  | 1000 | 1000 |  | 425.39 |  | 574.61 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 425.39
| 2 | 5 | Y |  |  | Lenel UL listed hardware enclosure (24"x18"x4.5") only with lock and tamper switch | Lenel |  |  | LNL-CTX-6 | Ariel Technologies |  | 1 |  | 2000 | 2000 |  | 194 |  | 1806 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 194
| 2 | 5 | Y |  |  | Lenel UL Listed Power supply-12 VDC 6A output, 115VAC (1.6 amps) input, continuous supply current with enclosure (24"x18"x4.5") | Lenel |  |  | LNL-AL600ULX-4CB6 | Ariel Technologies |  | 1 |  | 750 | 750 |  | 727.5 |  | 22.5 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 727.5
| 2 | 5 | Y |  |  | Dual Reader Interface Module (Series 2-Supports OSDP Readers)-12/24 VDC, 2 Reader Interface W/M, 8 inputs, 6 (5A) form C relays | Lenel |  |  | LNL-1320 | Ariel Technologies |  | 4 |  | 630 | 2520 |  | 2444.4 |  | 75.6 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 2444.4
| 2 | 5 | Y |  |  | Input Control Module (Series two)-12/24 VDC, 16 zone input monitor module, (32) 1k resistors (with 2 programmable output relays) | Lenel |  |  | LNL-1100 | Ariel Technologies |  | 1 |  | 708 | 708 |  | 686.76 |  | 21.24 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 686.76
| 2 | 5 | Y |  |  | Remote Monitor Client-Single Remote Monitor CLIENT SW LIC. | Lenel |  |  | DVG-RM | Ariel Technologies |  | 1 |  | 417 | 417 |  | 375.3 |  | 41.7 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 375.3
| 2 | 5 | Y |  |  | Onguard ADV client software license includes: system administration,alarm monitoring, map designer and login driver. | Lenel |  |  | SWC-ADV | Ariel Technologies |  | 1 |  | 2800 | 2800 |  | 2520 |  | 280 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 2520
| 2 | 5 | Y |  |  | Lenel network video recorder software-includes single channel software license for one IP/network based camera channel to be used with either a customer provided PC or adding on to a turnkey system. | Lenel |  |  | SW-LNR-CH1 | Ariel Technologies |  | 1 |  | 250 | 250 |  | 225 |  | 25 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 225
| 2 | 5 | Y |  |  | iclass, Finished Wall reader, RP40-H,PIVCLASS, SE E, LF STD,HF STD/SIO/SEOS/FIPS/CAK,485HDX,PIG, Black,STD-1,LED RED,FLSH GRN,BZR ON,OPT TAMP,OPEN COLL,FIPS 75-BIT,IPM OFF, UART OFF, WEIG ON | HID |  |  | 920PHPNEK00338 | Ariel Technologies |  | 8 |  | 352 | 2816 |  | 2534.4 |  | 281.6 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 2534.4
| 2 | 5 | Y |  |  | iclass, reader, RPKCL40-P,PIVCLASS,SE E, CONT LCD,LF STD,HF STD/SIO/SEOS/FIPS/CAK/PKI,485HDX,PIG,Black, STD-1, LED RED,FLSH GRN, BZR ON, OPT TAMP | HID |  |  | 923PPPNEK0033T | Ariel Technologies |  | 1 |  | 895 | 895 |  | 805.5 |  | 89.5 | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 805.5
| 2 | 5 | Y |  |  | Door security electronics |  |  |  | Discounts | Ariel Technologies |  | 1 |  | -934.74 | -934.74 |  | 0 |  |  | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  | 03/01/18: Submit PR week of 02/26/18 | Yes | 0
| 2 | 5 | Y |  |  | Door security electronics |  |  |  | Shipping | Ariel Technologies |  | 1 |  | 300 | 300 |  | 300 |  |  | PR-037328-2712 | PO18-02621 |  |  | 2018-04-25 |  | 2018-05-18 | 2018-05-10 |  |  |  | Yes | 300
| 2 | 5 | Y |  |  | Slave timing system, 2 fiber in, Rb ref, 2 AC supp, No out mod | Microsemi |  |  | ATS 6511C-FRN |  |  | 5 |  | 15120 | 75600 |  | 75600 |  | 0 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-07-23 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 75600
| 2 | 5 | Y |  |  | 10 MHz Module for Item 1 | Microsemi |  |  | 4395B-10 |  |  | 10 |  | 595 | 5950 |  | 5950 |  | 0 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-07-23 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 5950
| 2 | 5 | Y |  |  | Pulse Output Module for item 1 | Microsemi |  |  | 4394A |  |  | 12 |  | 595 | 7140 |  | 7140 |  | 0 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-07-23 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 7140
| 2 | 5 | Y |  |  | Fiber Output Module for item 1 | Microsemi |  |  | 4372A-T |  |  | 3 |  | 1495 | 4485 |  | 4485 |  | 0 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-07-23 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 4485
| 2 | 5 | Y |  |  | Modulated IRIG Module for item 1 | Microsemi |  |  | 4387A |  |  | 3 |  | 595 | 1785 |  | 1785 |  | 0 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-07-23 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 1785
| 2 | 5 | Y |  |  | Pre-Configured S650i w/ std osc, I/O module, single AC, no GNSS | Microsemi |  |  | 090-15200-653 |  |  | 3 |  | 3595 | 10785 |  | 11229.15 |  | -444.15 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-06-25 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 11229.15
| 2 | 5 | Y |  |  | S650 Security Protocols License Option, Quick Ship | Microsemi |  |  | 920-15201-002 |  |  | 1 |  | 13882.13 | 13882.13 |  | 4200 |  | 9682.13 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-06-25 |  |  |  | Yes | 4900
| 2 | 5 | Y |  |  | Distribution Amplifier with Auto Switching | Microsemi |  |  | 9611B-02 |  |  | 10 |  | 5350 | 53500 |  | 34066.5 |  | 19433.5 | PR-036750-2712 | PO18-02027 |  |  | 2018-03-30 |  | 2018-07-16 | 2018-06-25 |  |  | 02/09/18: Submit the week of 02/12/18 | Yes | 34066.5
QUOTE NO. 8031601 received 03/19/18 | 3 | 3 | Y |  |  | Mu-Del Up/Down Converter | Mu-Del Electronics |  |  | MUDC-625-70 |  |  | 3 |  | 12250 | 36945 |  | 36750 |  |  | PR-039778-2712 | PO18-03932 |  |  | 2018-06-26 |  | 2018-11-26 |  |  |  |  | Yes | 36750
| 3 | 3 | Y |  |  | Shipping | Mu-Del Electronics | [7 empty] | 195 |  |  | 195 |  |  | PR-039778-2712 | PO18-03932 |  |  | 2018-06-26 |  | 2018-11-26 |  |  |  |  | Yes | 195
Quote received: PERATON - QT#O6UJ9A0014YJ 7X7 MATRIX | 3 | 3 | Y |  |  | Matrix-EM Custom DOW-KEY | Dow-Key Microwave |  |  | 5454 |  |  | 1 |  | 31000 | 31000 |  | 31000 |  | 0 | PR-039785-2712 | PO18-03785 |  |  | 2018-06-19 |  | 2018-09-28 | 2018-09-25 |  |  | Week two Priority 06/04/18 | Yes | 31000
| 3 | 3 | Y |  |  | Shipping | Dow-Key Microwave | [5 empty] | 1 |  | 175 | 175 |  | 175 |  |  | PR-039785-2712 | PO18-03785 |  |  | 2018-06-19 |  | 2018-09-28 | 2018-09-25 |  |  | Week two Priority 06/04/18 | Yes | 29818
Quote received: PERATON - QT#O6UJ9A0014YJ 4X3 AND 10X5 | 3 | 3 | Y |  |  | Matrix-EM Custom DOW-KEY | Dow-Key Microwave |  |  | 5453 |  |  | 1 |  | 29818 | 29818 |  | 29818 |  | 0 | PR-039785-2712 | PO18-03785 |  |  | 2018-06-19 |  | 2018-09-28 | 2018-09-25 |  |  | Week two Priority 06/04/18 | Yes | 350
| 3 | 3 | Y |  |  | Shipping | Dow-Key Microwave | [5 empty] | 1 |  | 175 | 175 |  | 175 |  |  | PR-039785-2712 | PO18-03785 |  |  | 2018-06-19 |  | 2018-09-28 | 2018-09-25 |  |  | Week two Priority 06/04/18 | Yes | 0
Quote received 03/14/18 | 3 | 3 | Y |  |  | QuickTreX 24 Port Shileded Keystone Blank Patch Panel (1RU) )With Cable Manager+ $14.00, 24 Couplers+334.80, Without Hinged Wall Bracket) | LanShack |  |  | QT-24BSPP-1U-CM-24SC |  |  | 1 |  | 378.75 | 378.75 |  | 378.75 |  | 0 | PR-039842-2712 | PO18-03522 |  |  | 2018-06-08 |  | 2018-06-13 | 2018-06-15 |  |  | Week two Priority 06/04/18 | Yes | 378.75
| 3 | 3 | Y |  |  | COMMSCOPE (FORMERLY TE CONN) 6-2843007-1 MODULAR PLUG CAT 6A/6 UNSHIELDED, COND INSULATION OD-0.99MM, 100PCS | Anixter |  |  | 922414 |  |  | 5 |  | 45.66 | 228.3 |  | 228.3 |  | 0 | PR-039850-2712 | PO18-03509 |  |  | 2018-06-07 |  | 2018-06-13 | 2018-06-19 |  |  | Week two Priority 06/04/18 | Yes | 228.3
| 3 | 3 | Y |  |  | CS-ANDREW 2843023-3 RJ 45 BOOT -- -- Lead Time: 4 week lead time from the vendor Part Availability: Minimum 500 pieces | Anixter |  |  | 2843023-3 |  |  | 5 |  | 23.61 | 118.05 |  | 118.05 |  | 0 | PR-039850-2712 | PO18-03509 |  |  | 2018-06-07 |  | 2018-06-13 | 2018-07-13 |  |  | Week two Priority 06/04/18 | Yes | 118.05
| 3 | 3 | Y |  |  | 14ZZZ-FREIGHT | Anixter | [5 empty] | 1 |  | 50 | 50 |  | 50 |  | 0 | PR-039850-2712 | PO18-03509 |  |  | 2018-06-07 |  | 2018-06-13 | 2018-07-13 |  |  | Week two Priority 06/04/18 | Yes | 50
| 3 | 3 | Y |  |  | Cat 6E 1000x, UTP, Plenum rated (CMP), Solid Cond. Cable -1000 Ft by ABA Elite (Blue) | LanShack |  |  | EL-TUP2404N70-SBU-S |  |  | 2 |  | 358.53 | 717.06 |  | 717.06 |  | 0 | PR-039842-2712 | PO18-03522 |  |  | 2018-06-08 |  | 2018-06-13 | 2018-06-15 |  |  | Week two Priority 06/04/18 | Yes | 717.06
| 3 | 3 | Y |  |  | Shipping | LanShack | [5 empty] | 1 |  | 30 |  |  | 30 |  |  | PR-039842-2712 | PO18-03522 |  |  | 2018-06-08 | 2018-06-13 | 2018-06-13 | 2018-06-15 |  |  |  | Yes | 30
| 3 | 3 | Y |  |  | RG400 Coax Cable | Tessco |  |  | 273397 |  |  | 1500 |  | 2.9 | 4350 |  | 3000 |  | 1350 | PR-039854-2712 | PO18-03736 |  |  | 2018-06-18 |  | 2018-07-23 | 2018-09-18 |  |  | Week two Priority 06/04/18 | Yes | 3000
| 3 | 3 | Y |  |  | SMA Male RG-142,55B,223 901-9511-1 | Tessco |  |  | 584614 |  |  | 150 |  | 9.17 | 1375.5 |  | 1375.5 |  | 0 | PR-039854-2712 | PO18-03736 |  |  | 2018-06-18 |  | 2018-07-23 | 2018-07-23 |  |  | Week two Priority 06/04/18 | Yes | 1375.5
| 3 | 3 | Y |  |  | TNC Crimp RG55, 142, 223 122372 | Tessco |  |  | 378066 |  |  | 20 |  | 1.4 | 28 |  | 28 |  | 0 | PR-039854-2712 | PO18-03736 |  |  | 2018-06-18 |  | 2018-07-23 | 2018-07-23 |  |  | Week two Priority 06/04/18 | Yes | 28
| 3 | 3 | Y |  |  | BNC Male Crimp-RG142 | Tessco |  |  | 491002 |  |  | 25 |  | 2.81 | 70.25 |  | 70.25 |  | 0 | PR-039854-2712 | PO18-03736 |  |  | 2018-06-18 |  | 2018-07-23 | 2018-07-23 |  |  | Week two Priority 06/04/18 | Yes | 70.25
| 3 | 3 | Y |  |  | Shipping | Tessco | [5 empty] | 1 |  | 194.36 | 194.36 |  | 194.36 |  | 0 | PR-039854-2712 | PO18-03736 |  |  | 2018-06-18 |  | 2018-07-23 | 2018-07-23 |  |  | Week two Priority 06/04/18 | Yes | 194.36
| 4 | 3 | Y |  |  | Soil Sample Procurement | Terracon | [5 empty] | 1 |  |  | 2950 |  | 2950 |  | 0 | PR-039843-2712 | PO18-03491 |  |  | 2018-06-07 |  | 2018-06-08 | 2018-06-08 |  |  |  | Yes | 2950
| 3 | 4 | Y |  |  | Descope: IEM Softbench Simulator | [6 empty] | 1 |  | -61056.95 | -61056.95
Quote received 02/12/18 | 3 | 4 | Y |  |  | XPS 15 Equipment | Dell |  |  | XPS 15 |  |  | 2 |  | 1939.905 | 3879.81 |  | 4296.1 |  | -416.29 | PR-040272-2712 | PO18-04712 |  |  | 2018-08-09 |  | 2018-08-24 | 2018-09-19 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive Week Three priority (06/11/18) 06/06/18: Awaiting refresh quote from Adam Mirvis. | Yes | 4296.1
Quote received 02/12/18 | 3 | 4 | Y |  |  | Dell Adapter- USB-C to Ethernet (PXE Boot) | Dell |  |  | 470-ABND |  |  | 2 |  |  |  |  | 70.18 |  |  | PR-040272-2712 | PO18-04712 |  |  | 2018-08-09 |  | 2018-08-24 | 2018-09-19 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive Week Three Priority (06/11/18) 06/06/18: Awaiting refresh quote from Adam Mirvis | Yes | 0
Quote Number: NDS-113445b R1 received 03/20/18 | 3 | 4 | Y |  |  | Compass Redundant Backup System | Kratos |  |  | C-REDUNDANCY-15000 |  |  | 1 |  | 15000 | 0 |  | 15000 |  |  | PR-040130-2712 | PO18-04095 |  |  | 2018-07-06 |  | 2018-07-31 | 2018-08-09 |  |  | 02/06/18: For Pete Gaffney; Ship to Walker Drive. 06.11.2018-Week Three priority (06/11/18). Awaiting refresh quote from Pete Gaffney | Yes | 15000
Quote Number: NDS-113445b R1 received 03/20/18 | 3 | 4 | Y |  |  | A browser-based interface 5-pack for operator access, configuration and system modifications | Kratos |  |  | C-GUI-5 |  |  | 2 |  | 2250 | 0 |  | 4500 |  |  | PR-040130-2712 | PO18-04095 |  |  | 2018-07-06 |  | 2018-07-31 | 2018-08-09 |  |  | 06.11.2018-Week Three priority (06/11/18). Awaiting refresh quote from Pete Gaffney | Yes | 2250
Quote Number: NDS-113445b R1 received 03/20/18 | 3 | 4 | Y |  |  | Compass module that provides support for SNMP Manager V1, V2 and V3 capabilities. It provides an Alarm Trap GUI and allows for auto discovery and import of SNMP MIBs into Compass | Kratos |  |  | C-SNMP Server |  |  | 2 |  | 2250 | 0 |  | 4500 |  |  | PR-040130-2712 | PO18-04095 |  |  | 2018-07-06 |  | 2018-07-31 | 2018-08-09 |  |  | 06.11.2018-Week Three priority (06/11/18). Awaiting refresh quote from Pete Gaffney | Yes | 2250
| 3 | 4 | Y |  |  | A browser-based interface 5-pack for operator access, configuration and system modifications. | RTL/Kratos |  |  | C-GUI-5 |  |  | 1 |  |  |  |  | -2250 |  |  | PR-041001-2712 | PO18-04095 |  |  | 2018-07-31 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 4875
| 3 | 4 | Y |  |  | Compass module that provides support for SNMP Manager V1, V2 and V3 capabilities. It provides an Alarm Trap GUI and allows for auto discovery and import of SNMP MIBs into Compass. | RTL/Kratos |  |  | C-SNMP Server |  |  | 1 |  |  |  |  | -2250 |  |  | PR-041001-2712 | PO18-04095 |  |  | 2018-07-31 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 0
| 3 | 4 | Y |  |  | 12 Months Compass PLATINUM Maintenance for all software licenses from NDS-112846R2b. | RTL/Kratos |  |  | C- PLAT- MAIN-12 |  |  | 1 |  |  |  |  | -1125 |  |  | PR-041001-2712 | PO18-04095 |  |  | 2018-07-31 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 0
| 3 | 4 | Y |  |  | 12 Months Compass PLATINUM Maintenance for all software licenses from NDS-112846R2b. | Kratos |  |  | C- PLAT- MAIN-12 |  |  | 1 |  |  |  |  | 5667 |  |  | PR-040479-2712 | PO18-04098 |  |  | 2018-07-06 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 11335.01
| 3 | 4 | Y |  |  | Compass server license of for monitor and control of 100 devices remotely and automatically. Includes: - 1 Server license for up to 100 devices - 1 Compass GUI license - web-based interface for operator access, configuration and system modifications - Monitor and control of 100 devices via Ethernet, SNMP, Serial, TL-1, proprietary protocols, TBOS and Discrete IO - USB Key | RTL/Kratos |  |  | C-SERVER-100 |  |  | 1 |  |  |  |  | -11335.01 |  |  | PR-040977-2712 | PO18-04098 |  |  | 2018-07-27 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 2833.5
| 3 | 4 | Y |  |  | 12 Months Compass PLATINUM Maintenance for all software licenses from NDS-112846R2a. *OPEN MARKET ITEM* | RTL/Kratos |  |  | C- PLAT- MAIN-12 |  |  | 1 |  |  |  |  | -2833.5 |  |  | PR-040977-2712 | PO18-04098 |  |  | 2018-07-27 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 0
Quote Number: NDS-113445b R1 received 03/20/18 | 3 | 4 | Y |  |  | C-SNMP-SERVER | Kratos |  |  | 5B909 / 437164J |  |  | 2 |  | 3000 | 6000 |  | 1250 |  |  | PR-039624-2712 | PO18-03663 |  |  | 2018-06-14 |  | 2018-06-15 | 2018-07-10 |  |  | Week One Priority (05/29/18) | Yes | 11625
| 3 | 4 | Y |  |  | C-REDUNDANCY | Kratos |  |  | 5B909 /437164J |  |  | 2 |  | 2833.5 | 5667 |  | 1250 |  |  | PR-039624-2712 | PO18-03663 |  |  | 2018-06-14 |  | 2018-06-15 | 2018-07-10 |  |  | Week One Priority (05/29/18) | Yes | 0
| 3 | 4 | Y |  |  | C-GUI-5 |  |  |  | 5B909 / 437164J |  |  | 2 |  |  | 0 |  | 1125 |  |  | PR-039624-2712 | PO18-03663 |  |  | 2018-06-14 |  | 2018-06-15 | 2018-07-10 |  |  | Week One Priority (05/29/18) | Yes | 0
| 3 | 4 | Y |  |  | C-SERVER-100-U | Kratos |  |  | 5B909 / 437164J |  |  | 2 |  |  | 0 |  | 8000 |  |  | PR-039624-2712 | PO18-03663 |  |  | 2018-06-14 |  | 2018-06-15 | 2018-07-10 |  |  | Week One Priority (05/29/18) | Yes | 0
Quote Number: NDS-113445a R1 received 03/20/18 | 3 | 4 | Y |  |  | Compass server license of for monitor and control of 100 devices remotely and automatically. Includes: - 1 Server license for up to 100 devices - 1 Compass GUI license - web-based interface for operator access, configuration and system modifications - Monitor and control of 100 devices via Ethernet, SNMP, Serial, TL-1, proprietary protocols, TBOS and Discrete IO - USB Key | Kratos |  |  | C-SERVER-100 |  |  | 1 |  | 46670.06 | 46670.06 |  | 22670.02 |  | 24000.04 | PR-040479-2712 | PO18-04098 |  |  | 2018-07-06 | 2018-07-13 | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 0
| 3 | 4 | Y |  |  | 12 Months Compass PLATINUM Maintenance for all software licenses from NDS-112846R2a. *OPEN MARKET ITEM* | Kratos |  |  | C- PLAT- MAIN-12 |  |  | 1 |  |  |  |  | 0 |  |  | PR-040130-2712 | PO18-04095 |  |  | 2018-07-06 |  | 2018-07-31 | 2018-08-09 |  |  |  | Yes | 0
Quote received 03/14/18 | 3 | 4 | Y |  |  | Optiplex 7050 MFF | Dell |  |  | Dell Optiplex 7050 Micro |  |  | 1 |  | 2068.56 | 2068.56 |  | 1082.84 |  | 985.72 | PR-041156-2712 | PO18-04657 |  |  | 2018-08-06 |  | 2018-08-24 | 2018-08-28 |  |  | 02/06/18: For Pete Gaffney; Ship to Walker Drive | Yes | 1082.84
Quote received 03/14/18 | 3 | 4 | Y |  |  | Dell UltraSharp 34 Curved Ultrawide Monitor | Dell |  |  | E2417H |  |  | 1 |  | 379.98 | 379.98 |  | 783 |  | -403.02 | PR-040131-2712 | PO18-03804 |  |  | 2018-06-20 |  | 2018-06-27 | 2018-06-22 |  |  | 06.11.2018-Week Three priority (06/11/18). Pete will send a new quote for curve monitor. | Yes | 783
| 3 | 4 | Y |  |  | Dell UltraSharp 34 Curved Ultrawide Monitor | Dell |  |  | U341/ U3415W |  |  | 1 |  |  | 0 |  | 794.99 |  |  | PR-041109-2712 | PO18-04529 |  |  | 2018-07-30 |  | 2018-08-06 | 2018-08-07 |  |  |  | Yes | 794.99
| 3 | 4 | Y |  |  | Shipping | Dell | [5 empty] | 1 |  |  |  |  | 33 |  |  | PR-041109-2712 | PO18-04529 |  |  | 2018-07-30 |  | 2018-08-06 | 2018-08-07 |  |  |  | Yes | 0
DO NOT ORDER | 3 | 4 | Y |  |  | Dell Micro All in-One Stand | Dell | [5 empty] | 2 |  | 99.99 | 199.98 | [14 empty] | 07/26/18: Pete advised; Do not order.
DO NOT ORDER | 3 | 4 | Y |  |  | Shipping | [8 empty] | 34.99 | 34.99
Quote received 03/14/18 | 3 | 4 | Y |  |  | Red Hat Enterprise Linux Server, Standard (Physical or Virtual Nodes) | Red Hat |  |  | RH00004 |  |  | 6 |  | 799 | 4794 |  | 11400.48 |  | -6606.48 | PR-040397-2712 | PO18-04376 |  |  | 2018-07-24 |  | 2018-07-27 | 2018-07-27 |  |  | 02/06/18: For Pete Gaffney; Ship to Walker Drive | Yes | 11400.48
Quote received 03/14/18 | 3 | 4 | Y |  |  | Red Hat Enterprise Linux Developer Suite | Red Hat |  |  | RH2262474 |  |  | 3 |  | 99 | 297 |  | 277.35 |  | 19.65 | PR-041127-2712 | PO18-04569 |  |  | 2018-08-01 |  | 2018-08-10 | 2018-11-06 |  |  |  | No | [5 empty] | 277.35
Quote received 02/12/18 | 3 | 4 | Y |  |  | Cisco WS-C2960 switch | Cisco |  |  | WS-C2960X-24TS-L |  |  | 1 |  | 1057.09 | 1057.09 |  | 807.09 |  | 250 | PR-039861-2712 | PO18-03510 |  |  | 2018-06-08 |  | 2018-06-14 | 2018-06-11 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive Week Two Priority (06/04/18) | Yes | 807.09
Quote received 02/12/18 | 3 | 4 | Y |  |  | Red Hat Enterprise Linux Workstation, Self-support | Red Hat |  |  | RH0986300 |  |  | 6 |  | 179 | 1074 | [14 empty] | 03/05/18: PR Updated. B0 Contract # 11438921 and order # 40282170. The B1 set have contract # 11330596 and order # 40262378. 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive | Yes
Quote received 02/12/18 | 3 | 4 | Y |  |  | Cat6 Gray Ethernet Patch Cable, Snagless/Molded Boot, 5 foot | CableWholesale |  |  | 10X8-02105 |  |  | 3 |  | 1.79 | 5.37 |  | 5.37 |  | 0 | PR-041175-2712 | PO18-04666 |  |  | 2018-08-07 |  | 2018-08-10 | 2018-08-10 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive | Yes | 5.37
Quote received 02/12/18 | 3 | 4 | Y |  |  | Cat6 Gray Ethernet Patch Cable, Snagless/Molded Boot, 14 foot | CableWholesale |  |  | 10X8-02114 |  |  | 2 |  | 3.91 | 7.82 |  | 7.8 |  | 0.02 | PR-041175-2712 | PO18-04666 |  |  | 2018-08-07 |  | 2018-08-10 | 2018-08-10 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive | Yes | 7.8
| 3 | 4 | Y |  |  | Shipping | [8 empty] | 14.87 | 14.87 |  | 11.65 |  | 3.22 | PR-041175-2712 | PO18-04666 |  |  | 2018-08-07 |  | 2018-08-10 | 2018-08-10 |  |  |  | Yes | 11.65
Quote received 03/05/18 | 3 | 4 | Y |  |  | Broadcom 5720 DP 1Gb Network Interface Card, Low Profile,Customer Kit | Dell |  |  | 540-BBGW |  |  | 3 |  | 102.22 | 308.66 |  | 357.66 |  | -49 | PR-040272-2712 | PO18-04712 |  |  | 2018-08-09 |  | 2018-08-24 | 2018-09-13 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive. 06.11.2018-Week Three priority (06/11/18). Awaiting refresh quote from Adam Mirvis | Yes | 0
| 3 | 4 | Y |  |  | A. I. Solutions Software | A.I. Solutions | [5 empty] | 1 |  | 40871 | 40871 |  | 40871 |  | 0 | PR184207 | PO18-05191 |  |  | 2018-09-06 |  | 2018-09-06 | 2018-09-12 |  |  |  | Yes | 40871
| 3 | 4 | Y |  |  | A. I. Solutions Software | A.I. Solutions | [5 empty] | 1 |  | 7370 | 7370 |  | 7370 |  | 0 | PR184207 | PO18-05191 |  |  | 2018-09-06 |  | 2018-09-06 | 2018-09-12 |  |  |  | Yes | 7370
| 3 | 4 | Y |  |  | A. I. Solutions Software | A.I. Solutions | [5 empty] | 1 |  | 30000 | 30000 |  | 30000 |  | 0 | PR184207 | PO18-05191 |  |  | 2018-09-06 |  | 2018-09-06 | 2018-09-12 |  |  |  | Yes | 30000
| 3 | 4 | Y |  |  | A. I. Solutions Software | A.I. Solutions | [5 empty] | 1 |  | 5400 | 5400 |  | 5400 |  | 0 | PR184207 | PO18-05191 |  |  | 2018-09-06 |  | 2018-09-06 | 2018-09-12 |  |  |  | Yes | 5400
Quote received 02/06/18 | 3 | 4 | Y |  |  | Windows 10 Pro | Microsoft | [5 empty] | 2 |  | 199.99 | 399.98 |  | 379.2 |  | 20.78 | PR-041159-2712 | PO18-04638 |  |  | 2018-08-03 |  | 2018-08-10 | 2018-08-14 |  |  | 03/05/18: Omitron. Goes to Omitron; Ship to Walker Drive | Yes | 379.2
| 3 | 5 | Y |  |  | USM Appliance, All-in-One UA - Hardware Appliance | AlienVault | No |  | APP-L-AU-H.01 |  |  | 1 |  | 37195 | 37195 |  | 32879.56 |  | 4315.44 | PR-039648-2712 | PO18-03643 |  |  | 2018-06-14 |  | 2018-07-13 | 2018-06-25 |  |  | Week One Priority (05/29/18) | Yes | 32879.56
| 3 | 5 | Y |  |  | USM Appliance, Standard Sensor 6x1GbE - Hardware Appliance | AlienVault | No |  | APP-L-SSN6X-H.01 |  |  | 1 |  | 27195 | 27195 |  | 24039.78 |  | 3155.22 | PR-039648-2712 | PO18-03643 |  |  | 2018-06-14 |  | 2018-07-13 | 2018-06-25 |  |  | Week One Priority (05/29/18) | Yes | 24039.78
| 3 | 5 | Y |  |  | USM Appliance, Professional Services (1 Unit) | AlienVault | No |  | PS-APP-PS1U.01 |  |  | 1 |  | 2495 | 2495 |  | 0 |  | 2495 | PR-039648-2712 | PO18-03643 |  |  | 2018-06-14 |  | 2018-07-13 | 2018-07-06 |  |  | Week One Priority (05/29/18) | Yes | 0
| 3 | 5 | Y |  |  | Training, AlienVault USM Appliance for Security Engineers (AUSE) (5 days), Public, One (1) Student | AlienVault | No |  | TRN-APP-PUB-SE1S.01 |  |  | 2 |  | 3895 | 7790 |  | 3895 |  | 3895 | PR-039648-2712 | PO18-03643 |  |  | 2018-06-14 |  | 2018-07-13 | 2018-07-06 |  |  | Week One Priority (05/29/18) | Yes | 3895
| 3 | 5 | Y |  |  | Descope: SCWA Door | Descope from Mod 2 | [5 empty] | 1 |  | -11300 | -11300 | [15 empty] | N/A
| 3 | 5 | Y |  |  | IEM Softbench Simulator | Descope from Mod 2 | [5 empty] | 1 |  | -204408.05 | -204408.05 | [15 empty] | N/A
Quote received 03/12/18 | 3 | 5 | Y |  |  | LEGS FOR 30"D WORK SURFACE | Winsted Consoles | No |  | 48018 |  |  | 6 |  | 347.9 | 2087.4 |  | 2087.4 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | MODESTY PANEL FOR SIDE DESK | Winsted Consoles | No |  | 48112 |  |  | 6 |  | 163.1 | 978.6 |  | 978.6 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (B)LAMINATE W/SAFEGUARD WS | Winsted Consoles | No |  | S48584 |  |  | 2 |  | 432.99 | 865.98 |  | 865.98 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (C)LAMINATE W/SAFEGUARD WS | Winsted Consoles | No |  | S48584 |  |  | 2 |  | 432.99 | 865.98 |  | 865.98 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (D)LAMINATE W/SAFEGAURD WS | Winsted Consoles | No |  | S48584 |  |  | 2 |  | 432.99 | 865.98 |  | 865.98 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | 3/4" VERSA TRACK FOR 60" TOP | Winsted Consoles | No |  | 48244 |  |  | 6 |  | 209.3 | 1255.8 |  | 1255.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | ARTICULATING LCD MOUNT 15"H | Winsted Consoles | No |  | W6491 |  |  | 12 |  | 319.2 | 3830.4 |  | 3830.4 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | PULLOUT SWIVEL CPU HOLDER | Winsted Consoles | No |  | 46260 |  |  | 6 |  | 128.8 | 772.8 |  | 772.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | LEGS FOR 30"D WORK SURFACE | Winsted Consoles | No |  | 48018 |  |  | 2 |  | 347.9 | 695.8 |  | 695.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | MODESTY PANEL FOR 48" DESK | Winsted Consoles | No |  | 48111 |  |  | 2 |  | 152.6 | 305.2 |  | 305.2 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (E)LAMINATE W/SAFEGUARD WS | Winsted Consoles | No |  | S48580 |  |  | 1 |  | 362.99 | 362.99 |  | 362.99 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (F)LAMINATE W/SAFEGUARD WS | Winsted Consoles | No |  | S48580 |  |  | 1 |  | 362.99 | 362.99 |  | 362.99 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | 3/4" VERSA TRACK FOR 48" TOP | Winsted Consoles | No |  | 48242 | 1473.4985 |  | 2 |  | 191.1 | 382.2 |  | 382.2 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | ARTICULATING LCD MOUNT 15"H | Winsted Consoles | No |  | W6491 |  |  | 4 |  | 319.2 | 1276.8 |  | 1276.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | PULLOUT SWIVEL CPU HOLDER | Winsted Consoles | No |  | 46260 |  |  | 2 |  | 128.8 | 257.6 |  | 257.6 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | 28.5"H MOUNTING POST | Winsted Consoles | No |  | 64402 |  |  | 3 |  | 103.6 | 310.8 |  | 310.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | CUSTOM PARTITION | Winsted Consoles | No |  | S64711 |  |  | 3 |  | 388.97 | 1166.91 |  | 1166.91 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | LEGS FOR 30"D WORK SURFACE | Winsted Consoles | No |  | 48018 |  |  | 1 |  | 347.9 | 347.9 |  | 347.9 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | MODESTY PANEL FOR 72" DESK | Winsted Consoles | No |  | 48113 |  |  | 1 |  | 188.3 | 188.3 |  | 188.3 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | (G)LAMINATE W/SAFEGAUARD WS | Winsted Consoles | No |  | S48582 |  |  | 1 |  | 474.13 | 474.13 |  | 474.13 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | 3/4" VERSA TRACK FOR 72" TOP | Winsted Consoles | No |  | 48246 |  |  | 1 |  | 228.2 | 228.2 |  | 228.2 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | ARTICULATING LCD MOUNT 15"H | Winsted Consoles | No |  | W6491 |  |  | 2 |  | 319.2 | 638.4 |  | 638.4 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | PULLOUT SWIVEL CPU HOLDER | Winsted Consoles | No |  | 46260 |  |  | 1 |  | 128.8 | 128.8 |  | 128.8 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | 24/7 HIGH BACK CHAIR, BLACK | Winsted Consoles | No |  | 11745 |  |  | 10 |  | 1132 | 11320 |  | 11320 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | FREIGHT/HANDLING/INSURANCE CHG | Winsted Consoles | No |  | 1 |  |  | 1 |  | 2988 | 2988 |  | 2988 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/12/18 | 3 | 5 | Y |  |  | ONSITE ASSEMBLY | Winsted Consoles | No |  | 10202 |  |  | 1 |  | 5353 | 5353 |  | 5353 |  | 0 | PR-039862-2712 | PO18-03940 |  |  | 2018-07-02 |  | 2018-08-03 | 2018-10-12 |  |  | Week Two Priority (06/04/18) | Yes | 1473.4985
Quote received 03/06/18 | 3 | 5 | Y |  |  | SS-16D DOD High Security Paper & CD Shredder w/ Auto Oiler | Capital Shredder | No |  |  |  |  | 1 |  | 6779 | 6779 |  | 6779 |  | 0 | PR-039876-2712 | PO18-03806 |  |  | 2018-06-21 |  | 2018-07-06 | 2018-07-02 |  |  | Week Two Priority (06/04/18) | Yes | 6779
| 3 | 5 | Y |  |  | Shipping | Capital Shredder | [5 empty] | 1 |  | 338.95 | 338.95 |  | 339 |  | -0.05 | PR-039876-2712 | PO18-03806 |  |  | 2018-06-21 |  | 2018-07-06 | 2018-07-02 |  |  | Week Two Priority (06/04/18) | Yes | 339
Quote received 03/14/18 | 3 | 5 | Y |  |  | Type F - Rackmount 2U (L/R/VoIP) w/KPS | Frequentis | No |  | 30-1002200 |  |  | 2 |  | 3693 | 7386 |  | 7386 |  | 0 | PR-039878-2712 | PO18-04700 |  |  | 2018-08-20 |  | 2019-02-15 |  |  |  | Week Two Priority (06/04/18) | No | [5 empty] | 7386
| 3 | 5 | Y |  |  | Maintenance for 1st year | Frequentis | No | [6 empty] | 48 | 48 |  | 0 |  | 48 | PR-039878-2712 | PO18-04700 |  |  | 2018-08-20 |  | 2019-02-15 |  |  |  | Week Two Priority (06/04/18) | No | [5 empty] | 0
Quote received 03/14/18 | 3 | 5 | Y |  |  | Handset 02.00 (PTT/PJ7) | Frequentis | No |  | 70-0000626 |  |  | 2 |  | 146 | 292 |  | 292 |  | 0 | PR-039878-2712 | PO18-04700 |  |  | 2018-08-20 |  | 2019-02-15 |  |  |  | Week Two Priority (06/04/18) | No | [5 empty] | 292
This quote is not an official quote. I understand they do not provide this but this will not be eligible for Mod 3 submission. | 3 | 5 | Y |  |  | GSA Approved Class 6 - 4 Drawer - Multi Lock - Legal Size - Gray -Style 1 Kaba Mas X-10 Lock approved under FF-L-2740 | K L Security | No |  | 7110-01-563-1698 |  |  | 1 |  | 6485 | 6485 |  | 6180 |  | 305 | PR-039901-2712 | PO18-03741 |  |  | 2018-06-18 |  | 2018-07-20 | 2018-07-23 |  |  | Week Two Priority (06/04/18) | Yes | 6180
| 3 | 5 | Y |  |  | Shipping | K L Security |  |  | Shipping | [7 empty] | 175 |  |  | PR-039901-2712 | PO18-03741 |  |  | 2018-06-18 |  | 2018-07-20 | 2018-07-23 |  |  |  | Yes | 175
Eric Blum will provide updated quote. | 3 | 5 | Y |  |  | US National Sectéra vIPer Universal Secure Phone Fiber | GD Mission Systems | Yes |  | VIPF1000- XAMDM |  |  | 8 |  | 2995 | 23960 |  | 2995 |  | 20965 | PR-039970-2712 | PO18-03584 |  |  | 2018-06-11 |  | 2018-06-18 | 2018-08-30 |  |  | Week Three Priority (06/11/18) | Yes | 2995
| 3 | 5 | Y |  |  | DTD Fill Cable for SWT, vIPer | GD Mission Systems | Yes |  | 1DGTDTDX01 |  |  | 1 |  | 115 | 115 |  | 115 |  | 0 | PR-039970-2712 | PO18-03584 |  |  | 2018-06-11 |  | 2018-06-18 | 2018-08-30 |  |  | Week Three Priority (06/11/18) | Yes | 115
| 3 | 5 | Y |  |  | SW Update Cable for SWT & vIPer | GD Mission Systems | Yes |  | VIPUPDC01 |  |  | 1 |  | 50 | 50 |  | 50 |  | 0 | PR-039970-2712 | PO18-03584 |  |  | 2018-06-11 |  | 2018-06-18 | 2018-08-30 |  |  | Week Three Priority (06/11/18) | Yes | 0
| 3 | 5 | Y |  |  | Shipping | GD Mission Systems | Yes |  |  |  |  | 1 |  |  |  |  | 50 |  |  | PR-039970-2712 | PO18-03584 |  |  | 2018-06-11 |  | 2018-06-18 | 2018-08-30 |  |  |  | Yes | 50
Quote received 03/06/18 | 3 | 5 | Y |  |  | Capable Upgrade (with PSTN Connect) | Siemens | Yes |  | L30250F0600C164 |  |  | 8 |  | 330 | 2640 |  | 2640 |  | 0 | PR-039904-2712 | PO18-03536 |  |  | 2018-06-08 |  | 2018-06-18 | 2018-06-19 |  |  | Week Two Priority (06/04/18) | Yes | 2640
Quote received 03/06/18 | 3 | 5 | Y |  |  | Shipping | Siemens | [5 empty] | 1 |  | 111.27 | 111.27 |  | 22.44 |  | 88.83 | PR-039904-2712 | PO18-03536 |  |  | 2018-06-08 |  | 2018-06-18 | 2018-06-19 |  |  | Week Two Priority (06/04/18) | Yes | 22.44
Quote received 03/14/18 | 3 | 5 | Y |  |  | Wall-mount Time Zone Clock(Time Zone Clock, 2.3 inch (5.8cm) Characters, 6 Digit x 8 Alpha, NTP Driven Display) | Master Clock, Inc. | No |  | NTDS26-8AL |  |  | 2 |  |  |  |  | 1190 |  | -1190 | PR-039934-2712 | PO18-03547 |  |  | 2018-06-11 |  | 2018-06-29 | 2018-06-23 |  |  | Week Two Priority (06/04/18) 06/06/18: Awaiting refresh quote from vendor | Yes | 1190
| 3 | 5 | Y |  |  | Shipping | Master Clock, Inc. | [10 empty] | 29.08 |  | -29.08 | PR-039934-2712 | PO18-03547 |  |  | 2018-06-11 |  | 2018-06-29 | 2018-06-23 |  |  |  | Yes | 29.08
Quote received 03/06/18 | 3 | 5 | Y |  |  | HP Officejet Pro 7740 AIO color | CDWG | Yes |  | 4300266 | CDWG |  | 2 |  | 170.99 | 341.98 |  | 1170 |  | -828.02 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 | 2018-07-13 | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 1170
Quote received 03/06/18 | 3 | 5 | Y |  |  | Quartet Infinity whiteboard | CDWG |  |  | 3450208 | CDWG |  | 1 |  | 402.79 | 402.79 |  | 370.8 |  | 31.99 | PR-040367-2712 | PO18-03956 |  |  | 2018-06-27 |  | 2018-07-06 | 2018-07-23 |  |  | Week Three Priority (06/11/18) | Yes | 370.8
Quote received 03/06/18 | 3 | 5 | Y |  |  | Logitech MK200 USB Wired Keyboard & Mouse Set | CDWG | Yes |  | 2124293 | CDWG |  | 12 |  | 22.79 | 273.48 |  | 2550 |  | -2276.52 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 2550
Quote received 03/06/18 | 3 | 5 | Y |  |  | Bolted Workbench, ESD Laminate, 24" Depth, 30" to 34.75" Height, 60" Width, 1600 lb. Load Capacity | Grainger | No |  | 16Y089 |  |  | 1 |  | 368.5 | 368.5 |  | 368.5 |  | 0 | PR-040122-2712 | PO18-03773 |  |  | 2018-06-19 |  | 2018-07-06 | 2018-07-03 |  |  | Week Three Priority (06/11/18) | Yes | 368.5
| 3 | 5 | Y |  |  | Shipping | Grainger | No |  | Shipping |  |  | 1 |  | 65.97 | 65.97 |  | 63.97 |  | 2 | PR-040122-2712 | PO18-03773 |  |  | 2018-06-19 |  | 2018-07-06 | 2018-07-03 |  |  |  | Yes | 63.97
Quote received 03/06/18 | 3 | 5 | Y |  |  | HON® Metal Bookcase - Two-Shelf - 34-1/2w x 12-5/8d x29h - Putty | HON | No |  |  |  |  | 1 |  | 124 | 124 |  | 127.9 |  | -3.9 | PR-040116-2712 | PO18-03743 |  |  | 2018-06-18 |  | 2018-06-28 | 2018-06-21 |  |  | Week Three Priority (06/11/18) | Yes | 127.9
Quote received 03/06/18 | 3 | 5 | Y |  |  | StarTech.com DisplayPort to VGA Adapter with Audio | CDWG | Yes |  | 3755603 | CDW-G |  | 10 |  | 32.29 | 322.9 |  | 1142 |  | -819.1 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 1142
Quote received 03/06/18 | 3 | 5 | Y |  |  | Tripp Lite Displayport Monitor Cable with Latches Digital A/V 4K M/M 6ft | CDWG | Yes |  | 1561875 | CDW-G |  | 10 |  | 16.14 | 161.4 |  | 138 |  | 23.4 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 138
Quote received 03/06/18 | 3 | 5 | Y |  |  | StarTech.com DisplayPort to DVI Video Adapter Converter | CDWG | Yes |  | 1995678 | CDW-G |  | 10 |  | 18.04 | 180.4 |  | 74 |  | 106.4 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 74
Quote received 03/06/18 | 3 | 5 | Y |  |  | Tripp Lite 6ft DisplayPort to HDMI Adapter Cable Video / Audio Cable DP M/M | CDWG | Yes |  | 1685176 | CDW-G |  | 10 |  | 21.84 | 218.4 |  | 132 |  | 86.4 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 132
Quote received 03/06/18 | 3 | 5 | Y |  |  | StarTech.com 6 ft Mini DisplayPort to DisplayPort 1.2 Cable - 4k - 6ft | CDWG | Yes |  | 1973897 | CDW-G |  | 10 |  | 11.39 | 113.9 |  | 3666 |  | -3552.1 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 3666
Quote received 03/06/18 | 3 | 5 | Y |  |  | Black Box 48 Port Serial over IP Gigabit Console Server, Cisco Compatible | CDWG | Yes |  | 3946414 | CDW-G |  | 3 |  | 2227.74 | 6683.22 |  | 295 |  | 6388.22 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 295
Quote received 03/06/18 | 3 | 5 | Y |  |  | Cisco Four-Point Rack Mounting Kit - rack mounting kit | CDWG | Yes |  | 3035528 | CDW-G |  | 12 |  | 161.49 | 1937.88 |  | 82.5 |  | 1855.38 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-23 |  |  | Week Three Priority (06/11/18) | Yes | 82.5
| 3 | 5 | Y |  |  | Brother TZe2312PK - laminated tape - 2 roll(s) | CDWG | Yes |  | 2313278 |  |  | 3 |  | 23.74 | 71.22 |  | 120 |  | -48.78 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 120
| 3 | 5 | Y |  |  | LG 65UH5C-B UH5C Series - 65" LED display | CDWG | Yes |  | 4570680 |  |  | 2 |  | 2314.2 | 4628.4 |  | 126.5 |  | 4501.9 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-06 |  |  |  | Yes | 126.5
| 3 | 5 | Y |  |  | Tripp Lite Heavy Duty Computer Power Cord 15A 14AWG C14 to C15 Blue 6' 6ft | CDWG | Yes |  | 4354359 |  |  | 12 |  | 18.04 | 216.48 |  | 70 |  | 146.48 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 70
| 3 | 5 | Y |  |  | Tripp Lite Heavy Duty Computer Power Extension Cord 15A 14AWG C14 C15 10' | CDWG | Yes |  | 3325734 |  |  | 4 |  | 30.39 | 121.56 |  | 6477 |  | -6355.44 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 6477
| 3 | 5 | Y |  |  | Tripp Lite Heavy Duty Computer Power Cord 15A 14AWG C14 to C15 Red 6' 6ft | CDWG | Yes |  | 4354209 |  |  | 12 |  | 18.04 | 216.48 |  | 1800 |  | -1583.52 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 1800
| 3 | 5 | Y |  |  | Cisco 1100W Hot Plug/Redundant PowerSupply for Catalyst 3850-48F-E | CDWG | Yes |  | 2980344 |  |  | 1 |  | 1331.89 | 1331.89 |  | 350 |  | 981.89 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 350
| 3 | 5 | Y |  |  | Cisco 4-Port Expansion Module for Catalyst 3850-24 | CDWG | Yes |  | 2950417 |  |  | 10 |  | 293.54 | 2935.4 |  | 180 |  | 2755.4 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 180
| 3 | 5 | Y |  |  | Cisco 350W Hot Plug/ Redundant Power Supply for Catalyst 3850-24T-E | CDWG | Yes |  | 2947705 |  |  | 3 |  | 455.99 | 1367.97 |  | 114 |  | 1253.97 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 114
| 3 | 5 | Y |  |  | Shipping | CDWG | Yes |  |  |  |  | 1 |  | 521.36 | 521.36 |  | 63 |  | 458.36 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  |  | Yes | 63
| 3 | 5 | Y |  |  | PowerEdge R230 Server | Dell | Yes |  | 210-AEXB |  |  | 1 |  | 2651.82 | 2651.82 |  | 2787.71 |  | -135.89 | PR-039684-2712 | PO18-03409 |  |  | 2018-06-01 |  | 2018-06-29 | 2018-06-11 |  |  |  | Yes | 2787.71
| 3 | 5 | Y |  |  | 1 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue, No Label, Booted) | LanShack | No |  | C6PLEN- 01-STD-BLU-B |  |  | 10 |  | 7.26 | 72.6 |  | 61.1 |  | 11.5 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 61.1
| 3 | 5 | Y |  |  | 4 meter LC to SC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DSC-M- 04-10GIG-AQ |  |  | 6 |  | 27.27 | 163.62 |  | 157.62 |  | 6 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 157.62
| 3 | 5 | Y |  |  | 9 meter LC to SC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DSC-M- 09-10GIG-AQ |  |  | 4 |  | 35.66 | 142.64 |  | 138.64 |  | 4 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 138.64
| 3 | 5 | Y |  |  | 20 meter LC to SC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DSC-M- 20-10GIG-AQ |  |  | 2 |  | 54.1 | 108.2 |  | 106.2 |  | 2 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 106.2
| 3 | 5 | Y |  |  | 1 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DLC-M- 01-10GIG-AQ |  |  | 4 |  | 24.81 | 99.24 |  | 95.24 |  | 4 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 95.24
| 3 | 5 | Y |  |  | 4 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DLC-M- 04-10GIG-AQ |  |  | 4 |  | 28.77 | 115.08 |  | 111.08 |  | 4 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 111.08
| 3 | 5 | Y |  |  | 9 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DLC-M- 09-10GIG-AQ |  |  | 4 |  | 37.15 | 148.6 |  | 144.6 |  | 4 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 144.6
| 3 | 5 | Y |  |  | 20 meter LC to LC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DLC-M- 20-10GIG-AQ |  |  | 2 |  | 55.59 | 111.18 |  | 99.18 |  | 12 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 99.18
| 3 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) 10-GIG 50/125 OM3 Multimode "Fiber Whips" Assembly (LC to LC, Pulling Eye Both Ends, 100 Foot (30.48 Meters)) | LanShack | No |  | PRO-769- M10G-DP- 2-L-2P-100 |  |  | 2 |  | 136.73 | 273.46 |  | 253.46 |  | 20 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 253.46
| 3 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) 10-GIG 50/125 OM3 Multimode "Fiber Whips" Assembly (SC to LC (SC lead end), Pulling Eye Both Ends, 100 Foot (30.48 Meters)) | LanShack | No |  | PRO-769- M10G-DP-2-SC-LC- 2P-100 |  |  | 2 |  | 136.73 | 273.46 |  | 253.46 |  | 20 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 253.46
| 3 | 5 | Y |  |  | 9 meter LC to SC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC - LC side , UPC - SC side) | LanShack | No |  | FA-DLC-DSC-S- 09-YL-U/LC-U/SC |  |  | 4 |  | 44.89 | 179.56 |  | 159.56 |  | 20 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 159.56
| 3 | 5 | Y |  |  | 1 meter LC to SC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC - LC side , UPC - SC side) | LanShack | No |  | FA-DLC-DSC-S- 01-YL-U/LC-U/SC |  |  | 4 |  | 36.32 | 145.28 |  | 145.28 |  | 0 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 145.28
| 3 | 5 | Y |  |  | 4 meter LC to SC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC - LC side , UPC - SC side) | LanShack | No |  | FA-DLC-DSC-S- 04-YL-U/LC-U/SC |  |  | 4 |  | 39.54 | 158.16 |  | 158.16 |  | 0 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 158.16
| 3 | 5 | Y |  |  | 20 meter LC to SC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC - LC side , UPC - SC side) | LanShack | No |  | FA-DLC-DSC-S- 20-YL-U/LC-U/SC |  |  | 2 |  | 56.67 | 113.34 |  | 99.34 |  | 14 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 99.34
| 3 | 5 | Y |  |  | 1 meter LC to LC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC ) | LanShack | No |  | FA-DLC-DLC-S- 01-YL-U |  |  | 4 |  | 36.41 | 145.64 |  | 121.64 |  | 24 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 121.64
| 3 | 5 | Y |  |  | 4 meter LC to LC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC ) | LanShack | No |  | FA-DLC-DLC-S- 04-YL-U |  |  | 4 |  | 39.62 | 158.48 |  | 158.48 |  | 0 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 158.48
| 3 | 5 | Y |  |  | 9 meter LC to LC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC ) | LanShack | No |  | FA-DLC-DLC-S- 09-YL-U |  |  | 4 |  | 44.98 | 179.92 |  | 167.92 |  | 12 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 167.92
| 3 | 5 | Y |  |  | 20 meter LC to LC, 9/125, Singlemode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Yellow, UPC ) | LanShack | No |  | FA-DLC-DLC-S- 20-YL-U |  |  | 2 |  | 56.76 | 113.52 |  | 99.52 |  | 14 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 99.52
| 3 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC to SC (LC lead end of reel), Pulling Eye Both Ends, 100 Foot (30.48 Meters)) | LanShack | No |  | PRO-769-S-DP-2- LC-SC-2P-100 |  |  | 2 |  | 115.33 | 230.66 |  | 215.66 |  | 15 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 215.66
| 3 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC to LC, Pulling Eye Both Ends, 100 Foot (30.48 Meters)) | LanShack | No |  | PRO-769-S-DP-2- L-2P-100 |  |  | 2 |  | 115.33 | 230.66 |  | 215.66 |  | 15 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 215.66
| 3 | 5 | Y |  |  | 1 meter LC to SC, 50/125 OM3, 10 GIG Multimode Duplex Patch Cable - Plenum Rated - USA CustomLine by QuickTreX® (Aqua (Std.)) | LanShack | No |  | FA-DLC-DSC-M- 01-10GIG-AQ |  |  | 4 |  | 23.26 | 93.04 |  | 81.04 |  | 12 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 81.04
| 3 | 5 | Y |  |  | SC Duplex Mating Sleeve – Zirconia | LanShack | No |  | 15-08-S1-1 |  |  | 50 |  | 5.98 | 299 |  | 259 |  | 40 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 259
| 3 | 5 | Y |  |  | 50 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , White, No Label, Booted) | LanShack | No |  | C6PLEN- 50-STD-WH-B |  |  | 10 |  | 25.88 | 258.8 |  | 253.6 |  | 5.2 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 253.6
| 3 | 5 | Y |  |  | 3 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , White, No Label, Booted) | LanShack | No |  | C6PLEN- 03-STD-WH-B |  |  | 10 |  | 8.02 | 80.2 |  | 78.6 |  | 1.6 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 78.6
| 3 | 5 | Y |  |  | 50 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue, No Label, Non-Booted) | LanShack | No |  | C6PLEN-50-STDBLU-NB |  |  | 10 |  | 25.88 | 258.8 |  | 253.6 |  | 5.2 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 253.6
| 3 | 5 | Y |  |  | 3 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue, No Label, Booted) | LanShack | No |  | C6PLEN- 03-STD-BLU-B |  |  | 10 |  | 8.02 | 80.2 |  | 78.6 |  | 1.6 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 78.6
| 3 | 5 | Y |  |  | 25 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , White, No Label, Booted) | LanShack | No |  | C6PLEN- 25-STD-WH-B |  |  | 10 |  | 16.38 | 163.8 |  | 160.5 |  | 3.3 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 160.5
| 3 | 5 | Y |  |  | 10 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue,No Label, Booted) | LanShack | No |  | C6PLEN- 10-STD-BLU-B |  |  | 10 |  | 10.68 | 106.8 |  | 104.6 |  | 2.2 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 104.6
| 3 | 5 | Y |  |  | 25 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue,No Label, Booted) | LanShack | No |  | C6PLEN-25-STD-BLU-B |  |  | 10 |  | 16.38 | 163.8 |  | 160.5 |  | 3.3 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 160.5
| 3 | 5 | Y |  |  | 10 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru ,White, No Label, Booted) | LanShack | No |  | C6PLEN- 10-STD-WH-B |  |  | 10 |  | 10.68 | 106.8 |  | 104.6 |  | 2.2 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 104.6
| 3 | 5 | Y |  |  | 15 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru ,White, No Label, Booted) | LanShack | No |  | C6PLEN-15-STD-WH-B |  |  | 10 |  | 12.58 | 125.8 |  | 123.2 |  | 2.6 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 123.2
| 3 | 5 | Y |  |  | 1 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , White,No Label, Booted) | LanShack | No |  | C6PLEN-01-STD-WH-B |  |  | 10 |  | 7.26 | 72.6 |  | 71.1 |  | 1.5 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 71.1
| 3 | 5 | Y |  |  | 15 Ft Cat 6E Plenum Custom Patch Cable (568B Straight Thru , Blue,No Label, Booted) | LanShack | No |  | C6PLEN-15-STD-BLU-B |  |  | 10 |  | 12.58 | 125.8 |  | 123.2 |  | 2.6 | PR-040507-2712 | PO18-04526 |  |  | 2018-08-02 |  | 2018-08-17 | 2018-08-14 |  |  |  | Yes | 123.2
| 3 | 4 | Y |  |  | Vmware | Vmware | [5 empty] | 2 |  | 249.99 | 499.98 |  | 374 |  | 125.98 | PR184093 | PO18-05032 |  |  | 2018-09-04 |  | 2018-09-07 | 2018-10-25 |  |  |  | Yes | 374
| 3 | 4 | Y |  |  | Windows 10 Pro | Microsoft | [5 empty] | 2 |  | 199.99 | 399.98 |  | 446 |  | -46.02 | PR184091 | PO18-05032 |  |  | 2018-09-04 |  | 2018-09-07 | 2018-10-25 |  |  |  | Yes | 446
| 3 | 5 | Y |  |  | Brother P-Touch PT-D210 - labelmaker -monochrome - thermal transfer | CDWG | Yes |  | 3839168 |  |  | 3 |  | 42.74 | 128.22 |  | 192 |  | -63.78 | PR-040124-2712 | PO18-03889 |  |  | 2018-06-26 |  | 2018-07-13 | 2018-07-13 |  |  | Week Three Priority (06/11/18) | Yes | 192
| 9 | 3.0 | Y |  |  | 19x4 Crossbar Terminated RF Switch | DowKey |  |  | 5425 |  |  | 1 |  | 49304 | 49304
| 9 | 3 | Y |  |  | Splitter, L-Band | MECA Electronics, Inc. |  |  | 802-2-3.250WWP |  |  | 1 |  | 217.75 | 217.75
Quote Number: 018035 | 8 | 3 | Y |  |  | Splitter, S-Band | MECA Electronics, Inc. |  |  | 802-2-3.000 |  |  | 6 |  | 98.75 | 592.5
| 9 | 3 | Y |  |  | Splitter, IF | MECA Electronics, Inc. |  |  | 802-2-0.252 |  |  | 1 |  | 147.5 | 147.5
Quote # 135798 | 8 | 3 | Y |  |  | S1 Antenna, S-Band Spectrum Analyzer | Tevet | [5 empty] | 2 |  | 14443.02 | 28886.04 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
Internet Quote | 8 | 3 | Y |  |  | Circuit Breaker | Westinghouse |  |  | EB3045-R |  |  | 2 |  | 124 | 248 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
Quote # Y18-1005DB | 8 | 3 | Y |  |  | New Cutler Hammer QBHW3045H molded case circuit breaker | MIDWEST Switchgear Group |  |  | QBHW3045H |  |  | 1 |  | 185 | 185 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
Quote: LNMQ9707-03 | 8 | 3 | Y |  |  | S-Band Range Zero Set (RZS) | Narda-Miteq |  |  | DNS-2.07/2.25-1K |  |  | 1 |  | 21075 | 21075 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
| 8 | 3 | Y |  |  | ACU OS Upgrade | Viasat |  |  | Windows 7 |  |  | 1 |  | 16500 | 16500 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
| 8 | 3 | Y | S1 Antenna, S-Band ACU OS Upgrade Site Install Support & Testing |  | S1 Antenna, S-Band ACU OS Upgrade Site Install Support & Testing | Viasat | [5 empty] | 1 |  | 11990 | 11990
QUOTE 16426 | 8 | 3 | Y |  |  | S-Band Diplexer | MCS |  |  | 2742-0000 |  |  | 1 |  | 38750 | 38750 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
| 9 | 3 | Y |  |  | S1 Antenna, S-Band LNA | [6 empty] | 1 |  | 15086 | 15086
Quote # O6UJ9A0014Q0 | 8 | 3 | Y |  |  | TDRS/STPSat Mission Select Switch | Dowkey | [5 empty] | 1 |  | 8535 | 8535 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
Waiting on the decision with Diplexer first. | 8 | 3 | Y |  |  | S1 RF Monitoring Switch Cables | Dowkey | [5 empty] | 1 |  | 10000 | 10000 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
| 9 | 3 | Y |  |  | Select Switch, L/S-Band, 16 in, 8 out | [6 empty] | 1 |  | 10000 | 10000
Waiting on the decision with Diplexer first. | 8 | 3 | Y |  |  | S1 Antenna, S-Band Waveguide Seals/Gaskets | [6 empty] | 35 |  | 65.45 | 2290.75 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
| 9 | 3 | Y |  |  | STGT, Hi Rate Modem Interface IF Splitter, 1 to 2 | [6 empty] | 10 |  | 500 | 5000
| 9 | 3 | Y |  |  | STGT, Ka-Band Antenna Interface Splitter, L-Band, 1 to 2 | [6 empty] | 10 |  | 500 | 5000
| 9 | 3 | Y |  |  | STGT, Lo Rate Modem Interface S-Band Splitter, 1 to 2 | [6 empty] | 10 |  | 500 | 5000
| 9 | 3 | Y |  |  | STGT, S-Band Antenna Interface Splitter, S-Band, 1 to 2 | [6 empty] | 20 |  | 500 | 10000
DO NOT ORDER | 5 | 3 | Y |  |  | Environmental Distribution Center | Anixter |  |  | EDC-12P-NH |  |  | 1 |  | 599.97 | 599.97 | [15 empty] | N/A
| 5 | 3 | Y |  |  | Splice Trays | Anixter |  |  | M67-048 |  |  | 6 |  | 36.49 | 218.94 |  |  |  |  | PR1910841 | PO18-07773 |  |  | 2019-01-17 |  | 2019-01-17 |  |  |  |  | Yes | 194.1
| 5 | 3 | Y |  |  | Shipping | [6 empty] | 1 |  | 35.14 | 35.14 |  |  |  |  | PR1910841 | PO18-07773 |  |  | 2019-01-17 |  | 2019-01-17 |  |  |  |  | Yes | 23.14
| Not In the Plan | 3 | Newly added 01/07/19 |  |  | GDS-OFFICE-SUPPLIES | [6 empty] | 1 |  | 152.28 |  |  | 152.28 |  | -152.28 | PR188574 | PO18-06779 |  |  | 2018-11-19 |  | 2018-12-17 | 2018-12-27 |  |  |  | Yes | 152.28
| 5 | 3 | Y |  |  | Closet Connector Housing (CCH) Adapter Panels - LC/APC Connectors (6 LC Duplex) | Fiber Optic Supply |  |  | CCH10002 |  |  | 7 |  | 40 | 280 |  | 280 |  | 0 | PR1910843 | PO-0000007 |  |  | 2019-01-28 |  | 2019-02-08 | 2019-02-08 |  |  |  | Yes | 280
| 5 | 3 | Y |  |  | Shipping | [6 empty] | 1 |  | 25.01 | 25.01 |  | 0 |  | 25.01 | PR1910843 | PO-0000007 |  |  | 2019-01-28 |  | 2019-02-08 | 2019-02-08 |  |  |  | Yes | 0
| Not In the Plan | 3 | Newly added 01/15/19 |  |  | PE2CP1102 | Pasternack | [5 empty] | 13 |  | 153.33 |  |  | 2026.57 |  | -2026.57 | PR1910825 | PO-0000015 |  |  | 2019-01-28 |  | 2019-04-01 |  |  |  |  | No | [6 empty] | 2026.57
| Not In the Plan | 3 | Newly added 01/15/19 |  |  | RFDC5M2G10 | RFLamda | [5 empty] | 4 |  | 198 |  |  | 812 |  | -812 | PR1910834 | PO-0000026 |  |  | 2019-01-28 |  | 2019-02-06 | 2019-02-06 |  |  |  | No | [6 empty] | 812
| 5 | 3 | Y |  |  | LC/APC splice on pig tails | FIS |  |  | SP12LCAPCGR |  |  | 6 |  | 47.16 | 282.96 |  | 282.96 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 282.96
| 5 | 3 | Y |  |  | LC/APC Cheetah Splice on Connectors | FIS |  |  | F1LCAPCSOC10 |  |  | 8 |  | 63.6 | 508.8 |  | 508.8 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 508.8
| 5 | 3 | Y |  |  | FIS 2RU Rack Mount Fiber enclosure | FIS |  |  | F1RM2RU6XL |  |  | 1 |  | 137.95 | 137.95 |  | 137.95 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 137.95
| 5 | 3 | Y |  |  | LC Quad 3-pack APC Single Mode loaded | FIS |  |  | F1LC3QBLKAPCUL |  |  | 7 |  | 14.07 | 98.49 |  | 98.49 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 98.49
| 5 | 3 | Y |  |  | Fusion Splice Sleves 40mm length | FIS |  |  | F1S2540C50 |  |  | 2 |  | 10 | 20 |  | 20 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 20
| 5 | 3 | Y |  |  | FC/APC to LC/APC patch cables 1m | FIS |  |  | Y9YALAS1FISCU |  |  | 26 |  | 8.76 | 227.76 |  | 227.76 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 227.76
| 5 | 3 | Y |  |  | Shipping | [6 empty] | 1 |  | 36 | 36 |  | 36 |  | 0 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25 | 2019-01-25 |  |  |  | No | [6 empty] | 36
| 5 | 3 | Y |  |  | EzEntry 4mini/4 | Excel Automation LLC |  |  | EZEntry4mini/4 |  |  | 2 |  | 33.91 | 67.82 |  | 67.82 |  | 0 | PR1910844 | PO-0000118 |  |  | 2019-01-31 |  | 2019-01-31 | 2019-01-31 |  |  |  | Yes | 67.82
| 5 | 3 | Y |  |  | Roxtec Lube | Excel Automation LLC |  |  | 64457 |  |  | 2 |  | 2.63 | 5.26 |  | 5.26 |  | 0 | PR1910844 | PO-0000118 |  |  | 2019-01-31 |  | 2019-01-31 | 2019-01-31 |  |  |  | Yes | 5.26
| 5 | 3 | Y |  |  | Shipping | Excel Automation LLC | [5 empty] | 1 |  | 21 | 21 |  | 10 |  | 11 | PR1910844 | PO-0000118 |  |  | 2019-01-31 |  | 2019-01-31 | 2019-01-31 |  |  |  | Yes | 10
| 5 | 3 | Y |  |  | LC/UPC to LC/APC (270') (2 stranded) (MOVE from CDCN to ViaSat Rack) | LANshack |  |  | QT-MA-I-S-2-LCU-LCA-2P-270 |  |  | 1 |  | 504.14 | 504.14 |  | 504.14 |  | 0 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30 | 2019-01-30 |  |  |  | Yes
| 5 | 3 | Y |  |  | LC/APC to ST/UPC outdoor rated(~230')(MOVE system to Hub)(pair) | LANshack |  |  | QT-MA-IO-S-2-STU-LCA-2P-230 |  |  | 1 |  | 593.9 | 593.9 |  | 593.9 |  | 0 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30 | 2019-01-30 |  |  |  | Yes
| 5 | 3 | Y |  |  | LC/APC to LC/UPC outdoor rated (~230' feet long) (Timing to Hub)(two pairs) | LANshack |  |  | QT-MA-IO-S-2-LCU-LCA-1P-230 |  |  | 2 |  | 579.4 | 1158.8 |  | 1158.8 |  | 0 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30 | 2019-01-30 |  |  |  | Yes
| 5 | 3 | Y |  |  | Shipping | [6 empty] | 1 |  | 70.52 | 70.52 |  | 660.84 |  | -590.32 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30 | 2019-01-30 |  |  |  | Yes
| 5 | 3 | Y |  |  | 2 meter FC to LC Singlemode Duplex Patch Cables | LANshack |  |  | FA-DFC-DLC-S-02-FCA-LCA-YW |  |  | 12 |  | 61.91 | 742.92 |  | 70.52 |  | 672.4 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30 | 2019-01-30 |  |  |  | Yes
| Not In the Plan | 3 | Newly added 01/24/19 |  |  | Connectors | Online Components | [10 empty] | 124.92 |  | -124.92 | PR1911175 | PO-0000310 |  |  | 2019-02-08 |  | 2019-02-15 |  |  |  |  | No | [5 empty] | 124.92
| Not In the Plan | 3 | Newly added 01/24/19 |  |  | Connectors | Online Components | [10 empty] | 972.72 |  | -972.72 | PR1911175 | PO-0000310 |  |  | 2019-02-08 |  | 2019-02-15 |  |  |  |  | No | [5 empty] | 972.72
Requested a refresh quote 01-15-19 | 5 | 3 | Y |  |  | SM, 120 ft, 12x Fiber, MTP-F to 12 x LC/APC, Indoor / Outdoor, Riser, w/ 12 in X 2mm Fanout, Pull Eye (both ends), on Reel | Microwave Photonic Systems |  |  | 1600-37-12-4-IOR-MTF-1-R-5A-.3-K |  |  | 2 |  | 1250 | 2500 |  | 2500 |  | 0 | PR1911171 | PO-0000062 |  |  | 2019-01-29 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 2500
Requested a refresh quote 01-15-19 | 5 | 3 | Y |  |  | Shipping | Microwave Photonic Systems | [5 empty] | 1 |  | 250 | 250 |  | 250 |  | 0 | PR1911171 | PO-0000062 |  |  | 2019-01-29 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 250
Linda will get refresh quote | 8 | 3 | Y |  |  | Duplex | [6 empty] | 26 |  | 1000 | 26000
Linda will get refresh quote | 8 | 3 | Y |  |  | Patch Cable | [6 empty] | 50 |  | 1000 | 50000
Linda will get refresh quote | 8 | 3 | Y |  |  | - | [6 empty] | 1 |  | 2000 | 2000
Waiting on the decision with Diplexer first. | 8 | 3 | Y |  |  | CustomLine | [6 empty] | 1 |  | 10000 | 10000 | [14 empty] | 06/18/18: Check with Zwick on this if we will purchase now or later since this is S1 and S1 was deferred at one point in time.
This is a duplicate line item. We will keep for the purposes of budget. We only need one spare not quantity four | 9 | 3 | Y |  |  | (FC APC, | [6 empty] | 4 |  | 14293.8 | 57175.2
| 9 | 3 | Y |  |  | LC APC, | MCS |  |  | 2742-0000 |  |  | 2 |  | 27000 | 54000
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | Yellow | GD |  |  | LSC2S45 |  |  | 1 |  | 0 | 0
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | (Standard)) | GD |  |  | LRS1CxxXXXxxxx |  |  | 1 |  | 0 | 0
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | LNA S-Band 1:1 System Option C: Input Coax Coupler, -30dB | GD |  |  | LRS1CxxXXXxxxx |  |  | 1 |  | 0 | 0
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | LNA S-Band 1:1 System Option D: Output Coax Coupler, -20dB | GD |  |  | LRS1xxxxxxxDxx |  |  | 1 |  | 0 | 0
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | LNA S-Band 1:1 System Option E: Offline I/O Port, terminated, with isolator | GD |  |  | LRS1xxxxxxxxEx |  |  | 1 |  | 0 | 0
Quote No: SMV-0818-32979 - 0 | 8 | 3 | Y |  |  | 200 feet of cable (for LNAs) | GD |  |  | ACAB-10899A200 |  |  | 1 |  | 15152.11 | 15152.11
| 5 | 4 | Y |  |  | Clients (Optiplex 5050 SFF) | Dell |  |  | s012o5050sffusr |  |  | 21 |  | 1098.57 | 23069.97 |  | 15574.44 |  | 7495.53 | PR1911715 | PO-0001063 |  |  | 2019-03-20 |  | 2019-04-19 |  |  |  | 08/16/18: For Omitron | No | [7 empty] | 15574.44
| 5 | 4 | Y |  |  | Dell 24 Monitor - P2417H | Dell |  |  | p2417hsap |  |  | 20 |  | 279.99 | 5599.8 |  | 4208.8 |  | 1391 | PR1911715 | PO-0001063 |  |  | 2019-03-20 |  | 2019-04-19 |  |  |  | 08/16/18: For Omitron | No | [7 empty] | 4208.8
| 5 | 4 | Y |  |  | Shipping | [6 empty] | 1 |  | 460 | 460 |  | 0 |  | 460 | PR1911715 | PO-0001063 |  |  | 2019-03-20 |  | 2019-04-19 |  |  |  |  | No | [7 empty] | 0
| Not In the Plan | 4 | Newly added 04/03/19 |  |  | Windows 10 Pro Download | Microsoft | [5 empty] | 1 |  |  |  |  | 109.99 |  |  | PR1912799 | PO-0000867 |  |  | 2019-03-07 |  | 2019-03-07 |  |  |  |  | Yes
| Not In the Plan | 4 | Newly added 02/27/19 |  |  | LTO5-140 Tape label 1-200 Customer Kit | Dell | [5 empty] | 1 |  | 112.49 |  |  | 98.84 |  | -98.84 | PR1912798 | PO-0000866 |  |  | 2019-03-07 |  | 2019-03-15 |  |  |  |  | No | [6 empty] | 98.84
| Not In the Plan | 4 | Newly added 02/07/19 |  |  | PV-WAVE Foundation Standard Platform Deployment Standard Maintenance and Support LIC-201404016857 | PV-WAVE | [5 empty] | 1 |  | 252 |  |  | 252 |  | -252 | PR1911824 | PO-0000366 |  |  | 2019-02-12 |  | 2019-02-12 | 2019-02-12 |  |  |  | No | [5 empty] | 252
| Not In the Plan | 4 | Newly added 02/07/19 |  |  | PV-WAVE Foundation Standard Platform Deployment Standard Maintenance and Support LIC-201404191240 | PV-WAVE | [5 empty] | 2 |  | 252 |  |  | 504 |  | -504 | PR1911824 | PO-0000366 |  |  | 2019-02-12 |  | 2019-02-12 | 2019-02-12 |  |  |  | No | [5 empty] | 504
Order complete | Not In the Plan | 4 | Newly added 11/15/18 |  |  | VMware | VMware | [5 empty] | 1 |  | 7472 |  |  | 6919.06 |  | -6919.06 | PR188409 | PO18-06890 |  |  | 2018-11-27 |  | 2018-12-07 | 2018-12-28 |  |  |  | Yes | 6919.06
| Not In the Plan | 4 | Newly added 04/03/19 |  |  | P/N: 560003M GSA FreeFlyer Mission Node-Locked Maintenance P/N: MRDN03M Meridian Software Maintenance | A.I. Solutions | [5 empty] | 2 |  |  |  |  | 25540 |  |  | PR1912925 | PO-0001274 |  |  | 2019-03-28 |  | 2019-03-30 | 2019-03-31 |  |  |  | No | [6 empty] | 25540
Order complete | Not In the Plan | 4 | Newly added 11/15/18 |  |  | Windows 10 Pro | Microsoft | [5 empty] | 2 |  | 199.99 |  |  | 274.56 |  | -274.56 | PR188442 | PO18-06756 |  |  | 2018-11-19 |  | 2018-11-27 | 2019-01-03 |  |  |  | Yes | 274.56
Order complete | Not In the Plan | 4 | Newly added 12/13/18 |  |  | Renewal Red Hat Enterprise Linux | Carasoft | [5 empty] | 6 |  | 571.92 |  |  | 3431.52 |  | -3431.52 | PR188725 | PO18-06947 | 2018-12-04 |  | 2018-12-04 |  | 2018-12-04 | 2019-01-11 |  |  |  | Yes | 3431.52
| Not In the Plan | 4 | Newly added 12/19/18 |  |  | 6Gb Mini-SAS HD to Mini-SAS cable, 2M, Customer Kit | Dell | [5 empty] | 2 |  | 177.15 |  |  | 283.44 |  | -283.44 | PR1910268 | PO18-07610 |  |  | 2019-01-10 |  | 2019-01-16 | 2019-01-16 |  |  |  | No | [5 empty] | 283.44
| Not In the Plan | 4 | Newly added 12/19/18 |  |  | VERITAS Backup Exec Server Edition - On-Premise competitive upgrade license + 1 Year Essential Support - 1 server - corporate - CLP - Win | LINKSOURCEIT | [5 empty] | 1 |  | 574.99 |  |  | 574.99 |  | -574.99 | PR1910270 | PO-0000054 |  |  | 2019-01-29 |  | 2019-01-29 | 2019-01-29 |  |  |  | Yes | 574.99
| 5 | 4 | Y |  |  | Fileservers (Snapserver) | Dell | [5 empty] | 3 |  | 3727 | 11181 |  | 10755 |  | 426 | PR1911720 | PO-0000572 |  |  | 2019-02-21 |  | 2019-02-13 | 2019-03-20 |  |  | 08/16/18: For Omitron | No | [6 empty] | 10755
| 5 | 4 | Y |  |  | Shipping | [6 empty] | 1 |  | 1606.64 | 1606.64 |  | 0 |  | 1606.64 | PR1911720 | PO-0000572 |  |  | 2019-02-21 |  | 2019-02-13 | 2019-03-20 |  |  |  | No | [6 empty] | 0
| 5 | 4 | Y |  |  | Micro AIO Stand MFS18 CUS KIT | Dell | [5 empty] | 1 |  | 99.99 | 99.99 |  |  |  |  | PR1911722 | PO-0000786 |  |  | 2019-03-05 |  | 2019-03-22 |  |  |  | 02/06/18: For Pete Gaffney | No | [5 empty] | 99.99
| 5 | 4 | Y |  |  | OptiPlex 7050 Micro (Clients) | Dell | [5 empty] | 1 |  | 1270 | 1270 |  |  |  |  | PR1911722 | PO-0000786 |  |  | 2019-03-05 |  | 2019-03-22 |  |  |  | 02/06/18: For Pete Gaffney | No | [5 empty] | 1270
Order complete | 5 | 4 | Y |  |  | ETHERNET BRACE, CHASSIS, POWER AMP (REV C), ADAPTER, STRAIGHT SMA FEMALE/F | Dell | [5 empty] | 1 |  | 823.68 | 823.68 |  | 647.43 |  | 176.25 | PR186910 | PO18-06062 |  |  | 2018-10-18 |  | 2018-10-31 | 2018-10-29 |  |  |  | Yes | 647.43
| Not In the Plan | 4 | Newly added 12/27/18 |  |  | P/N: RH00004RN Renewal Red Hat Enterprise Linux Server | RedHat | [5 empty] | 4 |  |  |  |  | 2459.88 |  | -2459.88 | PR189486 | PO18-07301 |  |  | 2018-12-18 |  | 2018-12-31 | 2019-01-28 |  |  |  | Yes | 2459.88
| 5 | 4 | Y |  |  | Dell 24 Monitor - E2417H | Dell |  |  | E2417H |  |  | 1 |  | 169.99 | 169.99 |  |  |  |  | PR1911722 | Status: Buyer Assigned | [8 empty] | 01/30/18: Already purchased on line 30: Duplicates | [6 empty] | 169.99
| 5 | 4 | Y |  |  | PowerEdge R440 Rack Server | Dell | [5 empty] | 2 |  | 6422 | 12844 |  | 8889.06 |  | 3954.94 | PR1910560 | PO18-07823 |  |  | 2019-01-21 |  | 2019-02-06 | 2019-02-06 | No |  |  | No | [5 empty] | 8889.06
| 5 | 4 | Y |  |  | Shipping | [6 empty] | 1 |  | 23.99 | 23.99 |  | 0 |  | 23.99 | PR1910560 | PO18-07823 |  |  | 2019-01-21 |  | 2019-02-06 | 2019-02-06 |  |  | 01/30/18: Already purchased on line 31: Duplicates | No | [5 empty] | 0
| 8 | 4 | Y |  |  | Dell ProSupport Ent. Svc. | Dell | [5 empty] | 1 |  | 55000 | 55000 | [14 empty] | 06/18/18: For OMITRON
| 8 | 4 | Y |  |  | Spare RAM (VM host) | Dell | [5 empty] | 1 |  | 278.11 | 278.11
| 8 | 4 | Y |  |  | Spare SD module (VM host) | Dell | [5 empty] | 1 |  | 70.35 | 70.35
| 8 | 4 | Y |  |  | Spare fan (VM host) | Dell | [5 empty] | 1 |  | 29 | 29
| 8 | 4 | Y |  |  | Spare drives (VM host) | Dell | [5 empty] | 1 |  | 184 | 184
| 8 | 4 | Y |  |  | Spare SD card (VM host) | Dell | [5 empty] | 2 |  | 39 | 78
| 8 | 4 | Y |  |  | Spare drives (SAN) | Dell | [5 empty] | 4 |  | 250 | 1000
| 8 | 4 | Y |  |  | Monitors (34") | Dell | [5 empty] | 1 |  | 749.99 | 749.99
| 8 | 4 | Y |  |  | Spare RAM (SCWA) | Dell | [5 empty] | 1 |  | 150 | 150
| 8 | 4 | Y |  |  | Spare fan (SCWA) | Dell | [5 empty] | 1 |  | 29 | 29
| 8 | 4 | Y |  |  | Spare drives (SCWA) | Dell | [5 empty] | 4 |  | 69 | 276
| 8 | 4 | Y |  |  | Switches (SSOC) | Cisco | [5 empty] | 1 |  | 5200 | 5200
| 8 | 4 | Y |  |  | Monitors (24") | [6 empty] | 1 |  | 230 | 230
| 8 | 4 | Y |  |  | Dell 730 Server | [6 empty] | 1 |  | 7500 | 7500
| 8 | 4 | Y |  |  | Dell R440 Server | [6 empty] | 1 |  | 4500 | 4500
| 8 | 4 | Y |  |  | Spare drives (fileservers) | Overland | [5 empty] | 1 |  | 246 | 246
Quote# KCMV910 | 5 | 5 | Y |  |  | Computer Monitor | CDWG | Yes |  | U2417H |  |  | 10 |  | 275.37 | 2753.7 |  | 2500 |  | 253.7 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 2500
Quote# KCMV910 | 5 | 5 | Y |  |  | Keyboard | CDWG | Yes |  | JK-A0100EU-2 |  |  | 20 |  | 30.56 | 611.2 |  | 520 |  | 91.2 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 520
Quote# KCMV910 | 5 | 5 | Y |  |  | Mouse | CDWG |  |  | JM-0600-2 |  |  | 20 |  | 12.21 | 244.2 |  | 244.2 |  | 0 | PR187622 | PO18-06601 |  |  | 2018-11-09 |  | 2019-04-04 |  |  |  |  | Yes | 244.2
Quote# KCMV910 | 5 | 5 | Y |  |  | 48" x 96" White Board | CDWG | Yes |  |  |  |  | 2 |  | 370.8 | 741.6 |  | 771.26 |  | -29.66 | PR187622 | PO18-06601 |  |  | 2018-11-09 |  | 2018-11-21 |  |  |  |  | Yes | 741.6
| 8 | 5 | Y |  |  | Cisco 1100W Hot Plug/Redundant Power Supply for Cisco 3850-12X48U | Cisco | Yes |  | PWR-C1-1100WAC= |  |  | 2 |  | 1398.49 | 2796.98
Quote# KCMV910 | 5 | 5 | Y |  |  | Cisco Catalyst 2960X-24TS-L - switch - 24 ports - managed - rack-mountable | CDWG | Yes |  | WS-C2960X-24TS-L |  |  | 2 |  | 1192.5 | 2385 |  | 2310 |  | 75 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 2310
| 8 | 5 | Y |  |  | Firewall - Cisco ASA 5525-X Firewall Edition Security Applicance | Cisco | Yes |  | ASA5525-K9 |  |  | 2 |  | 5989.98 | 11979.96
| 8 | 5 | Y |  |  | Firewall - Cisco ASA 5525-X Interface Card Expansion Module | Cisco | Yes |  | ASA-IC-6GE-SFP-B= |  |  | 2 |  | 5006.44 | 10012.88
Do not order | 5 | 5 | Y |  |  | Black Box 48 Port Serial over IP Gigabit Console Server, Cisco | CDWG | Yes |  | LES1548A |  |  | 2 |  | 2173.51 | 4347.02
Quote# KCMV910 | 5 | 5 | Y |  |  | Seagate Expansion 2 TB External HDD | CDWG | Yes |  | STEA2000400 |  |  | 60 |  | 65.25 | 3915 |  | 3930 |  | -15 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 3930
Do not order | 5 | 5 | Y |  |  | Ethernet Protector | ShoreMicro |  |  | SM-2501CA |  |  | 3 |  | 522.5 | 1567.5
Do not order | 5 | 5 | Y |  |  | Shipping | [6 empty] | 1 |  | 97 | 97
Quote# KCMV910 | 5 | 5 | Y |  |  | LG 65UH5C-B UH5C Series - 65" LED display - Cisco Certified | CDWG |  |  | 65UH5C-B |  |  | 2 |  | 1868.74 | 3737.48 |  | 5355 |  | -1617.52 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 5355
Quote# KCMV910 | 5 | 5 | Y |  |  | Kramer VS-161H 16x1 HDMI Matrix Switcher - video/audio switch - rack-mounta | CDWG |  |  | VS-161H |  |  | 1 |  | 686.01 | 686.01 |  | 610 |  | 76.01 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 610
Quote# KCMV910 | 5 | 5 | Y |  |  | HON Volt 5700 Series H5701 - chair | CDWG |  |  | 5701GA10T |  |  | 10 |  | 109.01 | 1090.1 |  | 1090.1 |  | 0 | PR187622 | PO18-06601 |  |  | 2018-11-14 |  | 2018-11-21 |  |  |  |  | Yes | 1090.1
Quote# KCMV910 | 5 | 5 | Y |  |  | Polycom VoiceStation 300 Conference Room | CDWG |  |  | 2200-17910-001 |  |  | 1 |  | 231.84 | 231.84 |  | 462 |  | -230.16 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 462
| Not In the Plan | 5 | Newly added 03/28/19 |  |  | Windows Server 2016 Standard & Microsoft SQL Server 2017 Standard | PCMG, Inc. | [5 empty] | 1 |  |  |  |  | 6788 |  |  | PR199877 | PO18-07367 |  |  | 2018-12-31 |  | 2019-01-11 | 2019-01-11 |  |  |  | No | 6788 | [5 empty] | 6788
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Lavex Janitorial 7 Gallon Beige Wastebasket | WebstaurantStore |  |  | 475WC28BG |  |  | 6 |  | 4.39 | 26.34 |  | 300.15 |  | -273.81 | PR1912025 | PO-0000476 |  |  | 2019-02-18 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 300.15
Quote# KCMV910 | 5 | 5 | Y |  |  | HP Officejet Pro 7740 AIO color | CDWG | [5 empty] | 2 |  | 237.49 | 474.98 |  | 398 |  | 76.98 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 398
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Rubbermaid Slim Jim Red 8 Gallon | WebstaurantStore |  |  | 6901883564RD |  |  | 3 |  | 92 | 276 |  | 55.2 |  | 220.8 | ID 12025 | PO-0000476 |  |  | 2019-02-18 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 55.2
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | WebstaurantStore | [5 empty] | 1 |  | 49.1 | 49.1 |  | 0 |  | 49.1 | ID 12025 | PO-0000476 |  |  | 2019-02-18 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 0
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC - UPC, LC - UPC, Pulling Eye One End, 150 Foot (45.72 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-S-DP-2-LCU-LCU-1P-150 |  |  | 5 |  | 120.33 | 601.65 |  | 541.48 |  | 60.17 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 541.48
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC - UPC, LC - APC, Pulling Eye Both Ends, 30 Foot (9.14 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-S-DP-2-LCU-LCA-2P-30 |  |  | 3 |  | 96.93 | 290.79 |  | 141.49 |  | 149.3 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 141.49
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) 10-GIG 50/125 OM3 Multimode "Fiber Whips" Assembly (LC to LC, Pulling Eye Both Ends, 70 Foot (21.34 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-M10G-DP- 2-LC-2P-70 |  |  | 2 |  | 115.73 | 231.46 |  | 231.46 |  | 0 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 231.46
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC - UPC, LC - APC, Pulling Eye Both Ends, 270 Foot (82.30 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-S-DP-2-LCU-LCA-2P-270 |  |  | 1 |  | 180.93 | 180.93 |  | 162.84 |  | 18.09 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 162.84
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) Singlemode "Fiber Whips" Assembly (LC - UPC, LC - APC, Pulling Eye Both Ends, 140 Foot (42.67 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-S-DP-2-LCU-LCA-2P-140 |  |  | 1 |  | 135.43 | 135.43 |  | 121.89 |  | 13.54 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 121.89
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) 10-GIG 50/125 OM3 Multimode "Fiber Whips" Assembly (LC to LC, Pulling Eye Both Ends, 280 Foot (85.34 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-M10G-DP-2-LC-2P-280 |  |  | 1 |  | 262.73 | 262.73 |  | 262.73 |  | 0 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 262.73
Lanshack Quote #126957 | 5 | 5 | Y |  |  | 2 Strand CustomLine Indoor (Plenum) 10-GIG 50/125 OM3 Multimode "Fiber Whips" Assembly (LC to LC, Pulling Eye Both Ends, 200 Foot (60.96 Meters)) Terms: Non-cancelable, non-returnable. | LANshack |  |  | PRO-769-M10G-DP-2-LC-2P-200 |  |  | 1 |  | 206.73 | 206.73 |  | 261.71 |  | -54.98 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 261.71
Lanshack Quote #126957 | 5 | 5 | Y |  |  | QuickTreX® 24 Port Keystone Blank Patch Panel (1 RU) (24 Couplers, Add plastic Mounting Brackets (1 Pair)) | LANshack |  |  | QT-48-205-X2U-24C+Bracket |  |  | 1 |  | 107.04 | 107.04 |  | 107.04 |  | 0 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 107.04
Lanshack Quote #126957 | 5 | 5 | Y |  |  | Shipping | LANshack | [5 empty] | 1 |  | 141.49 | 141.49 |  | 206.73 |  | -65.24 | PR187640 | PO18-06354 |  |  | 2018-11-01 |  | 2018-11-09 |  |  |  |  | No | [6 empty] | 206.73
Quote# KCMV910 | 5 | 5 | Y |  |  | StarTech.com 6 ft HDMI to DVI-D Cable - M/M | CDWG |  |  | HDMIDVIMM6 |  |  | 10 |  | 7.42 | 74.2 |  | 80 |  | -5.8 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 80
Quote# KCMV910 | 5 | 5 | Y |  |  | C2G 2m HDMI to DVI Adapter Cable  Digital DVI-D (6ft) | CDWG |  |  | 3049291 |  |  | 10 |  | 7.46 | 74.6 |  | 50 |  | 24.6 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 50
Quote# KCMV910 | 5 | 5 | Y |  |  | StarTech.com 50 ft DisplayPort Cable with Latches - M/M | CDWG |  |  | DISPLPORT50L |  |  | 2 |  | 68.69 | 137.38 |  | 128 |  | 9.38 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 128
Quote# KCMV910 | 5 | 5 | Y |  |  | Tripp Lite 50' High Speed HDMI Cable Digital Audio Video Gold | CDWG | Yes |  | P568-050 |  |  | 17 |  | 34.96 | 594.32 |  | 510 |  |  | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 510
| 8 | 5 | Y |  |  | M/M 50ft | Cisco |  |  | CWDM-SFP10G-1470 |  |  | 2 |  | 1295 | 2590
| 8 | 5 | Y |  |  | Cisco Compatible SFP Module - CWDM 1490nm - 10Gbps | Cisco |  |  | CWDM-SFP10G-1490 |  |  | 2 |  | 1295 | 2590
| 8 | 5 | Y |  |  | Cisco Compatible SFP Module - Long Haul (SM) - 1Gbps | Cisco |  |  | GLC-LH-SM |  |  | 4 |  | 69 | 276
| 8 | 5 | Y |  |  | Cisco Compatible SFP Module - Short Haul (MM) - 1Gbps | Cisco |  |  | GLC-SX-MM |  |  | 4 |  | 39 | 156
| 8 | 5 | Y |  |  | Dell Optiplex 3050 MFF Computer w/VESA Mount | Dell | Yes |  | 3050MX |  |  | 2 |  | 932.37 | 1864.74
Quote #: 268116-1-10 | 8 | 5 | Y |  |  | Aggregation Taps | ViaviSolutions | Yes |  | TCTHG-K |  |  | 2 |  | 810 | 1620
Quote #: 268116-1-10 | 8 | 5 | Y |  |  | Aggregation Taps Mounts | ViaviSolutions | Yes |  | TCRM-K |  |  | 2 |  | 135 | 270
DO NOT ORDER | 5 | 5 | Y |  |  | Utility Table With Bottom Storage Shelf | OfficeDepot |  |  | 101662 |  |  | 1 |  | 189.99 | 189.99 |  |  |  |  | PR1912032 | PO-0000752 |  |  | 2019-03-01 |  | 2019-03-08 |  |  |  |  | No | [6 empty] | 189.99
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Realspace Conference Table | OfficeDepot |  |  | 878614 |  |  | 1 |  | 239.99 | 239.99 |  |  |  |  | PR1912032 | PO-0000752 |  |  | 2019-03-01 |  | 2019-03-08 |  |  |  |  | No | [6 empty] | 239.99
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | OfficeDepot | [5 empty] | 1 |  | 29.99 | 29.99 |  |  |  |  | PR1912032 | PO-0000752 |  |  | 2019-03-01 |  | 2019-03-08 |  |  |  |  | No | [6 empty] | 29.99
Quote: 12806703 | 5 | 5 | Y |  |  | LEGS FOR 24"D WORK SURFACE | Winsted Consoles |  |  | 48017 |  |  | 10 |  | 347.9 | 3479 |  | 3479 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 3479
Quote: 12806703 | 5 | 5 | Y |  |  | MODESTY PANEL FOR 72" DESK | Winsted Consoles |  |  | 48113 |  |  | 10 |  | 188.3 | 1883 |  | 1883 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 1883
Quote: 12806703 | 5 | 5 | Y |  |  | (A)LAMINATE W/COMF EDGE WS | Winsted Consoles |  |  | S48582 |  |  | 10 |  | 474.13 | 4741.3 |  | 4741.3 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 4741.3
Quote: 12806703 | 5 | 5 | Y |  |  | 3/4" VERSA TRACK FOR 72" TOP | Winsted Consoles | No |  | 48246 |  |  | 10 |  | 228.2 | 2282 |  | 2282 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 2282
Quote: 12806703 | 5 | 5 | Y |  |  | ARTICULATING LCD MOUNT 15"H | Winsted Consoles | No |  | W6491 |  |  | 30 |  | 319.2 | 9576 |  | 9576 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 9576
Quote: 12806703 | 5 | 5 | Y |  |  | PULLOUT SWIVEL CPU HOLDER | Winsted Consoles |  |  | 46260 |  |  | 10 |  | 128.8 | 1288 |  | 1288 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 1288
Quote: 12806703 | 5 | 5 | Y |  |  | ONSITE ASSEMBLY | Winsted Consoles |  |  | 10202 |  |  | 1 |  | 2912 | 2912 |  | 2912 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 2912
Quote: 12806703 | 5 | 5 | Y |  |  | FREIGHT/HANDLING/INSURANCE | Winsted Consoles |  |  | N/A |  |  | 1 |  | 5352 | 5352 |  | 5352 |  | 0 | PR188474 | PO18-07038 |  |  | 2018-12-05 |  | 2019-01-18 | 2019-01-18 |  |  |  | No | [5 empty] | 5352
| 8 | 5 | Y |  |  | Telephones | Siemens | [5 empty] | 12 |  | 200 | 2400
| 8 | 5 | Y |  |  | MOVE Headsets | Frequentis | [5 empty] | 34 |  | 100 | 3400
Quote VMA092018RG-2 Request to place order 01/30/19 | 5 | 5 | Y |  |  | FlexTiming Option for Timing I/O Module Uprade existing S650 Units. Serial Numbers : SCA171300040, SCA171300013, SCA171300036 | Microsemi |  |  | 920-15201-009 |  |  | 3 |  | 1000 | 3000 |  | 1470 |  |  | PR1912335 | PO-0000593 |  |  | 2019-02-22 |  | 2019-03-21 |  |  |  |  | No | 1470 | [6 empty] | 1470
Quote VMA092018RG-2 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | Microsemi | [5 empty] | 1 |  | 27 | 27 |  | 64.51 |  |  | PR1912335 | PO-0000593 |  |  | 2019-02-22 |  | 2019-03-21 |  |  |  |  | No | 64.51 | [6 empty] | 64.51
Quote# KCMV910 | 5 | 5 | Y |  |  | Red Hat Enterprise Linux Server - standard subscription | CDWG |  |  | RH00004S-CS |  |  | 1 |  | 929.71 | 929.71 |  | 275 |  |  | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 275
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | BNC Plug Connectors | TE Connectivity |  |  | 2-331350-9 |  |  | 35 |  | 16.49 | 577.15 |  | 301.7 |  |  | PR1912036 | PO-0000503 |  |  | 2019-02-18 |  | 2019-03-15 | 2019-03-15 |  |  |  | No | 301.7 | [5 empty] | 301.7
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | TE Connectivity | [5 empty] | 1 |  | 15 | 15 |  | 0 |  |  | PR1912036 | PO-0000503 |  |  | 2019-02-18 |  | 2019-03-15 | 2019-03-15 |  |  |  | No | 0 | [5 empty] | 0
Quote Number: 488177 Request to place order 01/30/19 | 5 | 5 | Y |  |  | OP-106/R/SC/13L/ME Optimux 106 with redundant power, SC fiber connectors, 1310 laser, metal enclosure | CutterNetworks |  |  | OP106RSC13LME |  |  | 1 |  | 775.44 | 775.44 |  |  |  |  | PR1912072 | PO-0000806 |  |  | 2019-03-05 |  | 2019-03-29 |  |  |  |  | No | [7 empty] | 775.44
Quote Number: 488177 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Rack Mount Kit 1/2 19", 1 device per shelf | CutterNetworks |  |  | RM-35/P1 |  |  | 1 |  | 17.28 | 17.28 |  |  |  |  | PR1912072 | PO-0000806 |  |  | 2019-03-05 |  | 2019-03-29 |  |  |  |  | No | [7 empty] | 17.28
Quote Number: 488177 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | CutterNetworks | [5 empty] | 1 |  | 85.63 | 85.63 |  |  |  |  | PR1912072 | PO-0000806 |  |  | 2019-03-05 |  | 2019-03-29 |  |  |  |  | No | [7 empty] | 85.63
Q20180919 r1 | 5 | 5 | Y |  |  | Type D - Desktop (L/R/VoIP) w/KPS | Frequentis | [5 empty] | 10 |  | 3042 | 30420 |  |  |  |  | PR189891 | PO-0000648 |  |  | 2019-02-26 |  | 2019-08-30 |  |  |  |  | No | 31387 | [9 empty] | 31387
Q20180919 r1 | 5 | 5 | Y |  |  | Maintenance for 1st year | Frequentis | [5 empty] | 8.3443 |  | 61 | 509 |  |  |  |  | PR189891 | PO-0000648 |  |  | 2019-02-26 |  | 2019-08-30 |  |  |  |  | No | 0 | [9 empty] | 0
Q20180919 r1 | 5 | 5 | Y |  |  | Handset 02.00 (PTT/PJ7) | United Communications | [5 empty] | 10 |  | 146 | 1460 |  | 1063.6 |  | 396.4 | PR1810229 | PO18-07550 |  |  | 2018-01-07 |  | 2019-01-18 | 2019-01-18 |  |  |  | Yes | 1048
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Round Lacing Bars With 1.5 Offset, 10 Pc. Pack | Middle Atlantic Parts/Anixter | [5 empty] | 2 |  | 82.52 | 165.04 |  | 152.52 |  | 12.52 | PR1912045 | PO-0000505 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 152.52
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Lacer Bar, Horizontal, Round, 4" Offset, 2 Mounting Point, 19" Width x 4" Depth x 0.4" Height, Steel, Black Powder Coated | Middle Atlantic Parts/Anixter | [5 empty] | 4 |  | 99.45 | 397.8 |  | 328.68 |  | 69.12 | PR1912045 | PO-0000505 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 328.68
Internet Quote Request to place order 01/30/19 | 5 | 5 | Y |  |  | Round Lacing Bars, 10 Pc. Pack | Middle Atlantic Parts/Anixter | [5 empty] | 2 |  | 62.24 | 124.48 |  | 122.75 |  | 1.73 | PR1912045 | PO-0000505 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 122.75
Quote #709 Request to place order 01/30/19 | 5 | 5 | Y |  |  | COMSEC Uni-Shelf 1U Assembly | Information Assurance Specialist | [5 empty] | 1 |  | 405 | 405 |  | 405 |  | 0 | PR1912055 | PO-0000510 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 405
Quote #709 Request to place order 01/30/19 | 5 | 5 | Y |  |  | IAS Quick Release Trays - Set of 2 | Information Assurance Specialists, Inc. | [5 empty] | 1 |  | 225 | 225 |  | 225 |  | 0 | PR1912055 | PO-0000510 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 225
Quote #709 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Outbound Shipping charges on product sales | Information Assurance Specialists, Inc. | [5 empty] | 1 |  | 30 | 30 |  | 30 |  | 0 | PR1912055 | PO-0000510 |  |  | 2019-02-18 |  | 2019-03-15 |  |  |  |  | Yes | 30
Quote# KCMV910 | 5 | 5 | Y |  |  | StarTech.com Flat-Screen TV Wall Mount | CDWG | [5 empty] | 6 |  | 44.64 | 267.84 |  | 240 |  | 27.84 | PR187622 | PO18-06661 |  |  | 2018-11-14 |  | 2018-11-21 | 2019-01-18 |  |  |  | Yes | 240
Quote ITSQ33193 Request to place order 01/30/19 | 5 | 5 | Y |  |  | 1000ft T1 - 24 awg - 2 Pair - Individually Shielded - Red Plenum Jacket - Solid Core (MOVE cables) | Infinit Technology Solutions | [5 empty] | 2 |  | 735 | 1470 |  | 1534.51 |  | -64.51 | PR1912115 | PO-0000593 |  |  | 2019-02-22 |  | 2019-03-21 |  |  |  |  | No | 1534.51 | [6 empty] | 1534.51
Quote 1045 Request to place order 01/30/19 | 5 | 5 | Y |  |  | 111S08080054C34 - Sentinel Connector RJ45 Plug (MOVE connectors) | RJ45S.COM | [5 empty] | 50 |  | 2.35 | 117.5 |  | 127.27 |  | -9.77 | PR1912051 | PO-0000574 |  |  | 2019-02-21 |  | 2019-03-01 |  |  |  |  | Yes | 127.27
Quote 1045 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | RJ45S.COM | [5 empty] | 1 |  | 9.99 | 9.99 |  | 10.82 |  | -0.83 | PR1912051 | PO-0000574 |  |  | 2019-02-21 |  | 2019-03-01 |  |  |  |  | Yes | 10.82
| Not In the Plan | 5 | Newly added 11/15/18 |  |  | Safco Scoot Desk-Side Printer Stand - printer cart | CDWG | [5 empty] | 4 |  | 133.53 |  |  | 534.12 |  | -534.12 | PR188461 | PO18-06781 |  |  | 2018-11-20 |  | 2018-11-30 | 2019-01-05 |  |  |  | Yes | 534.12
| Not In the Plan | 5 | Newly added 11/15/18 |  |  | basyx by HON HVL721 - chair | CDWG | [5 empty] | 20 |  | 194.1 |  |  | 3882 |  | -3882 | PR188461 | PO18-06781 |  |  | 2018-11-20 |  | 2018-11-30 | 2019-01-05 |  |  |  | Yes | 3882
| Not In the Plan | 5 | Newly added 12/12/18 |  |  | ES017 Handheld USB Wired Barcode Scanner | Esky |  |  | EAM Purchase |  |  | 1 |  | 62.99 |  |  | 59.99 |  | -59.99 | PR189385 | PO18-07446 |  |  | 2018-12-27 |  | 2018-12-27 | 2018-12-27 |  |  |  | Yes | 59.99
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | P/N: D0LG3LL: IBM Control Desk Authorized User License |  |  |  | EAM Purchase |  |  | 1 |  | 2143.05 |  |  | 2143.05 |  | -2143.05 | PR189372 | PO18-07407 |  |  | 2018-12-21 |  | 2018-12-21 | 2018-12-21 |  |  |  | No | [5 empty] | 2143.05
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | P/N:148-500-303 DataSplice Mobile Enterprise Named User | DataSpice Mobile |  |  | EAM Purchase |  |  | 1 |  | 795.39 |  |  | 16326.42 |  | -16326.42 | PR189359 | PO-0000300 |  |  | 2019-02-08 |  | 2019-02-13 | 2019-02-13 |  |  |  | No | [6 empty] | 16326.42
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | PowerEdge R430 Server (210-ADLO) | Dell Federal Systems |  |  | EAM Purchase |  |  | 1 |  | 2448.75 |  |  | 2448.75 |  | -2448.75 | PR189353 | PO18-07209 | 2018-12-12 |  | 2018-12-12 |  | 2018-12-20 | 2019-03-27 |  |  |  | No | [6 empty] | 2448.75
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | P/N: S535 Quartet Standard Whiteboard | CDW LLC | [5 empty] | 1 |  | 135.65 |  |  | 121.31 |  | -121.31 | PR189352 | PO18-07307 |  |  | 2018-12-18 |  | 2018-12-25 | 2019-02-03 |  |  |  | Yes | 121.31
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | P/N: SM538 Quartet Standard Whiteboard | CDW LLC | [5 empty] | 1 |  | 315.2 |  |  | 297.86 |  | -297.86 | PR189352 | PO18-07307 |  |  | 2018-12-18 |  | 2018-12-25 | 2019-02-03 |  |  |  | Yes | 297.86
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | P/N L30250F0600C151 UNIFY OPENSTAGE 40T (LAVA) (NEW) | VOIPLINK | [5 empty] | 8 |  | 299 |  |  | 2392 |  | -2392 | PR189261 | PO18-07080 |  |  | 2018-12-05 |  | 2018-12-11 | 2018-12-11 |  |  |  | Yes | 2392
| Not In the Plan | 5 | Newly added 12/13/18 |  |  | PREPAY AND ADD - Shipping | [6 empty] | 1 |  | 22.44 |  |  | 22.44 |  | -22.44 | PR189261 | PO18-07080 | 2018-12-05 |  | 2018-12-05 |  | 2018-12-11 | 2018-12-11 |  |  |  | Yes | 22.44
| Not In the Plan | 5 | Newly added 01/30/19 |  |  | Plantronics EncorePro HW540 - headset | CDWG | [5 empty] | 13 |  | 89 |  |  | 1131 |  | -1131 | PR1912022 | PO-0000426 |  |  | 2019-02-14 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 1131
| Not In the Plan | 5 | Newly added 01/30/19 |  |  | Plantronics A10-16 Direct Connect headset Cable | CDWG | [5 empty] | 13 |  | 33 |  |  | 1720 |  | -1720 | PR1912022 | PO-0000426 |  |  | 2019-02-14 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 1720
| Not In the Plan | 5 | Newly added 04/03/19 |  |  | Alien Vault Renewal | [6 empty] | 1 |  |  |  |  | 13308.01 |  |  | PR1913754 | PO-0001290 |  |  | 2019-03-28 |  | 2019-04-05 |  |  |  |  | No | [7 empty] | 13308.01
| Not In the Plan | 5 | Newly added 04/03/19 |  |  | Analog Phone | [6 empty] | 12 |  |  |  |  | 115.2 |  |  | PR1913789 | PO-0001410 |  |  | 2019-04-03 |  | 2019-04-03 |  |  |  |  | No | [7 empty] | 115.2
| Not In the Plan | 5 | Newly added 04/03/19 |  |  | Cat 6E 1000x, UTP, Plenum rate (CMP), Solid Cond, Cable | ATCOM SERVICES INC | [5 empty] | 1 |  |  |  |  | 517.04 |  |  | PR1912983 | PO-0000880 |  |  | 2019-03-08 |  | 2019-03-20 |  |  |  |  | No | [6 empty] | 517.04
| Not In the Plan | 5 | Newly added 04/03/19 |  |  | Pan Head Machine Screws | McMaster-Carr Supply Co. | [5 empty] | 1 |  |  |  |  | 9.82 |  |  | PR1912707 | PO-0000764 |  |  | 2019-03-04 |  | 2019-03-08 |  |  |  |  | No | [7 empty] | 9.82
| Not In the Plan | 5 | Newly added 04/03/19 |  |  | P/N: HBS304A24A | PROVANTAGE LLC | [5 empty] | 13 |  |  |  |  | 884 |  |  | PR1912982 | PO-0000881 |  |  | 2019-03-08 |  | 2019-03-15 |  |  |  |  | No | [7 empty] | 884
| Not In the Plan | 5 | Newly added 01/31/19 |  |  | Windows Server 2016 Standard & Microsoft SQL Server 2017 Standard) P/N: 228-11155 SQL SVR STD 2017 ENG OLP NL GOVT P/N: 359-06596 Microsoft - SQLCAL 2017 ENG OLP NL LclGov P/N: 9EM-00678 WinSvrSTDCore 2019 ENG OLP 2016Lic NL |  |  |  | EAM Purchase |  |  | 1 |  |  |  |  | 6788 |  | -6788 | PR199877 | PO18-07367 |  |  | 2018-12-20 |  | 2019-01-11 |  |  |  |  | No | [5 empty] | 6788
| Not In the Plan | 5 | Newly added 02/27/19 |  |  | OPTIPLEX 7060 Mini Tower XCTO (210-AOKJ) | Dell | [5 empty] | 2 |  | 1026.12 |  |  | 2069.84 |  |  | PR1912813 | PO-0000948 |  |  | 2019-03-12 |  | 2019-04-05 |  |  |  |  | No | [7 empty] | 2069.84
| Not In the Plan | 5 | Newly added 02/27/19 |  |  | CONN N Plug STR50 OHM CRIMP | DigiKey | [5 empty] | 10 |  | 289.24 |  |  | 298.23 |  |  | PR1912703 | PO-0000774 |  |  | 2019-03-04 |  | 2019-03-08 |  |  |  |  | No | [7 empty] | 298.23
| Not In the Plan | 5 | Newly added 02/27/19 |  |  | Cable Tie, Pan Ty® Locking, Nylon 6.6 (Polyamide 6.6) | Newark | [5 empty] | 10 |  | 30.21 |  |  | 280.4 |  |  | PR1912699 | PO-0000766 |  |  | 2019-03-04 |  | 2019-03-08 |  |  |  |  | No | [7 empty] | 280.4
| Not In the Plan | 5 | Newly added 02/12/19 |  |  | RF / Coaxial Connector, BNC Coaxial, Straight Plug, Crimp, 50 ohm, RG142, RG142A, RG142B, Brass | Newark |  |  | 2-331350-9 |  |  | 30 |  | 331.2 |  |  | 598.38 |  |  | PR1912081 | PO-0000589 |  |  | 2019-02-22 |  | 2019-03-06 |  |  |  |  | No | [6 empty] | 598.38
| Not In the Plan | 5 | Newly added 02/12/19 |  |  | Cables | LANshack | [5 empty] | 1 |  |  |  |  | 517.04 |  |  | PR1912094 | PO-0000880 |  |  | 2019-03-08 |  | 2019-03-20 |  |  |  |  | No | [6 empty] | 517.04
| Not In the Plan | 5 | Newly added 02/12/19 |  |  | LG 65UH5C-B UH5C Series - 65" LED display | CDWG | [5 empty] | 1 |  |  |  |  | 2851 |  | -2851 | PR1912061 | PO-0000426 |  |  | 2019-02-14 |  | 2019-02-22 |  |  |  |  | No | [5 empty] | 2851
| Not In the Plan | 5 | Newly added 02/12/19 |  |  | Digicert | [6 empty] | 1 |  |  |  |  | 680 |  |  | PR1912605 | PO-0000865 |  |  | 2019-03-06 |  | 2019-03-08 |  |  |  |  | No
Quote No: 207958 Request to place order 01/30/19 | 5 | 5 | Y |  |  | 225 Foot Fiber,10GB Multimode Duplex Fiber OM3, LC/LC, Plenum Rated | Cables for Less | [5 empty] | 3 |  | 126.28 | 378.84 |  | 378.84 |  | 0 | PR1912057 | PO-0000451 |  |  | 2019-02-15 |  | 2019-03-01 |  |  |  |  | No | [6 empty] | 378.84
Quote No: 207958 Request to place order 01/30/19 | 5 | 5 | Y |  |  | Shipping | Cables for Less | [5 empty] | 1 |  | 18.22 | 18.22 |  | 18.22 |  | 0 | PR1912057 | PO-0000451 |  |  | 2019-02-15 |  | 2019-03-01 |  |  |  |  | No | [6 empty] | 18.22
| 8 | 5 | Y |  |  | Wall-mount Time Zone Clock | Master Clock, Inc. | [5 empty] | 1 |  | 750 | 750
| 8 | 5 | Y |  |  | PowerEdge R630 Server (210-ACXS) | [6 empty] | 1 |  | 7363.08 | 7363.08
Q36185 | 8 | 3 | Y |  |  | Evaluation for Rotary Joints | Diamond Antenna & Microwave Corp. |  |  | 3171 |  |  | 3 |  | 500 | 1500
| 8 | 3 | Y |  |  | NEMA 4X Rated Enclosure | Hammond Mfg./Kaman Industrial technologies |  |  | 1418N4ALE10 |  |  | 1 |  | 1328.21 | 1328.21
| 8 | 3 | Y |  |  | Connector, N Male Straight Plug | Times Microwave/Anixter |  |  | TC-600-NMH-X |  |  | 30 |  | 14.63 | 438.9
| 8 | 3 | Y |  |  | Cable, LMR-600 | Times Microwave/Anixter |  |  | LMR-600-DB |  |  | 2000 |  | 2.47 | 4940
| 8 | 3 | Y |  |  | Connector, N Male Right Angle | RF Parts |  |  | F4NR-HC |  |  | 4 |  | 49.95 | 199.8
| 8 | 3 | Y |  |  | Cold Shrink Kit, ½ - 3/8 | RF Parts |  |  | 245173 |  |  | 20 |  | 20.95 | 419
| 8 | 3 | Y |  |  | Cold Shrink Kit, ½ - 7/8 | RF Parts |  |  | 245174 |  |  | 4 |  | 19.95 | 79.8
| 8 | 3 | Y |  |  | Connector, Bulkhead Adapter – Jack/Jack | Amphenol/Digi-Key |  |  | ARF1026-ND |  |  | 15 |  | 31.21 | 468.15
| 8 | 3 | Y |  |  | Connector, Bulkhead Adapter – F/M | ITT Cannon, LLC/Digi-Key |  |  | TBF22-14PSB-ND |  |  | 4 |  | 152.05 | 608.2
| 8 | 3 | Y |  |  | Waveguide to Coax Adapter | TBD |  |  | TBD |  |  | 1 |  | 291.06 | 291.06
| 8 | 3 | Y |  |  | WR430 Bulkhead Feedthru | L3-Narda-ATM |  |  | 430-130B-2-2 |  |  | 1 |  |  | 0
| 8 | 3 | Y |  |  | WR430 Stainless Hardware Kit | Mega Industries |  |  | 3928000000 |  |  | 30 |  |  | 0
| 8 | 3 | Y |  |  | SM Fiber Simplex Patch Cables | [6 empty] | 8 |  |  | 0
| 8 | 3 | Y |  |  | Rack Mount Chassis, Aluminum | Bud Industries |  |  | CH-14401 |  |  | 1 |  | 47.9 | 47.9
| 8 | 3 | Y |  |  | Rack Mount Chassis Lid | Bud Industries |  |  | C-14441 |  |  | 1 |  | 15.5 | 15.5
| 8 | 3 | Y |  |  | Custom Engraved I/O Panel | Front Panel Express |  |  | TBD |  |  | 1 |  |  | 0
| 8 | 3 | Y |  |  | SMA Female Bulkhead Adapter | Pasternack |  |  | PE91258 |  |  | 18 |  | 20.11 | 361.98
| 8 | 3 | Y |  |  | 10 dB Coupler | Pasternack |  |  | PE2202-10 |  |  | 2 |  | 343.65 | 687.3
| 8 | 3 | Y |  |  | Rotary Joint Refurb (PLACEHOLDER) | [9 empty] | 0
Quote #112259 | 8 | 3 | Y |  |  | S1 Antenna Waveguide Seals | Mega Industries |  |  | 77843-701 |  |  | 35 |  | 65.45 | 2290.75
Quotation Q-425264 | 8 | 3 | Y |  |  | S1 Antenna Waveguide Seals | Parker Hannifin Corporation |  |  | 20-03-1560-1212 |  |  | 99 |  | 89.47 | 8857.53
CDW Quote | 8 | 3 | Y |  |  | Cable Tray (xxx ft) - ETGT | [6 empty] | 40 |  | 12.8 | 512
[18 empty] | 3295255.22 |  | 187065.551 | [12 empty] | 3412374.32 |  | 0 | 0 | 0 | 69773.17 | 70936.1 | 40696.11 | 0 | 0 | 31387
[32 empty] | Status Unknown PO | 328355.25
[32 empty] | WBS 3 | 14528.6
[32 empty] | WBS 4 | 313826.65
[32 empty] | WBS 5 | None
[32 empty] | Check | TRUE
[35 empty] | 0 | 0 | 0
[35 empty] | 0 | 0 | 0
0
[35 empty] | 0 | 0 | 0 | 0 | 0
[35 empty] | Forecast January 2019 | Forecast February 2019
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Connectors | [11 empty] | 1097.64 |  | -1097.64 | PR1911175 | PO-0000310 |  |  | 2019-02-08 |  | 2019-02-15
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Fibers (PN: 1600-37-12-4-IOR-MTF-1-R-5A-.3-K) | [11 empty] | 2750 |  | -2750 | PR1911171 | PO-0000062 |  |  | 2019-01-29 |  | 2019-02-22
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Roxtec ALT0000003000 Assembly Gel,25 ml | [11 empty] | 83.08 |  | -83.08 | PR1910844 | PO-0000118 |  |  | 2019-01-31 |  | 2019-01-31
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Fibers | [11 empty] | 1311.96 |  | -1311.96 | PR1910840 | PO18-07774 |  |  | 2019-01-17 |  | 2019-01-25
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Cables | [11 empty] | 2988.2 |  | -2988.2 | PR1910839 | PO18-07799 |  |  | 2019-01-18 |  | 2019-01-30
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | RF Lambda Coupler | [11 empty] | 812 |  | -812 | PR1910834 | PO-0000026 |  |  | 2019-01-28 |  | 2019-02-06
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | RF Couplers | [11 empty] | 2026.57 |  | -2026.57 | PR1910825 | PO-0000015 |  |  | 2019-01-28 |  | 2019-03-22
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Copper Wire, Screws, Nut Spring | [11 empty] | 961.22 |  | -961.22 | PR198565 | PO18-07129 |  |  | 2018-12-07 |  | 2018-12-17
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | RACKMOUNT HW1032-100-CAGE 100PK 10-32 CAGE NUT HARDWARE KIT | [11 empty] | 152.28 |  | -152.28 | PR198574 | PO18-06779 |  |  | 2018-11-19 |  | 2018-12-17
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Fiber Materials | [11 empty] | 139.1 |  | -139.1 | PR1915045 | PO-0001835 |  |  | 2019-04-22 |  | 2019-05-17
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Fibers | [11 empty] | 250.32 |  | -250.32 | PR1915666 | PO-0001835 |  |  | 2019-04-22 |  | 2019-05-17
| Not In the Plan | 3 | Newly added 05/20/19 |  |  | Fiber Rack Termination | [11 empty] | 488.5 |  | -488.5 | PR1916264 | PO-0002550
| Not In the Plan | 4 | Newly added 05/20/19 |  |  | Red Hat Enterprise Linux Server | [11 empty] | 2459.88 |  | -2459.88 | PR199486 | PO18-07301 |  |  | 2018-12-18 |  | 2018-12-31
| Not In the Plan | 4 | Newly added 05/20/19 |  |  | PV-WAVE Renewal | [11 empty] | 756 |  | -756 | PR1911824 | PO-0000366 |  |  | 2019-02-12 |  | 2019-02-12
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | SAS adapter cable | [11 empty] | 283.44 |  | -283.44 | PR1910268 | PO18-07610 |  |  | 2019-01-10 |  | 2019-01-16
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | A.I. Solutions Renewal | [11 empty] | 25540 |  | -25540 | PR1912925 | PO-0001274 |  |  | 2019-03-28 |  | 2019-03-30
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | Red Hat Renewal | [11 empty] | 11400.48 |  | -11400.48 | PR1915017 | PO-0002063 |  |  | 2019-05-03 |  | 2019-05-06
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | VERITAS Backup Exec Server Edition | [11 empty] | 574.99 |  | -574.99 | PR1910270 | PO-0000054 |  |  | 2019-01-29 |  | 2019-01-29
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | LTO5-140 Tape label 1-200 Customer Kit | [11 empty] | 98.84 |  | -98.84 | PR1912798 | PO-0000866 |  |  | 2019-03-07 |  | 2019-03-15
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | Windows License | [11 empty] | 109.99 |  | -109.99 | PR1912799 | PO-0000867 |  |  | 2019-03-07 |  | 2019-03-07
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | Windows 10 Pro | [11 empty] | 274.56 |  | -274.56 | PR198442 | PO18-06756 |  |  | 2018-11-19 |  | 2018-11-27
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | BACKUP EXEC AGENT FOR LINUX 1 SKU: 10929-M2953 | [11 empty] | 239.99 |  | -239.99 | PR1915596 | PO-0002126 |  |  | 2019-05-06 |  | 2019-05-10
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | VMware Renewal | [11 empty] | 7472 |  | -7472 | PR1915668
| Not In the Plan | 4 | Newly added 05/21/19 |  |  | RedHat Renewal | [11 empty] | 4807 |  | -4807 | PR1915672
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | EAM Materials (Windows Server 2016 Standard & Microsoft SQL Server 2017 Standard) | [11 empty] | 6788 |  | -6788 | PR199877 | PO18-07367 |  |  | 2019-12-20 |  | 2019-12-31
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | EAM Materials (Vendor Esky for Wired Scanners Scanners) | [11 empty] | 59.99 |  | -59.99 | PR199385 | PO18-07446 |  |  | 2019-12-27 |  | 2019-12-27
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | EAM Materials (IBM Control Desk Authorized User License) | [11 empty] | 2143.05 |  | -2143.05 | PR199372 | PO18-07405
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | EAM Materials (DataSplice) | [11 empty] | 795.39 |  | -795.39 | PR199359 | PO-0000300 |  |  | 2019-02-08 |  | 2019-02-13
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | EAM Materials (Dell Server) | [11 empty] | 2448.75 |  | -2448.75 | PR199353 | PO18-07209 |  |  | 2018-12-12 |  | 2018-12-20
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Microsemi | [11 empty] | 3027 |  | -3027 | PR1912335 | PO-0000588 |  |  | 2019-02-22 |  | 2019-02-22
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Alien Vault Renewal | [11 empty] | 13308.01 |  | -13308.01 | PR1913754 | PO-0001290 |  |  | 2019-03-28 |  | 2019-04-05
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Cables | [11 empty] | 1534.51 |  | -1534.51 | PR1912115 | PO-0000593 |  |  | 2019-02-22 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Cables | [11 empty] | 517.04 |  | -517.04 | PR1912094 | PO-0000880 |  |  | 2019-03-08 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | RF / Coaxial Connector, BNC Coaxial, Straight Plug, Crimp, 50 ohm, RG142, RG142A, RG142B, Brass | [11 empty] | 598.38 |  | -598.38 | PR1912081 | PO-0000589 |  |  | 2019-02-22 |  | 2019-03-06
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | LED Display | [11 empty] | 2851 |  | -2851 | PR1912061 | PO-0000426 |  |  | 2019-02-14 |  | 2019-02-22
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Cables | [11 empty] | 397.06 |  | -397.06 | PR1912057 | PO-0000451 |  |  | 2019-02-15 |  | 2019-03-01
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | IAS Quick Release Trays - Set of 2, OMSEC Uni-Shelf 1U Assembly | [11 empty] | 660 |  | -660 | PR1912055 | PO-0000510 |  |  | 2019-02-18 |  | 2019-03-15
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Sentinel Connector RJ45 Plug | [11 empty] | 138.09 |  | -138.09 | PR1912051 | PO-0000574 |  |  | 2019-02-21 |  | 2019-03-01
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Round Lacing Bars | [11 empty] | 603.95 |  | -603.95 | PR1912045 | PO-0000505 |  |  | 2019-02-18 |  | 2019-03-15
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | DigiCert License | [11 empty] | 680 |  | -680 | PR1912605 | PO-0000844 |  |  | 2019-03-06 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | CONN N PLUG STR 50 OHM CRIMP | [11 empty] | 298.23 |  | -298.23 | PR1912703 | PO-0000774 |  |  | 2019-03-04 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Cable Tie, Pan Ty® Locking, Nylon 6.6 (Polyamide 6.6) | [11 empty] | 280.4 |  | -280.4 | PR1912699 | PO-0000766 |  |  | 2019-03-04 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Screws | [11 empty] | 9.82 |  | -9.82 | PR1912707 | PO-0000764 |  |  | 2019-03-04 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | OPTIPLEX 7060 Mini Tower XCTO (210-AOKJ) | [11 empty] | 2069.84 |  | -2069.84 | PR1912813 | PO-0000948 |  |  | 2019-03-12 |  | 2019-04-05
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Cable | [11 empty] | 517.04 |  | -517.04 | PR1912983 | PO-0000880 |  |  | 2019-03-08 |  | 2019-03-08
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | USB Sharing Switch | [11 empty] | 884 |  | -884 | PR1912982 | PO-0000881 |  |  | 2019-03-08 |  | 2019-03-15
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | AT T 210 Black Trimline Memory Telephone | [11 empty] | 115.2 |  | -115.2 | PR1913789 | PO-0001410 |  |  | 2019-04-03 |  | 2019-04-03
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Red Hat License | [11 empty] | 168 |  | -168 | PR1915025 | PO-0001847 |  |  | 2019-04-23 |  | 2019-04-26
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Nessus License | [11 empty] | 1877.65 |  | -1877.65 | PR1915027 | PO-0001845 |  |  | 2019-04-23 |  | 2019-04-26
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Rack Mount Shelf Kit | [11 empty] | 590 |  | -590 | PR1916181
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Power Cable | [11 empty] | 132.66 |  | -132.66 | PR1916182
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | V-Lock Power Cords | [11 empty] | 54 |  | -54 | PR1916183
| Not In the Plan | 5 | Newly added 05/21/19 |  |  | Graylog Enterprise - Unit Price per GB (5 GB/day) License | [11 empty] | 4500 |  | -4500 | PR1916267 | PO-0002546
| Not In the Plan | 5 | Newly added 05/22/19 |  |  | PIV USB PATCHPANEL AND CABLES | [14 empty] | PR1916590 | PO-0002687
| Not In the Plan | 5 | Newly added 05/22/19 |  |  | LEOP Table Ports | [14 empty] | PR1916588
3410380.32
[15 empty] | Materials Planned | MOD 0/ WBS 3.0 |  | 1354399.252
[15 empty] | Materials Planned | MOD 0/ WBS 4.0 |  | 415868.73
[15 empty] | Materials Planned | MOD 0/ WBS 5.0 |  | 13170.05
[15 empty] | Materials Planned | MOD 1/ WBS 3.0 |  | 2232
[15 empty] | Materials Planned | MOD 1/ WBS 4.0 |  | 225103.43
[15 empty] | Materials Planned | MOD 1/ WBS 5.0 |  | 0
[15 empty] | Materials Planned | MOD 2/ WBS 3.0 |  | 814122.876
[15 empty] | Materials Planned | MOD 2/ WBS 4.0 |  | 92785.94
[15 empty] | Materials Planned | MOD 2/ WBS 5.0 |  | 1077415.961
[15 empty] | Materials Planned | MOD 3/ WBS 3.0 |  | 105623.27
[15 empty] | Materials Planned | MOD 3/ WBS 4.0 |  | 96343.18
[15 empty] | Materials Planned | MOD 3/ WBS 5.0 |  | -24032.51
[15 empty] | Materials Planned | MOD 4/ WBS 3.0 |  | 2950
[15 empty] | Materials Planned | MOD 4/ WBS 4.0 |  | 0
[15 empty] | Materials Planned | MOD 4/ WBS 5.0 |  | 0
[15 empty] | Materials Planned | MOD 5/ WBS 3.0 |  | 7642.46
[15 empty] | Materials Planned | MOD 5/ WBS 4.0 |  | 56325.38
[15 empty] | Materials Planned | MOD 5/ WBS 5.0 |  | 96062.3
[15 empty] | Materials Planned | MOD 6/ WBS 3.0
[15 empty] | Materials Planned | MOD 6/ WBS 4.0
[15 empty] | Materials Planned | MOD 6/ WBS 5.0
[15 empty] | Materials Planned | MOD 7/ WBS 3.0 |  | 265250.48
[15 empty] | Materials Planned | MOD 7/ WBS 4.0 |  | 0
[15 empty] | Materials Planned | MOD 7/ WBS 5.0 |  | 0
[15 empty] | Materials Planned | MOD 8/ WBS 3.0 |  | 210930.45
[15 empty] | Materials Planned | MOD 8/ WBS 4.0 |  | 75520.45
[15 empty] | Materials Planned | MOD 8/ WBS 5.0 |  | 48069.64
[15 empty] | PO Issued Cost | MOD 0/WBS 3.0 |  | 812170.26
[15 empty] | PO Issued Cost | MOD 0/WBS 4.0 |  | 332435.37
[15 empty] | PO Issued Cost | MOD 0/WBS 5.0 |  | 0
[15 empty] | PO Issued Cost | MOD 1/WBS 3.0 |  | 2212
[15 empty] | PO Issued Cost | MOD 1/WBS 4.0 |  | 144692.71
[15 empty] | PO Issued Cost | MOD 1/WBS 5.0 |  | 0
[15 empty] | PO Issued Cost | MOD 2/ WBS 3.0 |  | 620566.94
[15 empty] | PO Issued Cost | MOD 2/ WBS 4.0 |  | 65030.13
[15 empty] | PO Issued Cost | MOD 2/ WBS 5.0 |  | 693379.04
[15 empty] | PO Issued Cost | MOD 3/ WBS 3.0 |  | 104303.27
[15 empty] | PO Issued Cost | MOD 3/ WBS 4.0 |  | 148116.22
[15 empty] | PO Issued Cost | MOD 3/ WBS 5.0 |  | 155462.64
[15 empty] | PO Issued Cost | MOD 4/ WBS 3.0 |  | 2950
[15 empty] | PO Issued Cost | MOD 4/ WBS 4.0 |  | 0
[15 empty] | PO Issued Cost | MOD 4/ WBS 5.0 |  | 0
[15 empty] | PO Issued Cost | MOD 5/ WBS 3.0 |  | 7342.72
[15 empty] | PO Issued Cost | MOD 5/ WBS 4.0 |  | 39427.3
[15 empty] | PO Issued Cost | MOD 5/ WBS 5.0 |  | #REF!
[15 empty] | PO Issued Cost | MOD 6/ WBS 3.0 |  | 0
[15 empty] | PO Issued Cost | MOD 6/ WBS 4.0 |  | 0
[15 empty] | PO Issued Cost | MOD 6/ WBS 5.0 |  | 0
[15 empty] | PO Issued Cost | MOD 7/ WBS 3.0 |  | 0
[15 empty] | PO Issued Cost | MOD 7/ WBS 4.0 |  | 0
[15 empty] | PO Issued Cost | MOD 7/ WBS 5.0 |  | 0
[15 empty] | PO Issued Cost | MOD 8/ WBS 3.0 |  | 0
[15 empty] | PO Issued Cost | MOD 8/ WBS 4.0 |  | 0
[15 empty] | PO Issued Cost | MOD 8/ WBS 5.0 |  | 0
Note on D2: Mason, Monika (Peraton) (US Person): “This column will be blank when a new row is initially added. WSC (C.Baxter or other designee) should be made aware of new items for inclusion in the CI database. Once this notification is made, a "Y" should be entered in this column.”
Note on S65: Mason, Monika (Peraton) (US Person): To date 08/30/18: payments 1, 2, and 3 have been paid
Note on S126: Mason, Monika (Peraton) (US Person): To date 08/30/18: payments 1, 2, and 3 have been paid
Note on N293: Mason, Monika (U.S. Person): Reduced the quantity from 3 to 1
Note on P297: Mason, Monika (U.S. Person): Increased from 10K to 33K
Note on N299: Mason, Monika (U.S. Person): Reduced from 5 to 1
Note on G320: Chaudhari, Supriya (Peraton) (Unknown): Line Inserted but no price in Budget estimate cost
Note on G328: Chaudhari, Supriya (Peraton) (Unknown): Line Inserted but no amount in Budget Estimated Cost.
Note on G330: Chaudhari, Supriya (Peraton) (Unknown): Replaced Dell 24' Monitor
Note on G331: Chaudhari, Supriya (Peraton) (Unknown): Replaced Dell 24' Monitor
Note on N335: Chaudhari, Supriya (Peraton) (Unknown) Quantity in Quotes is: 18.
Note on AG336: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG382: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold Emailed Yunita Allen in AP on the status.
Note on AG383: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold Emailed Yunita Allen in AP on the status.
Note on AG384: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold Emailed Yunita Allen in AP on the status.
Note on N387: Chaudhari, Supriya (Peraton) (Unknown): Quantity has to be changed to 1
Note on G393: Chaudhari, Supriya (Peraton) (Unknown): Not in the "various" quote
Note on AG480: Mason, Monika (Peraton) (US Person): Status: Open
Note on AG481: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG482: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG483: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG484: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG485: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG486: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG487: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG488: Mason, Monika (Peraton) (US Person): 04/04/19: Payment Status on Hold. Emailed Shebbrle Brown in AP to check on the status.
Note on AG497: Mason, Monika (Peraton) (US Person): 04/04/19: Anticipated Pay Date is 04/18/19
Note on AG498: Mason, Monika (Peraton) (US Person): 04/04/19: Anticipated Pay Date is 04/18/19
Note on AG499: Mason, Monika (Peraton) (US Person): 04/04/19: Payment status is on Hold. Emailed Dina Month in AP to check on the status.
Note on AG500: Mason, Monika (Peraton) (US Person): 04/04/19: Payment status is on Hold. Emailed Dina Month in AP to check on the status.
Note on AG513: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG514: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG515: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG517: Mason, Monika (Peraton) (US Person): 04/04/19: Anticipated Pay Date is 04/28/19
Note on AG518: Mason, Monika (Peraton) (US Person): 04/04/19: Payment status is on Hold. Emailed Mahelat Habtmariam regarding the status of payment.
Note on AG519: Mason, Monika (Peraton) (US Person): 04/04/19: Payment status is on Hold. Emailed Mahelat Habtmariam regarding the status of payment.
Note on AG521: Mason, Monika (Peraton) (US Person): 04/04/19: Anticipated Pay Date is 04/28/19
Note on AG524: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG526: Mason, Monika (Peraton) (US Person): Anticipated Delivery date: 03/20/19. Not reflecting on the Voucher History Inquiry section of CostPoint
Note on AG527: Mason, Monika (Peraton) (US Person): Anticipated Delivery date: 03/20/19. Not reflecting on the Voucher History Inquiry section of CostPoint
Note on AG533: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG534: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG567: Mason, Monika (Peraton) (US Person): Payment Status: HOLD
Note on AG568: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG570: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG571: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG572: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG573: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG574: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG575: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG576: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG577: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG578: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG579: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG580: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG595: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG596: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG597: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG598: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG599: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG600: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG601: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG602: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG605: Mason, Monika (Peraton) (US Person): Payment Status on Hold
Note on AG606: Mason, Monika (Peraton) (US Person): Payment Status on Hold
Note on AG608: Mason, Monika (Peraton) (US Person): Payment Status: HOLD
Note on AG609: Mason, Monika (Peraton) (US Person): Payment Status: HOLD
Note on AG616: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG617: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG618: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG619: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG620: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG621: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG624: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG625: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG628: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG629: Mason, Monika (Peraton) (US Person): Payment Status on hold
Note on AG630: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG631: Mason, Monika (Peraton) (US Person): Payment Status states Defer in CostPoint
Note on AG634: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG635: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG636: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG637: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG640: Mason, Monika (Peraton) (US Person): Payment Status: Hold
Note on AG641: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG642: Mason, Monika (Peraton) (US Person): Payment Status: Hold
Note on AG643: Mason, Monika (Peraton) (US Person): Payment Status: Hold
Note on AG644: Mason, Monika (Peraton) (US Person): Payment status on Hold
Note on AG645: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG646: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG648: Mason, Monika (Peraton) (US Person): Payment status on Hold
Note on AG649: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG650: Mason, Monika (Peraton) (US Person): Pcard purchase
Note on AG651: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AG652: Mason, Monika (Peraton) (US Person): Not appearing in the Vendor Voucher History Inquiry
Note on AJ1227: Mason, Monika (U.S. Person): WBS 3.0 (MOD 4)
Note on AK1227: Mason, Monika (U.S. Person): WBS 3.0 (MOD 4)
Note on AJ1228: Mason, Monika (U.S. Person): WBS 4.0 (MOD 4)
Note on AK1228: Mason, Monika (U.S. Person): WBS 4.0 (MOD 4)

## Milestone Payment
Oct | Nov | Dec | Jan 18 | Feb 18 | Mar 18 | Apr 18 | May 18 | Jun 18 | Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19 | Mar 19 | 2019-04-19 | 2019-05-20 | 2019-06-20 | 2019-07-19 | 2019-08-01 | 2019-09-19
Q1 FY 18 |  |  | Q2 FY 2018 |  |  | Q3 FY 2018 |  |  | Q4 FY 2018 |  |  | Q1 FY 2019 |  |  | Q2 FY 2019 |  |  | Q3 GFY 2019 |  |  | Q4 GFY 2019 |  |  | Milestone Payments | Milestone Dates | Vendor | WBS | MOD | Payment Amounts
[26 empty] | DigiSat | 5 | 2 | 199122
[25 empty] | Descope | DigiSat | 5 | 3 | -199122
[6 empty] | 369898 | [17 empty] | 9.1 M Antenna Milestone Payment #1 | 2018-01-19 | ViaSat | 3 | 2 | 369898
[8 empty] | 554847 | [15 empty] | 9.1 M Antenna Milestone Payment #2 | 2018-02-05 | ViaSat | 3 | 2 | 554847
[11 empty] | 554847 | [12 empty] | 9.1 M Antenna Milestone Payment #3 | 2018-05-04 | ViaSat | 3 | 2 | 554847
[11 empty] | 183673 | [12 empty] | 9.1 M Antenna Milestone Payment #4 | 2018-06-04 | ViaSat | 3 | 2 | 183673
[21 empty] | 1665817 |  |  | 9.1 M Antenna Milestone Payment #5 | 2018-08-03 | ViaSat | 3 | 2 | 1665817
[23 empty] | 369898 | 9.1 M Antenna Milestone Payment #6 | 2018-10-16 | ViaSat | 3 | 5 | 369898 | 3698980
[16 empty] | 202830 | [7 empty] | Antenna Pad Construction Payment #1 | 2019-01-20 | C & E Industrial Services Inc. | 3 | 6 | 202830
[19 empty] | 91273.5 |  |  |  |  | Antenna Pad Construction Payment #2 | 2019-02-20 | C & E Industrial Services Inc. | 3 | 6 | 101415
[21 empty] | 212971.5 |  |  | Antenna Pad Construction Payment #3 | 2019-04-20 | C & E Industrial Services Inc. | 3 | 6 | 202830 | 507075
[11 empty] | 32400.47 | [12 empty] | Contract Award Payment #1 | 2018-06-13 | BRPH | 3 | 4 | 32400.47
[11 empty] | 32400.47 | [12 empty] | 60% Design Review Payment #2 | 2018-08-05 | BRPH | 3 | 4 | 32400.47
[13 empty] | 38880.56 | [10 empty] | 90% Construction Documents Payment #3 | 2018-09-21 | BRPH | 3 | 4 | 38880.56
[15 empty] | 25920.38 | [8 empty] | Final Acceptance Payment #4 | 2018-10-05 | BRPH | 3 | 4 | 25920.38 | 129601.88
[13 empty] | 263083.8 | [10 empty] | Payment #1: Notice of Award Payment #2: Notice to Proceed Payment #3: Mobilization Payment #4: Demolition and Temporary Barriers Payment #5: Infrastructure Rough-In Payment #6: SCWA Build | 2018-10-01 | C & E Industrial Services Inc. | 5 | 3 | 263083.8
[13 empty] | 263083.8 | [10 empty] | Payment #7: SSOC Build | 2018-10-01 | C & E Industrial Services Inc. | 5 | 3 | 263083.8
[13 empty] | 87694.6 | [10 empty] | Payment #8: LSR Build Materials | 2018-10-01 | C & E Industrial Services Inc. | 5 | 3 | 87694.6
[13 empty] | 87694.6 | [10 empty] | Payment #9: SSOC / SCWA Build Completion | 2018-10-31 | C & E Industrial Services Inc. | 5 | 5 | 87694.6
[13 empty] | 28939.22 |  | 41216.46 | [8 empty] | Payment #10: LSR Infrastructure Rough-In | 2018-10-08 | C & E Industrial Services Inc. | 5 | 3 | 70155.68
[15 empty] | 87694.6 | [8 empty] | Payment #11: LSR Build | 2018-10-31 | C & E Industrial Services Inc. | 5 | 5 | 87694.6
[17 empty] | 8769.46 | [6 empty] | Payment #12: Commissioning & Owner Training | 2018-11-09 | C & E Industrial Services Inc. | 5 | 5 | 8769.46
[17 empty] | 8769.46 | [6 empty] | Payment #13: Project Close-Outs Complete & Demobilization | 2018-11-09 | C & E Industrial Services Inc. | 5 | 5 | 8769.46 | Sanity Check
[6 empty] | 369898 | 0 | 554847 | 0 | 0 | 803320.94 | 0 | 769376.58 | 0 | 154831.44 | 202830 | 17538.92 | 0 | 91273.5 | 0 | 1878788.5 | 0 | 369898 | [5 empty] | 5212602.88 | TRUE
[5 empty] | 0 | 924745 |  |  | 803320.94 |  |  | 769376.58 |  |  | 375200.36 |  |  | 91273.5 |  |  | 2248686.5 | [7 empty] | 5212602.88 | TRUE
0
GFY19 Milestone Payments
1235850.44
Note on G6: Mason, Monika (Peraton) (US Person): Actuals
Note on AA6: Mason, Monika (U.S. Person): Moved to Q1GFY19
Note on I7: Mason, Monika (Peraton) (US Person): Actuals
Note on L8: Mason, Monika (Peraton) (US Person): Actuals
Note on AA8: Mason, Monika (U.S. Person): Moved to Q1GFY19
Note on L9: Mason, Monika (Peraton) (US Person): Actuals
Note on V10: Thurston, Donna (Peraton) (US Person): ViaSat Payments for Factory Acceptance Test moved to March 2019 per Chris due to shift in schedule. Milestone Payment #5
Note on X11: Site Acceptance Test Completion- Milestone Payment #6
Note on L17: Mason, Monika (Peraton) (US Person): Actuals
Note on L18: Mason, Monika (Peraton) (US Person): Actuals

## calucations for ETC (hidden)
|  | Forecast February 2018 | Forecast March 2018 | Forecast April 2018 | Forecast May 2018 | Forecast June 2018 | Forecast July 2018 | Forecast August 2018 | Forecast September 2018 | Forecast October 2018 | Forecast November 2018 | Forecast December 2018 | Forecast January 2019 | Forecast February 2019 | Forecast March 2019 | Forecast April 2019 | Forecast May 2019 | Forecast June 2019 | Forecast July 2019 | Forecast August 2019 | Forecast September 2019 | Forecast October 2019 | Forecast November 2019 | Forecast December 2019 | Forecast January 2020 | Forecast February 2020 | Forecast March 2020 | Forecast April 2020 | Forecast May 2020 | Forecast June 2020 | Forecast July 2020 | Forecast August 2020 | Forecast September 2020 | Forecast October 2020
| MOD 0 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| MOD 1 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| MOD 2 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 3 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 4 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 3847.64 | 4150.53 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | 0
| MOD 5 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 3847.64 | 4150.53 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 6 - 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 3847.64 | 4150.53 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| WBS 3.0 Materials Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 7695.28 | 8301.06 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| MOD 0 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 1 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 2 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 3 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 4 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 5 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 6 - 4.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| WBS 4.0 Materials Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
| MOD 2 - 5.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 3 - 5.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 4 - 5.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 5 - 5.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| MOD 6 - 5.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0
| WBS 5.0 Materials Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
#REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 94646.75 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 94646.75 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 37858.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 18929.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 111698.75 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 111698.75 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 44679.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 22339.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RTLogic | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | 554847 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | 183673 | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1665817 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ViaSat | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 369898 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | 50000 | #REF! | #REF! | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 200000 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100000 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 150000 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 101467.55 | 22339.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70155.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 263083.8 | 245544.88 | 0 | 96464.06 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876946
#REF!

## analysis (hidden)
#REF!
Difference
ETC Mod 1/WBS 3.0 | 45494.05 | Mod 1 What we spent so far (PO's) | WBS 3.0 | 94368.06 | -48874.01
ETC Mod 1/ WBS 4.0 | 149621.48 | Mod 1 What we spent so far (PO's) | WBS 4.0 | 144692.71 | 4928.77
ETC Mod 1/ WBS 5.0 | 0 | Mod 1 What we spent so far (PO's) | WBS 5.0 | 0 | 0
ETC Mod 2/WBS 3.0 | 215077.3 | Mod 2 What we spent so far (PR + PO's) | WBS 3.0 | #REF! | #REF!
ETC Mod 2/ WBS 4.0 | 39207.12 | Mod 2 What we spent so far (PR + PO's) | WBS 4.0 | #REF! | #REF!
ETC Mod 2/ WBS 5.0 | 683045.927 | Mod 2 What we spent so far (PR + PO's) | WBS 5.0 | #REF! | #REF!
ETC Mod 3/WBS 3.0 | 267424.35 | Mod 3: (Current Basis of Estimate) | WBS 3.0 | #REF! | #REF!
ETC Mod 3/ WBS 4.0 | 5598.83 | Mod 3: (Current Basis of Estimate) | WBS 4.0 | #REF! | #REF!
ETC Mod 3/ WBS 5.0 | 161340.07 | Mod 3: (Current Basis of Estimate) | WBS 5.0 | #REF! | #REF!
| 1566809.127 |  |  | #REF! | #REF!
ETC Mod 4/WBS 3.0 | 207869.2 | Mod 4: (Current Basis of Estimate) | WBS 3.0 | #REF! | #REF!
ETC Mod 4/ WBS 4.0 | 87945.2 | Mod 4: (Current Basis of Estimate) | WBS 4.0 | #REF! | #REF!
ETC Mod 4/ WBS 5.0 | 106507.1 | Mod 4: (Current Basis of Estimate) | WBS 5.0 | #REF! | #REF!
| 1969130.627 |  |  | #REF! | #REF!

## TO 190 ETC (hidden)
| Materials | Forecast February 2018 | Forecast March 2018 | Forecast April 2018 | Forecast May 2018 | Forecast June 2018 | Forecast July 2018 | Forecast August 2018 | Forecast September 2018 | Forecast October 2018 | Forecast November 2018 | Forecast December 2018 | Forecast January 2019 | Forecast February 2019 | Forecast March 2019 | Forecast April 2019 | Forecast May 2019 | Forecast June 2019 | Forecast July 2019 | Forecast August 2019 | Forecast September 2019 | Forecast October 2019 | Forecast November 2019 | Forecast December 2019 | Forecast January 2020 | Forecast February 2020 | Forecast March 2020 | Forecast April 2020 | Forecast May 2020 | Forecast June 2020 | Forecast July 2020 | Forecast August 2020 | Forecast September 2020 | Forecast October 2020 | Total
| MOD 0 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 1 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 2 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51329 | 0 | 36595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 3 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47435.27 | 0 | 61168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 4 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 5 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 777.83 | 154343.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 6 - 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241102.45 | 0 | 0 | 0 | 0
| WBS 3.0 Materials Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101714.27 | 473000 | 98540.83 | 154343.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241102.45 | 0 | 0 | 0 | 0 | 1068700.9
| MOD 0 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 1 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 2 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 5378.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 3 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11625 | 169801.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 4 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 5 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 5574.87 | 0 | 0 | 37115.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 6 - 4.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5574.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75520.45 | 0 | 0 | 0 | 0 | 0
| WBS 4.0 Materials Total | 0 | 0 | 0 | 0 | 0 | 0 | 3648 | 28153.3 | 169801.28 | 0 | 37115.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75520.45 | 0 | 0 | 0 | 0 | 0 | 314238.23
| MOD 2 - 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296431.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 3 - 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191673.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 4 - 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 5 - 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41165.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MOD 6 - 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68990.56 | 0 | 0 | 0
| WBS 5.0 Materials Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296431.76 | 191673.54 | 0 | 41165.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68990.56 | 0 | 0 | 0 | 598260.91
1981200.04
| Milestones | Forecast February 2018 | Forecast March 2018 | Forecast April 2018 | Forecast May 2018 | Forecast June 2018 | Forecast July 2018 | Forecast August 2018 | Forecast September 2018 | Forecast October 2018 | Forecast November 2018 | Forecast December 2018 | Forecast January 2019 | Forecast February 2019 | Forecast March 2019 | Forecast April 2019 | Forecast May 2019 | Forecast June 2019 | Forecast July 2019 | Forecast August 2019 | Forecast September 2019 | Forecast October 2019 | Forecast November 2019 | Forecast December 2019 | Forecast January 2020 | Forecast February 2020 | Forecast March 2020 | Forecast April 2020 | Forecast May 2020 | Forecast June 2020 | Forecast July 2020 | Forecast August 2020 | Forecast September 2020 | Forecast October 2020 | Total
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333180.45 | 0 | 31175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 94646.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94646.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37858.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18929.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 111698.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111698.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44679.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22339.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTLogic | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 554847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 183673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ViaSat | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foundation Construction Vendor (Not selected Yet) | WBS 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 50000 | 738520 | 206345.5 | 2298997.45 | 0 | 757418.5 | 0 | 101467.55 | 22339.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4175088.75
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70155.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87694.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C & E Industrial Services Inc. | WBS 5.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263083.8 | 263083.8 | 245544.88 | 0 | 96464.06 | 8769.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876946 | Sanity Check | TRUE
[35 empty] | 5052034.75 | 7033234.79
| Totals for Materials and Milestone by Month | Forecast February 2018 | Forecast March 2018 | Forecast April 2018 | Forecast May 2018 | Forecast June 2018 | Forecast July 2018 | Forecast August 2018 | Forecast September 2018 | Forecast October 2018 | Forecast November 2018 | Forecast December 2018 | Forecast January 2019 | Forecast February 2019 | Forecast March 2019 | Forecast April 2019 | Forecast May 2019 | Forecast June 2019 | Forecast July 2019 | Forecast August 2019 | Forecast September 2019 | Forecast October 2019 | Forecast November 2019 | Forecast December 2019 | Forecast January 2020 | Forecast February 2020 | Forecast March 2020 | Forecast April 2020 | Forecast May 2020 | Forecast June 2020 | Forecast July 2020 | Forecast August 2020 | Forecast September 2020 | Forecast October 2020 | Total
|  | 0 | 0 | 0 | 0 | 50000 | 738520 | 209993.5 | 2988380.58 | 1097558.62 | 1101504.21 | 232623.6 | 197931.61 | 31109.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75520.45 | 241102.45 | 68990.56 | 0 | 0 | 0 | 7033234.79
Note on J4: Mason, Monika (U.S. Person): 19X4 Crossbar Terminated RF Switch I/O ports are terminated to 2W 50-ohm load DC to 18 GHz operating frequency 4RU Enclosure SMA connectors on the rear panel LCD Touch Screen for manual control Ethernet with HTTP-Server (built-in website), RS -232 and USB remote controls
Note on J5: Mason, Monika (U.S. Person): Mu-Del Up/Down Converter Cables
Note on J6: Mason, Monika (U.S. Person): Soil Sample

## Calculations (hidden)
Oct | Nov | Dec | Jan 18 | Feb 18 | Mar 18 | Apr 18 | May 18 | Jun 18 | Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19 | Mar 19
Q1 FY 18 |  |  | Q2 FY 2018 |  |  | Q3 FY 2018 |  |  | Q4 FY 2018 |  |  | Q1 FY 2019 |  |  | Q2 FY 2019 |  |  | Q3 FY 2019 | Q4 FY 2019 | Milestone Payments |  | Milestone Dates | Vendor | Payment Amounts
[5 empty] | 37858.7 | [14 empty] | HDR Modem Milestone Payment #1 |  | 2017-12-21 | RTLogic | 37858.7
[8 empty] | 94646.75 | [11 empty] | HDR Modem Milestone Payment #2 |  | 2018-01-18 | RTLogic | 94646.75
[11 empty] | 94646.75 | [8 empty] | HDR Modem Milestone Payment #3 |  | 2018-04-12 | RTLogic | 94646.75
[14 empty] | 94646.75 | [5 empty] | HDR Modem Milestone Payment #4 |  | 2018-08-02 | RTLogic | 94646.75
[16 empty] | 37858.7 |  |  |  | HDR Modem Milestone Payment #5 |  | 2018-09-13 | RTLogic | 37858.7
[16 empty] | 18929.35 |  |  |  | HDR Modem Milestone Payment #6 |  | 2018-10-11 | RTLogic | 18929.35
[5 empty] | 44679.5 | [14 empty] | LDR Modem Milestone Payment #1 |  | 2017-12-21 | RTLogic | 44679.5
[8 empty] | 111698.75 | [11 empty] | LDR Modem Milestone Payment #2 |  | 2018-01-18 | RTLogic | 111698.75
[11 empty] | 111698.75 | [8 empty] | LDR Modem Milestone Payment #3 |  | 2018-04-12 | RTLogic | 111698.75
[14 empty] | 111698.75 | [5 empty] | LDR Modem Milestone Payment #4 |  | 2018-08-02 | RTLogic | 111698.75
[16 empty] | 44679.5 |  |  |  | LDR Modem Milestone Payment #5 |  | 2018-09-13 | RTLogic | 44679.5
[17 empty] | 22339.75 |  |  | LDR Modem Milestone Payment #6 |  | 2018-10-11 | RTLogic | 22339.75
[20 empty] | Extra Amount in Proposal |  |  | RTLogic | 122340
[6 empty] | 369898 | [13 empty] | 9.1 M Antenna Milestone Payment #1 |  | 2018-01-19 | ViaSat | 369898
[7 empty] | 554847 | [12 empty] | 9.1 M Antenna Milestone Payment #2 |  | 2018-02-05 | ViaSat | 554847
[10 empty] | 554847 | [9 empty] | 9.1 M Antenna Milestone Payment #3 |  | 2018-05-04 | ViaSat | 554847
[10 empty] | 183673 | [9 empty] | 9.1 M Antenna Milestone Payment #4 |  | 2018-06-04 | ViaSat | 1183673
[12 empty] | 1665817 | [7 empty] | 9.1 M Antenna Milestone Payment #5 |  | 2018-08-03 | ViaSat | 665817
[14 empty] | 369898 | [5 empty] | 9.1 M Antenna Milestone Payment #6 |  | 2018-10-16 | ViaSat | 369898
[9 empty] | 50000 | [10 empty] | 9.1M Antenna Foundation Payment #1 |  | 2018-05-06 | ViaSat | 50000
[12 empty] | 200000 | [7 empty] | 9.1M Antenna Foundation Payment #2 |  | 2018-07-14 | ViaSat | 200000
[12 empty] | 100000 | [7 empty] | 9.1M Antenna Foundation Payment #3 |  | 2018-08-14 | ViaSat | 100000
[14 empty] | 150000 | [5 empty] | 9.1M Antenna Foundation Payment #4 |  | 2018-10-16 | ViaSat | 150000
[12 empty] | 0 | [7 empty] | Payment #1: Notice of Award |  | 2018-02-19 | C & E Industrial Services Inc. | 0
[12 empty] | 0 | [7 empty] | Payment #2: Notice to Proceed |  | 2018-07-18 | C & E Industrial Services Inc. | 0
[12 empty] | 0 | [7 empty] | Payment #3: Mobilization |  | 2018-07-02 | C & E Industrial Services Inc. | 0
[12 empty] | 0 | [7 empty] | Payment #4: Demolition and Temporary Barriers |  | 2018-07-11 | C & E Industrial Services Inc. | 0
[13 empty] | 0 | [6 empty] | Payment #5: Infrastructure Rough-In |  | 2018-08-17 | C & E Industrial Services Inc. | 0
[12 empty] | 263083.8 | [7 empty] | Payment #6: SCWA Build |  | 2018-10-01 | C & E Industrial Services Inc. | 263083.8
[13 empty] | 263083.8 | [6 empty] | Payment #7: SSOC Build |  | 2018-10-01 | C & E Industrial Services Inc. | 263083.8
[14 empty] | 87694.6 | [5 empty] | Payment #8: LSR Build Materials |  | 2018-10-01 | C & E Industrial Services Inc. | 87694.6
[14 empty] | 87694.6 | [5 empty] | Payment #9: SSOC / SCWA Build Completion |  | 2018-10-31 | C & E Industrial Services Inc. | 87694.6
[14 empty] | 70155.68 | [5 empty] | Payment #10: LSR Infrastructure Rough-In |  | 2018-10-08 | C & E Industrial Services Inc. | 70155.68
[16 empty] | 87694.6 |  |  |  | Payment #11: LSR Build |  | 2018-10-31 | C & E Industrial Services Inc. | 87694.6
[16 empty] | 8769.46 |  |  |  | Payment #12: Commissioning & Owner Training |  | 2018-11-09 | C & E Industrial Services Inc. | 8769.46
[17 empty] | 8769.46 |  |  | Payment #13: Project Close-Outs Complete & Demobilization |  | 2018-11-09 | C & E Industrial Services Inc. | 8769.46
[5 empty] | 82538.2 |  |  | 1131090.5 |  |  | 994865.5 |  |  | 3463772.98 |  |  | 220271.36 | [6 empty] | 6023648
[20 empty] | 1972090.85 |  | Mod 0,1,2 materials
[14 empty] | 9369179.96 | Awarded to Date through Mod 2 |  |  |  |  | 4646702 |  | Mod 0,1,2 milestone payments on contract to date |  | 455931.93 | Mod 3 materials
[14 empty] | 6618792.85 | Committed to date through Mod 2 |  |  |  |  | 6618792.85 |  | Total |  | 684017.88 | Mod 3 milestone payments
[14 empty] | 2750387.11 | Difference | [8 empty] | 1139949.81 | Total of Mod 3 without De-Scope
[20 empty] | 1972090.85 |  | Mod 0,1,2 materials |  | -475887 | Total De-scope
[20 empty] | 455931.93 |  | Mod 3 materials |  | 664062.81 | Expected cost for Mod 3
[20 empty] | 4646702 |  | Mod 0,1,2 milestone payments on contract to date |  | 662828.81 | Awarded amount for Mod 3
[20 empty] | 684017.88 |  | Mod 3 milestone payments |  | 1234 | Variance in quotes received
[20 empty] | 7758742.66 |  | Actuals to date of Mod 0,1,2 and Budgeted Estimated Cost for Mod 3
[24 empty] | 947722 | RTL Total
[20 empty] | -265465 | De-scope IEM Softbench Simulator | De-scope IEM Softbench Simulator |  | 825382 | RTL in May 8th file
[11 empty] | 6023648 | milestone payments in total | [7 empty] | -199122 | De-Scope DigiSat | De-Scope DigiSat |  | 122340 | Added May 22
[11 empty] | 2971224.86 | Total Materials for MOD 0-4 | [7 empty] | -11300 | De-scope SCWA Door Assembly | De-scope SCWA Door Assembly
[11 empty] | 8994872.86 | Total ETC for 190 | [7 empty] | -475887 |  | Total De-scope
[20 empty] | 7282855.66 |  | Actuals to date including the De-scope
[16 empty] | 8994872.86 | Cross check
[16 empty] | 8994872.86 | Cross check | [6 empty] | 3005197 | Materials only plan value from May 8th file
[16 empty] | 0 | variance |  |  | 692928.12 |  | Mod 4 milestones currently not on contract to date |  | 2971224.86 | Materials only from actuals used from May 22 update
[20 empty] | 543202.08 |  | Mod 4 materials |  | 33972.14 | Difference
[20 empty] | 1236130.2 |  | Total Mod 4
[11 empty] | 9032199.721 | Total ETC for 190 on TO 190 Summary Page | [7 empty] | 8994872.86 |  | ETC
[11 empty] | 8994872.86 | Total ETC for 190 adding in Actuals | [7 empty] | 8518985.86 |  | ETC with De-scope
[11 empty] | 37326.861 | Difference between ETC's | [7 empty] | 8518985.86 |  | ETC with De-scope
9369179.96
[22 empty] | 6618792.85 | Awarded to date
[11 empty] | Justification for Difference in Total ETC | [10 empty] | 2750387.11 | Actuals to date
[11 empty] | 37326.861 | [11 empty] | Difference
[20 empty] | 6618792.85 |  | 6618792.85 | Mod 0, 1, 2
[11 empty] | Difference | [10 empty] | 1139949.81 | Mod 3
[11 empty] | 638832.402 | Mod 0 overrun | [9 empty] | 1236130.2 | Mod 4
[11 empty] | 80430.72 | Mod 1 underrun | [9 empty] | 8994872.86 | Total ETC for 190
[11 empty] | 3208807.667 | Mod 2 underrun
[11 empty] | 3928070.789 | [10 empty] | 8994872.86 | Total ETC for 190
[22 empty] | -475887 | Total De-scope
[22 empty] | 8518985.86 | Total ETC for 190 including De-Scope
37326.861
[11 empty] | 3928070.789 | [10 empty] | 999134.01
[11 empty] | -3890743.928 | Mod 2 continue procurements | [10 empty] | Mod 3&4 materials only
[20 empty] | 8994872.86 |  | ETC Updated May 22nd
[20 empty] | 8906504.771 |  | ETC Reported May 8th
[20 empty] | 88368.089 |  | Difference
[20 empty] | 3 |  | Difference
[20 empty] | 122340 |  | RT Logic Milestone Payment Added
[20 empty] | -122337 |  | Mod's 0, 1, 2 variances
Formulas:
Milestone Dates = [Milestone Dates, row above]+4*7
Note on F3: Mason, Monika (U.S. Person): Paid in December 2017
Note on F9: Mason, Monika (U.S. Person): Paid in February 2018
Note on W16: Mason, Monika (U.S. Person): Moved to Q1GFY19
Note on W18: Mason, Monika (U.S. Person): Moved to Q1GFY19
Note on U42: Mason, Monika (U.S. Person): Actual Cost from PO's for MOD's 0,1,2
Note on U46: Mason, Monika (U.S. Person): Actual Cost from PO's for MOD's 0,1,2
Note on U47: Mason, Monika (U.S. Person): Budgeted cost for MOD 3

## Sheet1 (hidden)
3
4
5
0
1
2
3
4