## Dec 20
|  | GFY 20 | [11 empty] | GFY 21
|  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21
| SV Milestones |  |  |  |  | SV Tng | ETE 2 RF Compat |  |  |  | ETE 3 |  |  | ETE 4 'Ship SV | FRR LRR | Dec 25 ILC | NORR | LEOP Cmplt
| WBS 4 - SSOC | [5 empty] | B4.2 dev | B4.2 dev | B4.2 test | B4.2 FAT | B/4.2 SAT
| WBS 6 - I&T | [5 empty] | SGRT 3b
RF Compat
[7 empty] | EtE 2 |  |  |  | EtE 3 |  |  | EtE 4
| WBS 7 Ops Prep | [7 empty] | SOS 1 |  | SOS 2, 3 | SOS 4
|  | Crypto Test | [7 empty] | MR 1 | MR 2 |  | MR 3 | MR 4
[15 empty] | LR 1 | LR 2,3
|  | BATHTUB | [11 empty] | GS Freeze
Continued ops product dev, transfer of more responsibility to WSC FET. OJT. Coordination with NGIS.
TO189 / TO 216 WBS'
|  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21
WBS 7 | OMI FOT | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 4
WBS 4 | OMI SE | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1
WBS 4 | OMI SA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5
WBS 4 | OMI DEV | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 3 | 3 | 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
WBS 4 | ai Solutions | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1
WBS 4 | WSC IT&NE | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17
WBS 7 | WSC TM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 7 | WSC FET | 3 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
WBS 7 | WSC SE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5
WBS 7 | WSC SA | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS 7 | WSC ISSE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 7 | Abile | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 7 | Craig Tech | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
WBS 7 | Five Rivers | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
WBS 3 | GSFC CTA |  |  | 0.5 | 1 | 2 | 2 | 0.5
WBS 3 | WSC HW Eng | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
WBS 7 | Qwaltec |  |  | 1.1 | 1 | 1.1 | 1.5 | 1.4 | 1.7 | 1.7 | 1.2 | 1.8 | 2.2 | 1.4 | 1.1 | 0.5
| OMI Total | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 9.5 | 9.5 | 10 | 10 | 6.75 | 7.25 | 7.25 | 7.25 | 7.25 | 7.75 | 6.75 | 5.75
| WSC Total | 6.4 | 7.4 | 6.9 | 8.9 | 8.9 | 8.9 | 8.9 | 8.9 | 9.4 | 9.4 | 9.4 | 9.4 | 9 | 9 | 9 | 8.5 | 8.5
| GFSC Total | 0 | 0 | 0.5 | 1 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Qwaltec Total | 0 | 0 | 1.1 | 1 | 1.1 | 1.5 | 1.4 | 1.7 | 1.7 | 1.2 | 1.8 | 2.2 | 1.4 | 1.1 | 0.5 | 0 | 0
| ai Solutions Total | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1 | 0
| Abile | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Five Rivers | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
| Craig Tech | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
| Total | 11.3 | 12.3 | 13.4 | 15.8 | 16.9 | 24.3 | 22.7 | 23 | 23.5 | 19.75 | 21.8 | 22.2 | 19.6 | 19.3 | 19.2 | 16.25 | 14.25
TRAVEL
|  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21
| OMI - WBS 4 |  |  |  |  | 663.6795 | 0 | 0 | 0 | 0 | 13300.8993 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OMI - WBS 6 |  |  |  |  | 0 | 13300.8993 | 0 | 0 | 0 | 13300.8993 | 0 | 0 | 11706.7983 | 0 | 0 | 0 | 0
| OMI - WBS 7 | 5871 |  |  |  | 442.453 | 0 | 0 | 10836.3937 | 12557.8323 | 28937.1672 | 12557.8323 | 14279.2709 | 17485.0439 | 9319.1398 | 18638.2797 | 50546.868 | 22171.7644
| WSC FET |  |  |  |  | 3000 | 3000
WSC SE
WSC SA
WSC ISSE
| GSFC CTA |  |  |  | 500 | 500 | 1000
| Qwaltec | [8 empty] | 1500 | 1500 |  | 1500 | 1500
| ai Solutions | [8 empty] | 1500 | 1500 |  |  |  |  | 6000 | 6000
| Travel Total | 5871 | 0 | 0 | 500 | 4606.1325 | 17300.8993 | 0 | 10836.3937 | 15557.8323 | 58538.9658 | 12557.8323 | 15779.2709 | 30691.8422 | 9319.1398 | 24638.2797 | 56546.868 | 22171.7644
Note on F24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on G24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on H24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on I24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on J24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on K24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on L24: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Assumes 3 new hires get clearances in and start work in Jan 20
Note on G55: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: FET for SV Training at NGIS
Note on H55: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: FET support at ETE/RF compat
Note on F59: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local travel to NGIS
Note on G59: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local Travel to NGIS
Note on H59: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local travel to NGIS
Note on K60: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal
Note on L60: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal
Note on N60: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal
Note on O60: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal

## Mar 21
|  | GFY 20 | [11 empty] | GFY 21
|  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21
| SV Milestones | [5 empty] | SV Tng |  |  | ETE 2 RF Compat |  |  |  | ETE 3 |  |  | ETE 4 'Ship SV | FRR LRR | Mar 25 ILC | NORR | LEOP Cmplt
| WBS 4 - SSOC | [8 empty] | B4.2 dev | B4.2 dev | B4.2 test | B4.2 FAT | B/4.2 SAT
| WBS 6 - I&T | [8 empty] | SGRT 3b
RF Compat
[10 empty] | EtE 2 |  |  |  | EtE 3 |  |  | EtE 4
| WBS 7 Ops Prep | [10 empty] | SOS 1 |  | SOS 2, 3 | SOS 4
[13 empty] | MR 1 | MR 2 |  | MR 3 | MR 4
[18 empty] | LR 1 | LR 2,3
|  | BATHTUB | [14 empty] | GS Freeze
Continued ops product dev, transfer of more responsibility to WSC FET. OJT. Coordination with NGIS.
TO189 / TO 216 WBS' |  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21
WBS 7 | OMI FOT | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 4
WBS 4 | OMI SE | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1
WBS 4 | OMI SA | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5
WBS 4 | OMI DEV | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 3 | 3 | 3 | 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
WBS 4 | ai Solutions | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1
WBS 7 | WSC TM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 7 | WSC FET | 0.5 | 0.5 | 0.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7
WBS 7 | WSC SE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
WBS 7 | WSC SA | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 7 | WSC ISSE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WBS 3 | GSFC CTA | [5 empty] | 0.5 | 1 | 2 | 2 | 0.5
WBS 7 | Qwaltec | [5 empty] | 1.1 | 1 | 1.1 | 1.5 | 1.4 | 1.7 | 1.7 | 1.2 | 1.8 | 2.2 | 1.4 | 1.1 | 0.5
| OMI Total | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 9.5 | 9.5 | 9.5 | 10 | 10 | 7.25 | 7.25 | 7.25 | 7.25 | 7.25 | 7.75 | 5.75
| WSC Total | 3.5 | 3.5 | 4 | 7 | 7 | 7 | 7 | 7 | 9.5 | 9.5 | 9.5 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 10.5
| GSFC Total | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Qwaltec Total | 0 | 0 | 0 | 0 | 0 | 1.1 | 1 | 1.1 | 1.5 | 1.4 | 1.7 | 1.7 | 1.2 | 1.8 | 2.2 | 1.4 | 1.1 | 0.5 | 0 | 0
| ai Solutions Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1 | 0
| Total | 7 | 7 | 7.5 | 10.5 | 10.5 | 12.1 | 12.5 | 13.6 | 23.5 | 21.9 | 21.7 | 22.7 | 22.2 | 22 | 22.4 | 21.6 | 21.3 | 20.7 | 19.75 | 16.25
TRAVEL |  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21
| OMI - WBS 4 | [5 empty] | 663.6795 | 0 | 0 | 0 | 0 | 0 | 0 | 13300.8993 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OMI - WBS 6 | [5 empty] | 0 | 0 | 0 | 13300.8993 | 0 | 0 | 0 | 13300.8993 | 0 | 0 | 11706.7983 | 0 | 0 | 0 | 0
| OMI - WBS 7 | [5 empty] | 442.453 | 0 | 0 | 0 | 0 | 10836.3937 | 12557.8323 | 28937.1672 | 12557.8323 | 14279.2709 | 17485.0439 | 9319.1398 | 18638.2797 | 50546.868 | 22171.7644
| WSC FET | [5 empty] | 3000 |  |  | 3000
WSC SE
WSC SA
WSC ISSE
| GSFC CTA | [6 empty] | 500 | 500 | 1000
| Qwaltec | [11 empty] | 1500 | 1500 |  | 1500 | 1500
| ai Solutions | [11 empty] | 1500 | 1500 |  |  |  |  | 6000 | 6000
| Travel Total | 0 | 0 | 0 | 0 | 0 | 4106.1325 | 500 | 500 | 17300.8993 | 0 | 10836.3937 | 15557.8323 | 58538.9658 | 12557.8323 | 15779.2709 | 30691.8422 | 9319.1398 | 24638.2797 | 56546.868 | 22171.7644
Note on H44: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: FET travel to NGIS for SV training
Note on K44: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: FET travel to NGIS to support RF Compat and ETE
Note on I48: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local travel to NGIS for RF compat
Note on J48: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local travel to NGIS for RF compat
Note on K48: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: CTA local travel to NGIS for RF compat
Note on N49: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission rehearsal
Note on O49: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission rehearsal
Note on Q49: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal
Note on R49: Zwick, David J. (GSFC-450.S)[Exelis, Inc.]: Mission Rehearsal